Csc

eff

Eighty-first session

Item 138 of the preliminary list*

Proposed programme budget for 2027

Proposed programme budget for 2027

Part II

Political affairs

Section 3

Political affairs

Special political missions

Estimates in respect of special political missions

Summary

The present report is the first addendum to the report of the Secretary-General on the proposed programme budget for 2027 under section 3, Political affairs, and contains information on the overall resource requirements of 36 special political missions authorized by the General Assembly and/or the Security Council.

The report describes the continued relevance and effectiveness of the contributions of special political missions to the prevention and resolution of violent conflict and to peacebuilding within an evolving global context and increasingly challenging operational environments. It further provides details on efforts undertaken and planned to strengthen a culture of efficiency in special political missions, including quantifiable savings achieved. The overall proposed resource requirements of special political missions for 2027 amount to $422,671,000 (net of staff assessment). The requirements include $3,259,100 to provide for the share of special political missions for the financing of the budget of the Regional Service Centre in Entebbe, Uganda, for the period from 1 July 2026 to 30 June 2027. Detailed information in respect of each special political mission is contained in three addenda to section 3, Political affairs (A/81/6 (Sect. 3)/Add.2, A/81/6 (Sect. 3)/Add.3, A/81/6 (Sect. 3)/Add.4) corresponding to three thematic clusters, with the resource requirements for the United Nations Assistance Mission in Afghanistan now incorporated into the report on thematic cluster III.

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Introduction |  |  | 3 |
| - Organization of reports…………………………………… |  |  | 4 |
| - Status of the extension or renewal of mandates |  |  | 4 |
| - Discontinuing or discontinued missions |  |  | 6 |
| - Delivering on mandates in an evolving global context |  |  | 6 |
| - Performance information |  |  | 6 |
| - Operating environment and key policy issues |  |  | 8 |
| - Evaluation activities |  |  | 11 |
| - Lessons learned from the closure of missions and transition planning |  |  | 11 |
| - Operational effectiveness and responsible stewardship |  |  | 13 |
| - Integration of services in the Regional Service Centre in Entebbe, Uganda |  |  | 13 |
| - Aligning human resources and capabilities with operational requirements |  |  | 15 |
| - Continued efforts to improve operational effectiveness |  |  | 19 |
| - Budget formulation and management of resources |  |  | 26 |
| - Proposed resource requirements for 2027 |  |  | 31 |
| - Financial resources |  |  | 31 |
| - Human resources |  |  | 54 |
| - Financial performance of special political missions for 2025 |  |  | 69 |
| Annexes |  |  |  |
| - Definitions |  |  | 71 |
| - Summary of follow-up action taken to implement decisions and requests made by the General Assembly in its resolutions 80/243A and 80/254, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly |  |  | 73 |

- Introduction

Special political missions continued to play a vital role in the maintenance of international peace and security by contributing to the prevention and resolution of violent conflict and to peacebuilding in some of the world’s most complex contexts. Special political missions undertake a wide spectrum of critical functions, from engaging in preventive diplomacy and supporting the implementation of peace agreements, to assisting Member States in the promotion of human rights, enhancing the meaningful participation of women, and advancing the engagement of youth and other marginalized constituencies in political and peace processes. They also play a key role in strengthening the partnerships between the United Nations and regional and subregional organizations. Across all these areas, special political missions cooperate closely with United Nations development, human rights and humanitarian entities to implement integrated and effective responses.

The appropriation for special political missions for 2026 amounted to $536.1 million, representing a decrease of 22.6 per cent compared with the 2025 appropriation of $693.0 million, due primarily to the implementation of efficiency measures under the UN80 initiative, as well as the liquidation and closure of three missions: the United Nations Assistance Mission in Iraq (UNAMI), the United Nations Transitional Assistance Mission in Somalia (UNTMIS) and the United Nations Mission to Support the Hudaydah Agreement (UNMHA).

The proposed budget for 2027 builds on the momentum of the UN80 initiative and aims to minimize resource growth, while continuing to pursue efficiencies where feasible. The proposed budget amounts to $422.7 million, representing a decrease of $113.5 million, or 21.2 per cent compared to the approved budget for 2026. The net decrease is attributable to: (a) a decrease of $121.5 million due the closure of the three missions noted in paragraph 2 above; and (b) an increase of $8.0 million attributable to the 36 continuing missions including an increase of $0.9 million for the share of special political missions in the cost of the Regional Service Centre (RSCE).  In terms of staffing, the proposed budget reflects an overall decrease of 89 posts and positions, including a reduction of four higher-level posts (D-1 and above).

The proposed budget reflects the collective effort of missions, supported by Headquarters, to maximize cost reductions and efficiency gains while maintaining effective mandate delivery. These efforts builds on a systematic process to enhance cost-effectiveness embarked upon by special political missions in the last few years, culminating in the launch in January 2025 of a strategic approach to a culture of efficiency. This initiative aims to transform discrete efficiency initiatives into a global, coherent, systematic, and consistent approach for all field missions. Efficiency initiatives resulted in actual savings of $16.8 million in 2025, while projected savings for 2026, initially estimated at $12.7 million (or 2.1 per cent of the approved 2025 budget) in the proposed budget, increased to reflect additional reductions of $96.3 million (or 15 per cent) under the revised estimates (A/80/400). The commitment to this culture of efficiency enables missions to reflect targeted efficiencies in their budget proposals for 2027 estimated at $14.7 million (or 3.6 per cent of the approved 2026 budget for these missions).

The full implementation of the programme budget continues to be impacted by the current liquidity situation. To operate within these liquidity constraints, cash conservation measures and hiring freezes have been implemented. For special political missions, the liquidity situation has also required that new and expanded mandates be accommodated largely within existing resources. This means that budget performance (and pattern of expenditures from the prior year) is no longer an indicator of mission requirements and implementation capacities.

In line with budgetary practices, any adjustments to the resource requirements emanating from additional mandates or changes in mandates will be presented to the General Assembly either as additional reports of the Secretary-General on estimates resulting from such changes of mandates, or as supplementary information or updates during the legislative review prior to the approval of budgets. Given the volatility of the security and operating environments of special political missions, should any changes from such environments significantly alter the planning assumptions and costing parameters applied in the current budget, and if such changes cannot be absorbed from existing resources, the consequent changes to either resource or staffing requirements will be brought to the attention of the General Assembly, as appropriate, in accordance with established practices and procedures, and pursuant to the financial regulations and rules of the United Nations.

- A.	Organization of reports

As per established practice, the budget requirements of special political missions are presented as addenda to Section 3, Political affairs, of the proposed programme budget, and organized in three thematic clusters. Details of the individual missions are further presented in the following reports:

(a)	Thematic cluster I: special and personal envoys, advisers and representatives of the Secretary-General (A/81/6 (Sect. 3)/Add.2);

(b)	Thematic cluster II: sanctions monitoring teams, groups and panels, and other entities and mechanisms (A/81/6 (Sect. 3)/Add.3);

(c)	Thematic cluster III: regional offices, offices in support of political processes and other missions (A/81/6 (Sect. 3)/Add.4).

One change to the organization of reports for 2027 is with regard to the United Nations Assistance Mission in Afghanistan (UNAMA). Previously, the budgets of UNAMA and UNAMI (now closed and undergoing liquidation), despite both being part of thematic cluster III, were presented separately in standalone reports. That was the result of a practice introduced in 2007, at a time when UNAMA and UNAMI collectively represented two thirds of the total resources for special political missions. It is recalled that the General Assembly in its resolution 59/276 endorsed the recommendations of the Advisory Committee on Administrative and Budgetary Questions (A/59/569/Add.1, paras. 6 and 7) that the magnitude and complexity of large political missions, such as UNAMA and UNAMI, created new challenges in respect of effective consideration of resource requirements for special political missions and that while maintaining the overall benefits of consolidated reporting for most special political missions, the Secretary General should consider ways and means to present the budgets of large missions in a manner that would be more suitable for their size and complexity. To facilitate consideration, the Advisory Committee on Administrative and Budgetary Questions was of the view that thought should be given to reorganize the report on special political missions so that the missions would be presented in clusters on the basis of thematic or regional considerations, as appropriate. Reflecting the evolution of mandates and resource requirements over the past two decades, particularly following the closure of UNAMI in 2025, the proposed budget for UNAMA is now comparable in size to those of other large missions within thematic cluster III. Accordingly, the budget requirements for UNAMA are integrated into the report on thematic cluster III, beginning from the 2027 budget period. This integration enables a more harmonized structure and presentation across missions of similar magnitude and size, as well as a more enriched presentation of resource requirements for all missions under thematic cluster III.

B.	Status of the extension or renewal of mandates

Of the 36 special political missions for which resource requirements are proposed for 2027, 15 have open-ended mandates, 9 have mandates extended into 2027 or later, and 12 have mandates expiring in 2026 and pending extension by the General Assembly or the Security Council, as detailed below:

(a)	Special political missions with open-ended mandates:

(i)	Mission of the Secretary-General’s Good Offices in Cyprus;

(ii)	Office of the Special Adviser to the Secretary-General on the Prevention of Genocide;

(iii)	Personal Envoy of the Secretary-General for Western Sahara;

(iv)	Support to the implementation of Security Council resolution 1559 (2004);

(v)	Office of the United Nations Representative to the Geneva International Discussions;

(vi)	Office of the Special Envoy of the Secretary-General for Syria;

(vii)	Office of the Special Envoy of the Secretary-General for the Horn of Africa;

(viii)	Office of the Special Envoy of the Secretary-General for the Great Lakes Region;

(ix)	Office of the Special Envoy of the Secretary-General for Yemen;

(x)	Office of the Personal Envoy of the Secretary-General for the Sudan;

(xi)	Support to the Security Council Committee established pursuant to resolution 1718 (2006);

(xii)	Office of the Focal Point for Delisting;

(xiii)	United Nations Regional Centre for Preventive Diplomacy for Central Asia;

(xiv) United Nations support for the Cameroon-Nigeria Mixed Commission;

(xv)	Office of the United Nations Special Coordinator for Lebanon;

(b)	Special political missions with mandates renewed or extended into 2027 or later:

(i)	Senior Representative for the Implementation of Security Council resolution 2792 (2025);

(ii) 	Panel of Experts on Libya;

(iii)	Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning Islamic State in Iraq and the Levant (ISIL) (Da’esh), Al-Qaida and the Taliban and associated individuals and entities;

(iv)	Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009);

(v)	Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction;

(vi)	Counter-Terrorism Committee Executive Directorate;

(vii)	United Nations Office for West Africa and the Sahel (UNOWAS);

(viii)	United Nations Regional Office for Central Africa (UNOCA);

(ix)   United Nations Integrated Office in Haiti (BINUH);

(c)	Special political missions with mandates expiring in 2026 pending extension into 2027 or later:

(i)	Office of the Special Envoy of the Secretary-General on Myanmar;

(ii)	Group of Experts on the Democratic Republic of the Congo;

(iii)	Panel of Experts pursuant to resolution 2745 (2024);

(iv)	Panel of Experts on Yemen;

(v)	Panel of Experts on South Sudan;

(vi)	Panel of Experts on Haiti;

(vii)  Panel of Experts on the Sudan;

(viii) Panel of Experts on the Islamic Republic of Iran;

(ix)	Panel of Experts pursuant to Security Council resolution 2713 (2023);

(x) 	United Nations Support Mission in Libya (UNSMIL);

(xi)	United Nations Verification Mission in Colombia;

(xii) United Nations Assistance Mission in Afghanistan (UNAMA).

C.	Discontinuing or discontinued missions

The mandate of UNAMI expired on 31 December 2025 pursuant to Security Council resolution 2732 (2024). The liquidation of UNAMI commenced on 1 January 2026 and is expected to be completed by 30 September 2026. Remaining liquidation activities will be transferred to the Department of Operational Support (DOS) in New York, while logistics and property management related activities will be undertaken by the United Nations Logistics Base (UNLB). The Kuwait Joint Support Office (KJSO) will be closed by 30 June 2026, with its clients transferred to RSCE.  Separately, on the issue of the missing Kuwaiti persons and missing Kuwaiti property not resolved upon termination of the mandate of UNAMI, the Security Council adopted resolution 2792 (2025) and requested the Secretary-General to appoint a senior representative to promote, support and facilitate efforts regarding the repatriation or return of all Kuwaiti and third-country nationals or their remains, as well as the return of Kuwaiti property, including the national archives. The new mission was established in 2026 under thematic cluster I, as previously reported in the revised estimates (A/80/6 (Sect. 3)/Add.7).

The mandate of UNTMIS is set to end on 31 October 2026 pursuant to Security Council resolution 2753 (2024). Its liquidation process will start on 1 November 2026 and be executed by a small residual team until 31 December 2026, jointly with the United Nations Support Office in Somalia (UNSOS).

The mandate of UNMHA ended on 31 March 2026, pursuant to Security Council resolution 2813 (2026) adopted in January 2026. In the same resolution, the Security Council requested UNMHA to start the transfer of its residual functions to the Office of the Special Envoy of the Secretary-General for Yemen. The liquidation budget of UNMHA and the proposal for transfer of residual functions to the Office of the Special Envoy were reported in the revised estimates (A/80/6 (Sect. 3)/Add.7). The liquidation process commenced on 1 April 2026 and is expected to be completed by 30 June 2026.

No resources are required for 2027 for the three discontinuing or discontinued missions.

- Delivering mandates in an evolving global context

  - Performance information

The special envoys and advisers appointed by the Secretary-General, presented under thematic cluster I, continued to offer good offices and to facilitate negotiations with a view to brokering and implementing peace agreements. The Office of the Special Envoy for the Great Lakes Region supported the implementation of the Peace, Security and Cooperation Framework for the Democratic Republic of the Congo and the Region, including through shuttle diplomacy and by providing support to the Regional Oversight Mechanism. The Special Envoy intensified engagements with regional and international stakeholders to prevent a regional spillover and maintain coherence and complementarity among the concurrent peace initiatives. Through sustained outreach, the Special Envoy helped ensure that African-led efforts were consistent with ongoing efforts under the Washington and Doha processes. The Special Envoy of the Secretary-General for Yemen engaged with a range of Yemeni stakeholders, with the aim of achieving de-escalation and maintaining the prospects for an inclusive, multitrack political process to end the conflict amid a significantly escalating situation. The Special Envoy for the Horn of Africa worked with regional leaders, Member States and partners to promote dialogue, advance preventive diplomacy and confidence‑building amid regional tensions, including through the establishment of structured engagement platforms.

The various sanctions monitoring teams, groups and panels, the Ombudsperson and the Focal Point presented under thematic cluster II continued to provide substantive support to the Security Council in the implementation of its respective sanctions regimes. By resolution  2819 (2026), the mandate of the Panel of Experts on Libya was renewed until 15 August 2027. In resolutions 2780 (2025) and 2804 (2025), the Council requested the Secretary-General to report on the implementation of the arms embargo on the high seas off the coast of Libya within 5 months of the adoption of the resolutions. The Secretary-General submitted his reports pursuant to those resolutions (S/2025/675 and S/2026/354, respectively. In addition, pursuant to resolution 2769 (2025), the Council authorized the frozen cash reserves of the Libyan Investment Authority to be invested in low-risk time deposits and in fixed financial instruments, subject to a notification and approval procedure by the Sanctions Committee established pursuant to resolution 1970 (2011) concerning Libya, and requested the Panel of Experts to assess the effect and performance of those investments in their annual final reports. The Security Council also mandated the Panel of Experts on Yemen to present two additional reports: the first regarding dual-use components and precursor chemicals and their direct or indirect sale, supply or transfer to Yemen, and the second on ways to improve information-sharing and flag State capacity to prevent vessels, suspected of violating resolution 2216 (2015), from entering Yemen. Pursuant to the process set forth in paragraphs 11 and 12 of Security Council resolution 2231 (2015), effective 27 September 2025, all provisions of resolutions 1696 (2006), 1737 (2006), 1747 (2007), 1803 (2008), 1835 (2008) and 1929 (2010) were re-applied in the same manner as they applied before the adoption of resolution 2231 (2015) on 20 July 2015. Accordingly, the Panel of Experts on the Islamic Republic of Iran was reinstated by the Security Council, and its 2026 budget was approved by the General Assembly in its resolution 80/254.

The United Nations Verification Mission in Colombia has implemented the adjustments to the mandate approved by Security Council resolution 2798 (2025), focused on verifying the implementation of the provisions of the Final Peace Agreement concerning comprehensive rural reform, the reintegration of former combatants, as well as their security, and that of communities in conflict-affected regions. The Mission accompanied the Government in the formulation of the rapid response plan adopted in October 2024 to accelerate the implementation of the Final Agreement, which includes the establishment of pacts between national and local authorities to accelerate the implementation of the development programmes with a territorial focus and to enhance their transformative potential in conflict-affected regions, as well as actions related to the comprehensive rural reform and security guarantees.

In Libya, in line with Libyan Political Roadmap, UNSMIL launched the Structured Dialogue with thematic groups on the economy, governance, security, as well as national reconciliation and human rights. Across the four tracks, the mission supported a series of meetings aimed at developing concrete recommendations. UNSMIL has also facilitated meetings between the Governance and Economy tracks of the Structured Dialogue and the relevant Berlin Process Working Groups in order for Libyans to convey first-hand their priorities and exchange views on international support needed to address critical reforms on strengthening governance.

In West Africa and the Sahel, UNOWAS led or supported several initiatives to prevent conflict, defuse election- and transition-related tensions, sustain peace and consolidate peacebuilding efforts. The Office continued efforts towards inclusive dialogue and open political processes, and intensified its support to nationally owned dialogue processes, including through engagement with civil society, youth and women. The Office worked closely with regional and subregional organizations to strengthen peace and security in the region and to safeguard regional integration. The mission continued to solidify its existing partnerships in the area of maritime safety and security in the Gulf of Guinea. In addition, the Office fostered cooperation between coastal States and Sahelian countries, enhancing collaborative efforts to counter the southward spread of terrorism and violent extremism conducive to terrorism.

In Haiti, BINUH developed the strategy requested through Security Council resolution 2743 (2024) in consultation with the government of Haiti, improving international support for a Haitian-led, Haitian-owned formula to restore democratic institutions, fostering participation of all sectors of Haitian society. The period saw the completion of the term of office of the Transitional Presidential Council and a peaceful handover of executive authority to the Council of Ministers on 7 February 2026.  BINUH provided advice and guidance to the Haitian Provisional Electoral Council on the main challenges of the electoral process. BINUH continued to mentor and advise the Haitian National Police (and the Penitentiary Administrative Directorate) on critical policing matters, including anti-gang and anti-kidnapping operations, intelligence, election security, judicial police, criminal investigations, weapons and ammunition management, gender, mainstreaming and gender equality, legal framework, and police integrity and oversight. In January 2026, the mandate of BINUH was renewed by the Security Council under resolution 2814 (2026), focusing on elections, disarmament, dismantlement and reintegration, human rights, and on eliminating the mandate on police while maintaining BINUH’s support to the judiciary and to helping to address prolonged pretrial detention, in addition to providing advisory support on the handling of high-risk individuals. In line with the provisions of paragraph (e) of the resolution 2793 (2025), UNSOH started providing, on a cost-recovery basis, mission support services to BINUH in support of the delivery of its mandate.

In Afghanistan, UNAMA continued to support dialogue between Afghan stakeholders, UNAMA and the international community on human rights, rule of law, governance and inclusion issues. Despite persistent restrictions on media freedoms, civic space and Afghans’ enjoyment of their human rights, most acutely affecting women, Afghans retained access to channels to express concerns and communicate priority needs, enabling their voices to inform discussions on protection of human rights, including the rights of women and girls, and advocacy for a coherent socio-economic, political and policy agenda. The Mission supported the counter-narcotics and private sector working groups under the Doha Process and facilitated the High-Level Coordination Forum and the Technical Level Coordination Forum with de facto ministries.

B.	Operating environment and key policy issues

1.	Women and peace and security

In line with the Secretary-General’s continued commitment to advocate for a minimum of onethird of women participants in mediation and peace processes, special political missions further advanced the full, equal and meaningful participation of women in peace and political processes and strengthened gender‑responsive conflict prevention, peacemaking and peacebuilding efforts. Gender advisers and gender focal points across special political missions continued to provide essential guidance to special representatives and envoys of the Secretary‑General, ensuring that gender analysis and multidimensional risk assessments were systematically integrated into political strategies, good offices engagements and reporting.

Following the launch of the Secretary-General’s Common Pledge for Women’s Full, Equal and Meaningful Participation in Peace Processes on 24 October 2024, efforts to broaden its uptake accelerated. As of December 2025, 43 mediating entities, including Member States, regional organizations and other mediation actors, had adopted the Pledge, which was initiated, developed and supported by DPPA to galvanize collective action to overcome persistent barriers to women’s participation. In Sudan, the Office of the Personal Envoy of the Secretary‑General facilitated civil society consultations on the protection of civilians, including a dedicated session with women’s groups, ensuring that women’s perspectives informed conflict‑resolution efforts and the Personal Envoy’s engagement with stakeholders.

The Office of the Special Envoy for the Great Lakes convened regular virtual coordination meetings with civil society organizations, women’s groups and youth representatives in the Democratic Republic of the Congo and the wider Great Lakes region. These consultations provided timely gender‑responsive analysis during the rapid escalation of M23 hostilities in North Kivu beginning in January 2025 and the subsequent advances in South Kivu. Insights from women and local actors were systematically incorporated into the Office’s political, security and economic assessments, ensuring that local realities and gendered impacts directly informed reporting and recommendations.

The Mission of the Secretary-General’s Good Offices in Cyprus continued to support women’s organizations and women‑led initiatives, bringing together women and bicommunal women’s groups from across the island. Emphasizing the centrality of women’s participation in peacemaking, the Office sustained facilitation of the Technical Committee on Gender Equality and advanced efforts to operationalize and further implement elements of the Action Plan to ensure women’s full, equal and meaningful participation in the settlement process. In 2025, the membership of the Technical Committees reached gender parity, reflecting sustained advocacy and benchmarks established under the Action Plan. The Committee also co‑developed, together with the Technical Committee on Environment, a project on climate change and women in science, technology, engineering and mathematics, examining and addressing the disproportionate impacts of climate change on women.

2.	Youth and peace and security

In the context of growing geopolitical tensions and constrained resources, the youth, peace and security agenda remains an important framework across the United Nations system. During the reporting period, the Security Council held one meeting on youth, peace and security and subsequently adopted resolution 2807 (2025), reaffirming the positive role of youth, including young women, in conflict prevention, peacebuilding, sustaining peace and recovery, and emphasizing the importance of their full, effective and meaningful participation in peace and security efforts. The Council also recognized the significance of the world’s youth population as a potential driver of stability and resilience, while expressing concern that young people remain among those most adversely affected by armed conflict and instability.

Special political missions, uniquely positioned to advance the youth, peace and security agenda through their direct engagement with affected communities and established relationships with political actors and civil society organizations, continued to support youth participation in political and peace processes and to strengthen engagement with young women and men as agents of positive change. In March 2025, UNSMIL convened a workshop in Tripoli bringing together youth representatives and officials from the Ministries of Youth and Labour under its YouEngage strategy. Participants identified priorities for reducing community violence, including expanded vocational training, economic opportunities, psychosocial support and strengthened local governance. The United Nations Regional Centre for Preventive Diplomacy for Central Asia, through its Preventive Diplomacy Academy, continued to build the capacities of young leaders and support alumni-led community initiatives aimed at addressing drivers of tension and strengthening dialogue across communities in Central Asia and Afghanistan.

Special political missions also supported youth-led initiatives addressing structural drivers of conflict and promoting social cohesion. In Somalia, the Promoting Inclusive Action in Peacebuilding project in Marka District, supported by the Secretary-General’s Peacebuilding Fund, used the joint rehabilitation and management of irrigation canals as an entry point to address resource-related tensions between communities. Youth from different communities were trained as “peace agents” and played a leading role in establishing inclusive water governance committees. The initiative contributed to a significant reduction in disputes over water resources and strengthened cooperation among communities, demonstrating the important role young people can play in advancing local conflict prevention and inclusive governance. In Afghanistan, amid continued restrictions on civic space, UNAMA conducted a series of youth consultations across the country in 2025 to facilitate engagement between Afghan youth and the United Nations. The consultations culminated in a Youth Roundtable held on 25 September 2025 that brought together participants from all regions of the country and ensured gender-balanced participation, including young women. Participants discussed issues affecting young people and shared perspectives on priorities and concerns regarding their future.

3.	Electoral assistance

During the reporting period, special political missions continued to provide electoral assistance to Member States where mandated or requested. In her capacity as the General Assembly-mandated focal point for electoral assistance, the Under-Secretary-General for Political and Peacebuilding Affairs receives requests aimed at supporting and strengthening the capacities of national electoral institutions. United Nations technical assistance and capacity-building were delivered in an integrated manner and, in many cases, alongside preventive diplomacy and conflict prevention efforts to foster consensus on electoral legal frameworks, promote inclusion and non-discrimination, and encourage broad participation. Missions with electoral mandates continued to ensure that electoral assistance activities were guided by the principles of respect for sovereignty, national ownership and sustainability, while promoting the participation of women, youth, persons with disabilities and other marginalized groups.

In Libya, municipal council elections remained an ongoing process spanning 2025 and continuing into 2026. Pursuant to Security Council mandates, the United Nations is providing technical and advisory support to the High National Elections Commission through UNSMIL and the integrated UN electoral support team. This includes support to voter registration systems, operational preparedness and institutional capacity, as well as assistance to the UN-facilitated political roadmap and Structured Dialogue aimed at resolving legal, institutional and governance obstacles to credible presidential and legislative elections.

In Somalia, UNTMIS provided technical assistance to the newly established National Independent Electoral and Boundaries Commission, including legal, operational, logistical and training support. The Mission assisted the Commission on the electoral legal framework, planning, logistics, candidate nomination procedures, women’s representation and ballot design. On 25 December 2025, the Commission conducted its first one-person, one-vote district elections in Banadir, Mogadishu, with technical support from UNTMIS. The Mission also delivered training sessions for civil society organization leaders in the Federal Member States on temporary special measures, electoral systems and electoral observation, and continued to provide technical advice for forthcoming district, state and federal electoral processes.

In Iraq, on 11 November 2025, Iraq held its sixth parliamentary elections since 2005 with the support of UNAMI. The elections took place in a generally peaceful environment, with no major irregularities reported, reflecting Iraq’s significant democratic progress. This marked the final electoral event supported by UNAMI. Over more than two decades, UNAMI assisted with 17 electoral processes, including six federal legislative elections, provincial polls, and elections in the Kurdistan Region. UNAMI’s support focused on strengthening the Independent High Electoral Commission, enhancing institutional capacity and procedures, and promoting trust through dialogue, inclusion, and transparency. In 2025, UNAMI’s electoral assistance continued to operate at the intersection of preventive diplomacy, technical advice, human rights, gender equality, and development.

4.	Safety and security

The majority of special political missions continue to operate in security environments which are characterized by their volatility and unpredictability, particularly within the context of highly complex local and regional events. Many missions deliver their mandates in areas of high-intensity military conflict or where the risks of terrorism, kinetic activity by armed groups, social unrest and high criminality require active mitigation, while in areas of relative stability, the situation may evolve to present serious safety and security threats.

In many locations mission personnel, assets and premises remain at considerable risk from security threats including through being in proximity to incidents where the Organization is not the intended target. In Haiti, BINUH operates in an environment where gang violence and criminality continue to affect international support to the country, while missions in Yemen again saw significant military activity in areas they operate. Other missions across countries including Afghanistan, Iraq, Somalia and Syria also continued to face evolving security challenges related to their day-to-day activities as well as to the drawdown of their presence in some cases.

While host Governments bear primary responsibility for the security of mission personnel, some lack the capacity to provide adequate protection, therefore special political missions continued to adapt to local conditions, undertaking active measures to ensure the continued effective delivery of their mandates and fulfilment of their operational objectives. In support of this approach, missions have adopted robust security measures, guided by ongoing and systematic risk management processes. These are founded on a process of continuous risk assessment, adjustment of profile and presence, along with the implementation of proactive mitigation measures, including through deploying United Nations armed civilian security personnel, guard units and other security modalities where necessary.

In all contexts the Department of Political and Peacebuilding Affairs (DPPA) and the missions’ leadership work closely with the Department of Safety and Security (DSS) and other entities to review and refine risk management strategies, including mitigation measures as needed, in order to minimize disruption to mandate implementation, including in support of the deployment of expert panels supporting Security Council committees.

C.	Evaluation activities

DPPA continued to support evaluations and audits, including those conducted by external oversight bodies such as the Office of Internal Oversight Services (OIOS), the Joint Inspection Unit (JIU), and the Board of Auditors as well as its own internal evaluations. When relevant, key findings, recommendations and lessons learned arising from these evaluations were shared with special political missions to strengthen and inform their mandate implementation, and have been factored in the programme plan for the upcoming period.

In 2025, OIOS completed an evaluation of conflict specific special political missions under thematic cluster I to assess the relevance, effectiveness and coherence of their contributions to mitigating the risk of violent conflict. The evaluation concluded that these missions were uniquely positioned to convene stakeholders and facilitate dialogue, drawing on their perceived legitimacy, credibility and impartiality. Missions engaged a broad range of actors, including parties to conflict, geopolitical stakeholders, intergovernmental bodies and civil society, and employed diverse modalities to support political processes in complex and evolving contexts. The evaluation also found that missions effectively leveraged partnerships within the United Nations system and with external stakeholders to expand the scope and reach of their activities. At the same time, the evaluation identified areas for improvement, notably the need to strengthen strategic planning to better respond to evolving mandates and operating environments, enhance inclusivity to support broader social buy‑in and the sustainability of peace processes, and improve inter‑mission collaboration by making more systematic use of existing information‑sharing mechanisms.

In 2025, DPPA provided support to the OIOS exercise on strengthening the role of evaluation and the application of evaluation findings on programme design, delivery and policy directives as well as the evaluation of the mandate implementation by UNAMA. Mission-specific evaluation activities are described, as applicable, under the specific missions in the three addenda to section 3, Political affairs (A/81/6 (Sect. 3)/Add.2, A/81/6 (Sect. 3)/Add.3, A/81/6 (Sect. 3)/Add.4).

D.	Lessons learned from the closure of missions and transition planning

DOS continues to systematically capture and apply lessons learned from mission closures and transitions to strengthen future planning and execution. Insights drawn from completed and ongoing closures are analyzed and fed back into policy, guidance, and operational frameworks, ensuring that institutional knowledge is retained and applied consistently. These lessons directly inform practical guidance materials, including the Senior Mission Leadership Closure Guide, as well as associated standard operating procedures, tools, and checklists. They are also embedded in tailored training programmes and learning modules for senior leadership, planners, and operational staff, helping to build capacity, mitigate risks, and promote orderly, cost-effective, and well-coordinated mission drawdowns across the Secretariat.

From 2025 to early 2026, lessons learned from past mission transitions and closures were integrated into the planning processes of the liquidation of UNAMI, UNTMIS and UNMHA.

In Iraq, in line with Security Council resolution 2732 (2024) and the Secretary-General’s Transition and Liquidation Plan (S/2024/966), UNAMI continued to implement its mandate and drawdown during its final year. By 2 April 2026, UNAMI formally handed over all of its premises to the Government of Iraq following environmental remediation, asset verification and the repatriation of the United Nations Guard Unit.. UNAMI will continue to undertake liquidation related tasks remotely, until 30 September 2026, after which all residual liquidation activities will be transferred to DOS.

In order to help preserve gains and sustain peace, in cooperation with Iraqi counterparts, UNAMI worked with the United Nations country team and relevant agencies, funds and programmes on a set of thematic priorities that could continue to be advanced in the post-mission phase. This included electoral assistance, as the Mission had worked in support of the Independent High Electoral Commission, which managed the smooth and effective conduct of the November 2025 Council of Representatives election.

To ensure uninterrupted security at the United Nations Integrated Compound in Baghdad, a new unarmed guard force recruited jointly by DSS and the United Nations Development Programme assumed full-time access and internal control duties on 15 December 2025, replacing UNAMI’s guard unit personnel.

Drawing from lessons learnt from past United Nations transitions, UNAMI undertook extensive efforts to support career transitions for staff separating from the Mission, including upskilling, reskilling, and other professional development initiatives. Its Training Unit, in close collaboration with the Capacity Development and Operational Training Service within DOS, organized multiple training events and hosted four job fairs – one each in Baghdad, Erbil, Mosul and Kirkuk – with dozens of private sector employers, attracting over 350 United Nations staff and personnel.

The United Nations Sustainable Development Cooperation Framework for Iraq for 2025-2029 was signed on 25 December 2025 by the Minister of Planning and the United Nations resident coordinator. In line with recommended practice, the framework incorporates residual tasks previously mandated to UNAMI, such as electoral assistance, human rights, women, peace and security, and climate security, and further aligns with the national priorities of economic diversification, social protection, climate and water resilience, good governance and the rule of law.

In Somalia, the phased two-year transition of the United Nations presence, as outlined in resolution 2753 (2024), continued to progress during the reporting period. The handover of responsibilities under the first phase (ended 31 October 2025) has been completed. A roadmap for the second and final phase of the transition, jointly developed by the Federal Government of Somalia and the United Nations, was endorsed by the Security Council in its resolution 2809 (2025) and is currently under implementation. The drawdown of UNTMIS is scheduled to be completed by 31 October 2026.

Following the adoption of the road map for the second phase of the transition, the Joint Technical Committee is meeting quarterly to monitor progress on all remaining UNTMIS tasks to be fully transitioned to the Federal Government, the country team and other stakeholders, and to address challenges and ensure that the implementation of the road map remains on track for the conclusion of the UNTMIS mandate by 31 October 2026.

This work has informed the development of the United Nations Sustainable Development Cooperation Framework for Somalia for the period 2026-2030, which has been aligned to support the implementation of the country’s national transformation plan. UNTMIS will support joint resource mobilization strategies of the joint Federal Government of Somalia and the United Nations country team through the use of existing pooled funds such as the Somali Joint Fund and the Secretary-General’s Peacebuilding Fund, as well as by reaching out to international financial institutions, other donors, and the Somali private sector.

The Council requested in its resolution 2786 (2025) a review of UNMHA with a view to delivering further efficiencies and structural coherence and coordination across United Nations missions in Yemen. After the arbitrary detention of dozens of UN national personnel (73 since 2021), the United Nations had to significantly narrow the operating environment for staff across Houthi-controlled areas as a mitigating measure to ensure staff safety and security. In response to heightened security risks in Houthi-controlled areas, in October 2025, UNMHA international staff temporarily relocated to Government-controlled areas, along with other United Nations international staff, from Houthi-controlled areas.

In its resolution 2813 (2026), the Council extended the mandate of UNMHA for a final two-month period until 31 March and requested that UNMHA residual tasks be transferred to the Office of the Special Envoy for Yemen. In February 2026, both UNMHA and the Office of the Special Envoy for Yemen jointly developed a transition plan and initiated the gradual handover of UNMHA’s core residual tasks to the Office of the Special Envoy for Yemen. A joint delegation from UNMHA and the Office of the Special Envoy for Yemen met with members of the Redeployment Coordination Committee in Hudaydah. Discussions focused on joint achievements by the Redeployment Coordination Committee, residual tasks and transition arrangements to the Office of the Special Envoy for Yemen. UNMHA and the Office of the Special Envoy for Yemen reiterated the commitment of the United Nations to continue supporting the implementation of the Hudaydah Agreement and the importance of sustained communication and cooperation in support of stability in Hudaydah and in Yemen. The delegation also met with Houthi de facto authorities in Sana’a, further developing the necessary transition arrangements, and preparing for the next phase of their partnership. UNMHA has also engaged with the United Nations country team, local authorities and other key actors to ensure a smooth handover to the Office of the Special Envoy for Yemen.

III. 	Operational effectiveness and responsible stewardship

A.	Integration of services in the Regional Service Centre in Entebbe, Uganda

Established in July 2010, the Regional Service Centre in Entebbe (RSCE) provides administrative, financial, procurement, logistical and information and communication technology (ICT) services to peacekeeping operations, special political missions and other client entities. The Centre also provides residual administrative and liquidation support to closed and liquidating missions, thereby safeguarding the Organization’s fiduciary responsibilities beyond mandate closure. Through the application of standardized processes, economies of scale and strengthened internal controls, the RSCE enables client entities in the discharge of their mandate while promoting efficiency, accountability and continuity of operations.

In 2026, in line with the recommendation of the ACABQ as endorsed by the General Assembly in resolution 78/294, RSCE adopted a phased, risk-based approach to assume responsibility for the provision of services to current client entities previously supported by the Kuwait Joint Support Office (KJSO). The full operational integration of these clients into RSCE service delivery arrangements will take effect on 1 July 2026, concurrent with the operational closure of KJSO. The transition was coordinated under the leadership of the Department of Operational Support and guided by dedicated governance and transition management arrangements, with a view to ensuring operational readiness, service continuity and an orderly transfer of responsibilities. The Secretariat considers this integration a significant milestone in its efforts to strengthen, standardize and consolidate shared service delivery, in line with the Secretary-General’s reform agenda and the requests from the General Assembly on centralized support functions.

As of 1 July 2026, RSCE will support 33 active client entities with combined annual budgets of approximately $4.3 billion. The transfer of KJSO clients will result in an increase in the number of active clients receiving full services. This level of service activities underscores the Centre’s critical role in enabling the effective and compliant implementation of mandates financed under both peacekeeping and regular budget resources.

In addition to supporting active mandates, the RSCE continues to perform residual liquidation functions for previous client missions whose mandates expired in previous periods, including the United Nations Integrated Transition Assistance Mission in Sudan (UNITAMS), the United Nations Integrated Peacebuilding Office in Guinea-Bissau (UNIOGBIS), where certain administrative support processes remain.  The Centre is also assuming responsibility for residual liquidation support for the United Nations Investigative Team to Promote Accountability for Crimes Committed by Da’esh/Islamic State in Iraq and the Levant (UNITAD), UNAMI, and UNMHA, all of which transitioned from the KJSO to the RSCE.

The proposed budget for RSCE for the 2026/27 period (see A/80/611) is currently under consideration by the General Assembly at the second part of its resumed eightieth session. In that budget, resources in the amount of $45,155,400 are proposed by the Secretary-General for the maintenance of the Centre for the period from 1 July 2026 to 30 June 2027, to be apportioned on a pro rata basis among the budgets of the Centre’s active client peacekeeping operations, as well as special political missions financed under section 3, Political affairs, of the regular budget. The Advisory Committee recommended that the proposed resources be increased by $756,200, from $45,155,400 to $45,911,600, for the maintenance of the Centre for the 12-month period from 1 July 2026 to 30 June 2027 (A/80/604/Add.4, para. 56). Towards this end, an amount of $3.3 million has been included in the proposed programme budget for 2027, representing the share of special political missions. This provision will be subject to a final adjustment to be made in accordance with the decision to be taken by the Assembly in the context of the budget of RSCE for the 2026/27 period, which is expected by the end of June 2026.

With regard to the Advisory Committee’s observation that the provision of a full suite of services to clients previously receiving limited services should be reviewed for possible streamlining (A/80/7/Add.10, para. 56), the Secretariat underscores that the RSCE is fully positioned to provide the complete range of non-location dependent services to all former KJSO clients.

B.	Aligning human resources and capabilities with operational requirements

Within the broader context of the UN80 initiative, improving efficiency, realigning functions and optimizing the way the Organization work are core considerations when undertaking workforce planning. For delivering on these expectations, having strategic workforce capabilities continue to be reinforced throughout the Organization. For example, the key capabilities for a UN 2.0, including data expertise, innovation capacity, digital dexterity and strategic foresight and leveraging behavioural science are priorities, along with strengthening capabilities in strategic communications. New generic job profiles covering these capabilities have been developed or are under development.

Proposals for reclassification and reassignment of existing functions in missions using these new profiles, especially when leveraging opportunities from upcoming retirements to create more junior-level posts to rejuvenate the workforce, are vital elements in advancing a workforce transformation. Particular attention is also paid to reducing the number of high-level posts (D-1 and above), with the proposed budget for 2027 comprising: the abolishment of one USG in Support to the implementation of Security Council resolution 1559 (2004), one D-1 in the United Nations Verification Mission in Colombia and one D-1 in BINUH; and the downward reclassification  of one D-1 post to the P-5 level in the Office of the Special Envoy of the Secretary-General for Syria.

Efforts continue to ensure that human resources policies are responsive to the needs of entities with a field presence. Specifically, the Office of Human Resources develops and revises administrative issuances, streamlined policies and procedures to respond to the needs of field entities and provides authoritative policy interpretation and advice on all human resources policies applicable to field entities, including in emergency and crisis situations, as well as during downsizing and reduction of staff exercises. The Office remains actively engaged in the work of the Human Resources Network Standing Committee on Field Duty Stations and the tripartite Working Group for the Review of Conditions of Life and Work in Field Duty Stations of the International Civil Service Commission (ICSC), which monitor matters related to the conditions of service of staff in the field, including rest and recuperation, danger pay, hardship classification and non-family designation of duty stations. As part of the Office’s participation in ICSC discussions, ongoing reviews are carried out for key field entitlements, including hardship allowance, non-family service allowance, mobility incentive, relocation package, danger pay and security evacuation allowance, as well as the methodology for setting post adjustment in field duty stations. The Office is actively engaged in the comprehensive review of the United Nations common system compensation package being conducted by ICSC pursuant to 77/256 A-B, which includes a full review of the compensation package for staff in field locations. The Office also conducts periodic salary surveys to establish and update salary scales for staff in locally recruited categories in field duty stations.

Promoting national capacities

Encouraging the use of national capacities has been a core area of focus in human resources management in special political missions. In line with the request of the General Assembly in its resolutions 61/276 and 66/264 for greater utilization of national staff, and through the guidance provided in the workforce planning nationalization guide issued in December 2021, special political missions reviewed their staffing requirements prior to the submission of the budget to determine the feasibility of nationalization, commensurate with the requirements of the missions and their respective mandates.

According to the workforce planning nationalization guide, when identifying opportunities for nationalization, special political missions use the following criteria: (a) identification of vacant international posts and positions, including United Nations Volunteer positions, which could be considered for conversion to national posts or positions; (b) in the case of any changes in mandate, determination of whether the function remains necessary to meet the objectives of the mission and maintain the international character of the operation; (c) assessment of whether there might be a perception of conflict of interest for the function; (d) determination of whether the function requires regular movement across international borders or lines of conflict; (e) determination of whether the function has security-related requirements that prohibit specific categories of staff; and (f) determination of the availability of talent in the local labour market, including the required knowledge and skills. The rate of nationalization is therefore dynamic and can be affected if there is a lack of qualifications in the local labour market, which tends to occur in conflict-affected areas where the local education system and pool of qualified candidates may have been disrupted.

The conditions and criteria for nationalization outlined above are further assessed against each mission’s operational context. Missions were encouraged to ensure that national staff are empowered and skilled to carry out the implementation of the mandate while ensuring that the international character of the mission is maintained.

Special political missions continued to make steady progress in the nationalization of posts . For 2027, it is proposed that two posts be nationalized in the United Nations Verification Mission in Colombia and one post in UNSMIL. In addition, eight additional national posts (six National Professional Officer and two Local level) are proposed to be established in UNSMIL reflecting the Mission’s efforts towards the promotion of national capacity for the delivery of its critical mandated activities, and one Local level in the United Nations Verification Mission in Colombia, as indicated in table 1.

Table 1

Proposed nationalization of functions and additional national posts for 2027

| Mission | Number | Original functional title of post | Proposed functional title of post |
| --- | --- | --- | --- |
| UNSMIL | 1 | Security Sector Reform Officer (P-3) | Associate Security Sector Reform Officer (National Professional Officer) |
| UNSMIL | 1 | – | Economic Affairs Officer (NPO) |
| UNSMIL | 1 | – | Associate Security Sector Reform Officer (National Professional Officer) |
| UNSMIL | 2 | – | Associate Public Information Officer (National Professional Officer) |
| UNSMIL | 1 | – | Associate Human Rights Officer (National Professional Officer) |
| UNSMIL | 1 | – | Medical Officer (National Professional Officer |
| UNSMIL | 1 | – | Supply Assistant (Local level) |
| UNSMIL | 1 | – | Information Technology Assistant (Local level) |
| United Nations Verification Mission in Colombia | 1 | Administrative Officer (P-3) | Administrative Officer (National Professional Officer) |
| United Nations Verification Mission in Colombia | 1 | Associate Training Officer (P-2) | Associate Training Officer (National Professional Officer) |
| United Nations Verification Mission in Colombia | 1 | – | Administrative Assistant (Local level) (new) |

Gender parity and geographical representation

The Organization is advancing efforts to achieving gender parity, guided by the principles of merit and fairness in all selection processes. Efforts are ongoing, with focus on strengthening recruitment, particularly through a proactive outreach, among other efforts. While financial constraints continue to cause temporary hiring restrictions, the Organization remains committed to pursuing existing efforts and expanding targeted engagement, especially for field-based roles in special political missions. Outreach strategies are being refined to maintain momentum and ensure a steady pipeline of diverse talent.

Improving living and working conditions in field duty stations remains a critical priority for the recruitment and retention of women and continues to be advanced through more targeted and practical interventions. Efforts are focused on strengthening the implementation of the Field-specific Enabling Environment Guidelines for the United Nations System, including by strengthening more consistent implementation across duty stations and promoting measurable improvement in safety, flexibility and inclusive workplace practices. Particular attention is being given to reinforce organizational culture and leadership accountability, informed by the results of the 2024 staff engagement survey, to address persistent gaps in workplace experience across field settings. At the same time, dedicated efforts are under way to strengthen workforce resilience, including through enhanced support for mental health and well-being of all staff, preventive psychosocial measures and the expansion of tools and guidance for managers to better support staff serving in hardship duty stations, who face heightened stressors and operational challenges.

The Secretariat remains committed to accelerating progress towards equitable geographical distribution in posts subject to geographical distribution and to promoting as wide a geographical basis as possible in the recruitment of staff for non-geographical posts, including those in special political missions and peacekeeping operations. Achieving equitable geographical distribution and greater geographical representation requires sustained and deliberate action, particularly in light of low applicant volumes from un- and underrepresented Member States, systemic challenges and legacy recruitment patterns.

As highlighted in the report of the Secretary-General on the Implementation of human resources management reforms: outlook for 2026–2029, structural issues in the staff selection system continue to hinder faster progress towards the equitable geographical distribution goal. In response, the Secretariat is advancing reforms to strengthen its staff selection framework. The implementation of the staff selection 2.0 initiative is progressing, aimed at enhancing the efficiency, transparency and consistency of recruitment processes and supporting more objective and skills-based selection decisions. Concurrently, the Secretariat has recalibrated its talent attraction approaches, including through the development of purposeful partnerships with Member States, universities and professional networks, with a focus on expanding outreach and translating such efforts into sustained improvements in geographical representation. These efforts are aimed at positioning the United Nations as an employer of choice and at cultivating diverse talent pipelines to meet both current and future workforce needs. This forward-looking approach is designed to ensure a continuous flow of qualified candidates and to strengthen workforce readiness. While substantive change will require time, benefits from this approach are already anticipated in the short to medium term. The Secretariat underscores the importance of adequate resources to sustain and scale talent outreach initiatives. Additional investments would enhance the Secretariat’s capacity to engage meaningfully with Member States and to implement outreach activities in support of equitable geographical distribution.

Generic job openings recruitment panels

Recruitment from global rosters remains a critical enabler for timely and high-quality staffing of civilian positions in special political missions.  Under the new staff selection system policy promulgated through the administrative instruction ST/AI/2025/2, the building and management of rosters is reinforced as the Secretariat’s primary mechanism for ensuring that qualified, gender-balanced, geographically diverse and multilingual personnel are readily available for rapid deployment to support mission mandates. Expert panels, which play a central role in the establishment and maintenance of global rosters for international recruited positions, are normally comprised of at least three members, including two subject matter experts at the same or higher level of the job opening, at least one woman and one member from outside the originating work unit. This composition enhances impartiality, consistency and the overall integrity of the assessment process. Expert panels, which mirror the constitution of assessment panels, will continue to convene in 2027 to assess and recommend candidates applying to Generic Job Openings in support of the roster-based recruitment by field missions. By centralizing the assessment function, the panels reduce the administrative burden on individual hiring managers while supporting the Human Resources Services Division of the Department of Operational Support in conducting high quality- and standardized evaluations. Roster selections continue to demonstrate their operational value as a fast-track recruitment modality: in 2025, 70 per cent of selections for international positions (Field Service level 4 to D-1) in field missions (special political missions and peacekeeping operations) were from rosters, compared with 37 per cent in the global Secretariat.

In 2027, through its Human Resources Services Division and in collaboration with roster-building partners across the Secretariat, DOS will continue to manage generic job openings across networks to ensure that the global rosters remain current diverse, and responsive to projected civilian staffing demands in special political missions. These efforts are further supported by enhanced assessment modalities, continued improvements to the Secretariat’s recruitment platform, and strengthened data-driven operational workforce planning methodologies to reinforce the timely deployment of high-quality personnel in support of evolving mission mandates.

Strengthening coherence and collaboration between pillars in special political missions

Depending on the context of the country and mission, the Deputy Special Representatives of the Secretary-General may have triple functions to perform, also serving as resident coordinators and humanitarian coordinators. Five special political missions, namely UNTMIS, the Office of the United Nations Special Coordinator for Lebanon, UNSMIL, BINUH, and UNAMA include Deputy Special Representatives of the Secretary-General, or Deputy Special Coordinators, who have the triple functions and serve also as resident coordinators and humanitarian coordinators in complex, multidimensional contexts. These deputies constitute the link between the political work of the special political mission and the United Nations entities implementing development and humanitarian activities in coordination with the mission. As Resident Coordinator, the incumbent is responsible for coordinating operations and activities relating to the United Nations country team and United Nations development activities, for ensuring that the activities of the United Nations country team are aligned with national priorities, as captured in United Nations cooperation frameworks, for providing oversight and transparency on joint activities of the United Nations country team and for mobilizing partnerships and financing in support of country efforts towards the achievement of the Sustainable Development Goals. The office of the resident coordinator supports those functions. As Humanitarian Coordinator, the incumbent is responsible for coordinating humanitarian plans and operations and for maintaining links with Governments and other parties, donors and the broader humanitarian community. The salaries and common staff costs related to the posts of Deputy Special Representative of the Secretary-General, Resident Coordinator and Humanitarian Coordinator are budgeted at 50 per cent of the total cost in the 2027 budgets of the respective special political missions, pursuant to General Assembly resolutions 59/296 and 72/279, with the other 50 per cent funded through the Development Coordination Office. In line with Security Council resolution 2594 (2021), the Secretariat continues to strengthen coherence and collaboration between the respective pillars in mission settings.

Appropriately sized and dedicated capacity in the mission structure is required to support the Deputy Special Representatives, Resident Coordinators and Humanitarian Coordinators in carrying out their cross-pillar function within the respective mission and to provide sufficient support for their role in coordinating the work of the various units reporting to them. Where needed, the Secretariat will apply the two criteria of its policy in ascertaining the level of support capacity for the Deputy Special Representatives of the Secretary-General, Resident Coordinators and Humanitarian Coordinators: (a) the number of units reporting to them; and (b) the number of substantive mandate points assigned to the office (see A/79/6 (Sect. 3)/Add.1, para. 79).

C.	Continued efforts to improve operational effectiveness

Air operations

The Secretariat has taken measures to seek efficiencies and enhance the utilization of air fleets, with guidance provided to inform staff in field missions with the requisite technical and operational oversight. The portfolio of standby air solutions, which include charter agreements, air ambulance services, aircraft services under letters of assist and other short-term agreements, is aimed at increasing the Secretariat’s agility and responsiveness in logistics by addressing, among other things, urgent requests for ad hoc requirements, and at providing improved, efficient and timely support.

In 2026, total approved resources for air operations for the 36 special political missions amount to $27.6 million, with planned utilization of approximately 2,903 flight hours (2,203 for fixed-wing aircraft and 700 for rotary-wing aircraft). For 2027, resources in the amount of $22.4 million are proposed for a total of 2,016 flight hours (1,406 for fixed-wing aircraft and 610 for rotary-wing aircraft). This represents a decrease of $4.7 million, or 17 per cent, in proposed resources, and a reduction of 887 flight hours, or 30.6 per cent, compared with 2026. Six missions (Office of the Special Envoy for Yemen, UNOWAS, UNSMIL, the United Nations Verification Mission in Colombia, BINUH and UNAMA) account for 99.4 per cent of the total projected air operations requirements for 2027.  The decrease in requirement is the result of: (a) the downsizing of the aviation fleet in the United Nations Verification Mission in Colombia through the discontinuation of the rental and operations of the fixed-wing aircraft and the reduction of one rotary-wing aircraft, owing to operational adjustments and optimization of fleet utilization; (b) reduced requirements in UNSMIL and UNAMA due to a decrease of flight hours in line with historical utilization rates; and (c) a review of the BINUH’s air operations arrangements following the deployment of UNSOH and the arrangements with UNSOH to utilize its air capabilities on a cost recovery basis in BINUH. The decrease is offset in part by increased requirements for the Office of the Special Envoy for Yemen reflecting a full-year provision in 2027, compared with nine months in 2026, following the transfer of UNMHA air operations contracts to the Office of the Special Envoy effective 1 April 2026.

Travel

The total resources proposed for official travel amount to $9.8 million, reflecting a decrease of $56,100, or 0.6 per cent, compared with the approved budget for 2026. While the reduction is modest, this reflects a level carefully considered after multiple years of reductions to resources under official travel. The travel plans are based on the principle that official travel will be undertaken only where it cannot be substituted by other means of communication, including videoconferencing. For the sanctions monitoring teams, groups and panels, the proposed budget for official travel of staff for 2027 takes into account the frequency of travel by the Chairs of relevant sanctions committees to countries and regions relevant to their respective sanctions regime, which requires support from Secretariat staff. The proposed budget for all sanctions expert groups or panels not based in New York provides for one trip by one Secretariat staff member to the relevant region to assist the Chair and/or the group or panel, as well as two trips by one staff member to assist the group or panel during the drafting of interim or midterm and final reports. In addition, the proposed budget for three of the groups or panels that are not based in New York includes one more trip by two Secretariat staff to a country relevant to the sanctions regime to conduct Security Council-mandated sanctions assessment missions.

The programme plans of the special political missions, as presented in the proposed programme budget under the thematic clusters, provide further information, when applicable, on how special political missions have incorporated good practices and increased the use of technology in their work, while also reflecting upon the challenges experienced where technology meets its limits and in-person travel is needed to meet demand and fill coverage gaps. Travel to provide good offices and mediation, conduct fact-finding, investigation and monitoring activities, verify compliance and conduct outreach, as well as provide training or capacity-building to national and local partners, remains an indispensable tool in carrying out the work of the special political missions in 2027.

With respect to the performance of special political missions against the 16-day advance purchase policy, the Secretariat is following the observations and recommendations of the Advisory Committee on Administrative and Budgetary Questions with respect to the need to put measures in place to enhance performance. The overall performance of all special political missions improved from 39 per cent in 2024 to 50 per cent in 2025, maintaining a sustained positive trend since 2019 (18 per cent).  Out of 37 missions in 2025, three achieved 100 per cent and majority of the remaining (22 missions) showed improved performance compared to 2024. This improvement reflected efforts across the Secretariat, including regular reminders to missions of their responsibility to monitor real-time performance against the advance purchase policy using corporate dashboards and to investigate performance drivers and solutions. As noted in the most recent report of the Secretary-General on standards of accommodation for air travel (A/79/628), key performance drivers across the Secretariat are: late submission of travel requests; travel requests that were not “right the first time” and require rework, adding to the processing time; travel by “external” travellers such as meeting participants and external experts over whom the Secretariat has less administrative control; and circumstances outside the entities’ control such as travel document delays or operational issues, including emergencies or exigencies of service. Actions entities have taken to improve performance include: preparing and monitoring quarterly travel plans; escalating late travel requests to senior leadership within the entity; and regularly communicating to staff the process to comply with the policy.

Mine action activities

In 2025, the Mine Action Service continued to support special political missions with a mine action component by providing assistance in planning, programme design, implementation, reporting, and representation.

In the field, mine action efforts contributed to mandate delivery primarily through the provision of technical advice and expertise to mission leadership and relevant national counterparts. Specifically, in UNAMA, the mine action component provided explosive ordnance threat assessments, advised and coordinated mitigation measures in support of humanitarian and development initiatives, including support to the Mine Action Technical Cell, which leads nationwide coordination, quality assurance, and management of data on hazardous area to keep the United Nations, partners, and the public informed of the explosive threat. In accordance with its mandate of as contained in resolution 2626 (2022) and reaffirmed by subsequent resolutions, UNAMA supports existing mechanisms to improve the overall security situation in Afghanistan, provide assessments of the explosive ordnance threat and its impact on civilians, including children, advise and coordinate explosive ordnance threat mitigation measures in support of humanitarian and development initiatives, support the coordination of the humanitarian mine action sector. As the UNAMA’s current mine action capacity is not sufficient to undertake mine action coordination at the national level, the ability of UNAMA to undertake its  mine action mandate depends on a functioning Mine Action Technical Cell. Amid declining funding for the sector alongside a growing reliance on the coordination and data function, UNAMA plans to provide direct support to sustain the Mine Action Technical Cell core functions in 2027.

In UNSMIL, efforts focused on capacity building of the Libyan Mine Action Centre and relevant national security institutions in explosive ordnance clearance and weapons and ammunition management. Mine action also supported ceasefire implementation through engagement with the 5+5 Joint Military Commission and military demining teams from both the west and east.

In UNMHA, prior to 2025, mine action  efforts  centered on technical guidance to improve coordination among local authorities and with international partners. Following UNMHA’s closure pursuant to Security Council resolution 2813 (2026), technical guidance on mine action and coordination support in Yemen will continue under the auspices of Office of the Special Envoy of the Secretary-General for Yemen.

Ratios for vehicles and information technology equipment

In its resolution 80/243 A, the General Assembly endorsed the recommendation of the Advisory Committee on Administrative and Budgetary Questions for special political missions to limit, to the extent possible, the acquisition of new vehicles and laptops pending a review of the composition of their ground fleets and laptop holdings in the context of reduced operational footprints (A/80/7/Add.10, para. 65).  The missions continue to monitor excess holdings of vehicles and plan to dispose of vehicles once they meet established criteria, including life expectancy or write-off thresholds, or to recommend their transfer to other missions where feasible and cost-effective.

In the above context, the holdings of vehicles and information technology equipment are proposed on the basis of the anticipated personnel incumbency levels planned for 2027, as opposed to the full authorized level of personnel. Table 2 provides the ratios for vehicles for all special political missions that have vehicle holdings, while table 3 provides the ratios for information technology equipment for all special political missions.

Table 2

Proposed allocation of light vehicles for 2026

|  | 2027 proposed personnela | Personnel adjusted for vacancy ratea | Standard allocationb,c | 2027 proposed holdings (budget)b,c | Variance (percentage) |
| --- | --- | --- | --- | --- | --- |
| Cluster I |  |  |  |  |  |
| Mission of the Secretary-General’s Good Offices in Cyprus | 9 | 8 | 3 | 3 | _ |
| Office of the United Nations Representative to the Geneva International Discussions | 3 | 2 | 1 | 2 | 100.0 |
| Office of the Special Envoy of the Secretary-General for Syria | 31 | 28 | 13 | 7 | (46.2) |
| Office of the Special Envoy of the Secretary-General for the Great Lakes Region | 18 | 15 | 6 | 6 | _ |
| Office of the Special Envoy of the Secretary-General for the Horn of Africa | 7 | 7 | 4 | 4 | _ |
| Office of the Special Envoy of the Secretary-General for Yemen | 64 | 56 | 18 | 19 | 5.6 |
| Subtotal | 132 | 116 | 45 | 41 | (8.9) |
| Cluster II |  |  |  |  |  |
| Panel of Experts pursuant to resolution 2713 (2023) | 1 | 1 | 2d | 2 | _ |
| Subtotal | 1 | 1 | 2 | 2 | _ |
| Cluster III |  |  |  |  |  |
| UNOWAS | 57 | 52 | 15 | 13 | (13.3) |
| United Nations Regional Centre for Preventive Diplomacy for Central Asia | 10 | 10 | 4 | 1 | (75.0) |
| United Nations support for the Cameroon-Nigeria Mixed Commission | 7 | 6 | 3 | 8 | 166.7 |
| Office of the United Nations Special Coordinator for Lebanon | 19 | 18 | 10 | 11 | 10.0 |
| UNOCA | 29 | 28 | 10 | 11 | 10.0 |
| UNSMIL | 252 | 226 | 65 | 54 | (16.9) |
| United Nations Verification Mission in Colombia | 516 | 454 | 107 | 130 | 21.5 |
| BINUH | 103 | 97 | 25 | 44 | 76.0 |
| UNAMA | 359 | 317 | 76 | 131 | 72.4 |
| Subtotal | 1 352 | 1 208 | 315 | 403 | 27.9 |
| Total | 1 485 | 1 325 | 362 | 446 | 23.2 |

a	Includes United Nations international staff, National Professional Officers, international United Nations Volunteers, military and police personnel (military observers, military police and civilian police officers), government-provided personnel and contractors.

b	Includes armoured vehicles except those earmarked or required for the exclusive use of close protection and certain security tasks. Excludes guard-forces-carrying and utility vehicles, buses and electric carts.

c	Based on standard equipment as outlined in the Standard Cost and Ratio Manual issued by the Department of Operational Support.

d	Takes into account requirements for the five experts.

The total proposed vehicle holdings for special political missions are 23.2 per cent higher than the standard allocation based on the Standard Cost and Ratio Manual. Provisions of new or replacement vehicles to missions take into consideration the operational circumstances, including the terrain and infrastructure in the area of operations, security considerations and the supply and availability of spare parts. Explanations for vehicle holdings that are higher than the standard allocation in specific missions are as follows:

(a)	The vehicle holdings for the Office of the United Nations Representative to the Geneva International Discussions are 100 per cent, or one vehicle higher than the standard allocation, and reflect the operational needs in both Tbilisi and Zugdidi, Georgia;

(b)	The vehicle holdings for the Office of the Special Envoy of the Secretary-General for Yemen are 5.6 per cent, or one vehicle higher than the standard allocation, and reflect operational needs;

(c)	The vehicle holdings for United Nations support for the Cameroon-Nigeria Mixed Commission are higher than the standard allocation by 166.7 per cent or five vehicles higher, which reflects the need for dedicated transportation to support the movement of the joint technical teams and their security personnel along with all their logistics equipment while in the field. The presence of these vehicles allows for flexibility and the ability to move freely within the areas of operations, many of which are isolated and hard to reach and have limited infrastructure and unsafe conditions;

(d)	The vehicle holdings for the Office of the United Nations Special Coordinator for Lebanon are higher than the standard allocation by 10.0 per cent, or one vehicle, and reflect the operational need to support official meetings and engagement across Lebanon;

(e)	The vehicle holdings for UNOCA are higher than the standard allocation by 10.0 per cent, or one vehicle, and reflect operational needs;

(f)	The vehicle holdings for the United Nations Verification Mission in Colombia are 21.5 per cent higher than the standard allocation, which is attributable to: (i) an operational requirement for national Local level staff to utilize mission vehicles in a manner comparable to National Professional Officers and military observers to perform official duties, attend field activities, and support mandate implementation;

(g)	The vehicle holdings for BINUH are 76.0 per cent higher than the standard allocation, which is attributable to: (i) the need for mission personnel to self-drive to and from residences within the green zone following the transfer of mission support functions to UNSOH; and (ii) the need for frequent maintenance and repair caused by poor road conditions and the extensive time needed for repairs at outsourced workshops;

(h)	The vehicle holdings for UNAMA are 72.4 per cent higher than the standard allocation, which is attributable to: (i) the operational requirement for a pool of vehicles for Kabul to provide dispatch transportation for all staff in the Mission; (ii) provision of airport shuttle services; and (iii) vehicles to conduct driver testing. Notwithstanding, UNAMA is currently reviewing the holdings with the aim of achieving better alignment with the standard ratio, with consideration for its security and operational needs.

Table 3

Proposed allocation of computing devices for 2027

|  | 2027 proposed personnelb | Personnel adjusted for vacancy rateb | Computing devicesa |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Standard allocationc | Standard allocation and spares | 2027 proposed holdings (budget) | Variance (percentage) |
| Cluster I |  |  |  |  |  |  |
| Mission of the Secretary-General’s Good Offices in Cyprus | 13 | 12 | 12 | 14 | 14 | _ |
| Office of the Special Adviser to the Secretary-General on the Prevention of Genocide | 14 | 12 | 12 | 14 | 14 | _ |
| Personal Envoy of the Secretary-General for Western Sahara | 2 | 2 | 2 | 2 | 2 | _ |
| Support to the implementation of Security Council resolution 1559 (2004) | 2 | 2 | 2 | 2 | 2 | _ |
| Office of the United Nations Representative to the Geneva International Discussions | 4 | 3 | 3 | 4 | 4 | _ |
| Office of the Special Envoy of the Secretary-General for Syria | 65 | 62 | 62 | 71 | 80 | 12.7 |
| Office of the Special Envoy of the Secretary-General for the Horn of Africa | 7 | 7 | 7 | 11 | 11 | _ |
| Office of the Special Envoy of the Secretary-General for the Great Lakes Region | 30 | 27 | 27 | 49 | 33 | (32.7) |
| Office of the Special Envoy of the Secretary-General for Yemen | 130 | 117 | 117 | 142 | 160 | 12.7 |
| Office of the Special Envoy of the Secretary-General on Myanmar | 5 | 5 | 5 | 5 | 5 | _ |
| Office of the Personal Envoy of the Secretary-General for the Sudan | 7 | 5 | 5 | 7 | 7 | _ |
| Senior Representative for the Implementation of Security Council resolution 2792 (2025) | 2 | 2 | 2 | 2 | 2 | _ |
| Subtotal | 281 | 256 | 256 | 323 | 334 | 3.4 |
| Cluster II |  |  |  |  |  |  |
| Group of Experts on the Democratic Republic of the Congo | 1 | 1 | 1 | 1 | 1 | _ |
| Panel of Experts on the Sudan | 1 | 1 | 1 | 1 | 1 | _ |
| Support to the Security Council Committee established pursuant to resolution 1718 (2006) | 2 | 2 | 2 | 2 | 2 | _ |
| Panel of Experts on Libya | 2 | 2 | 2 | 2 | 2 | _ |
| Panel of Experts pursuant to resolution 2745 (2024) | 2 | 2 | 2 | 2 | 2 | _ |
| Panel of Experts on Yemen | 4 | 4 | 4 | 4 | 4 | _ |
| Panel of Experts on South Sudan | 3 | 3 | 3 | 3 | 3 | _ |
| Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities | 24 | 21 | 21 | 24 | 24 | _ |
| Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009) | 2 | 2 | 2 | 2 | 2 | _ |
| Panel of Experts pursuant to resolution 2713 (2023) | 9 | 9 | 9 | 9 | 9 | _ |
| Panel of Experts on Haiti | 3 | 3 | 3 | 3 | 3 | _ |
| Office of the Focal Point for Delisting | 3 | 2 | 2 | 3 | 3 | _ |
| Panel of Experts on the Islamic Republic of Iran | 3 | 2 | 2 | 2 | 2 | _ |
| Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction | 14 | 14 | 14 | 15 | 15 | _ |
| Counter-Terrorism Committee Executive Directorate | 48 | 43 | 43 | 48 | 48 | _ |
| Subtotal | 121 | 111 | 113 | 121 | 121 | _ |
| Cluster III |  |  |  |  |  |  |
| UNOWAS | 77 | 71 | 71 | 76 | 87 | 14.5 |
| United Nations Regional Centre for Preventive Diplomacy for Central Asia | 26 | 26 | 26 | 26 | 25 | (3.8) |
| United Nations support for the Cameroon-Nigeria Mixed Commission | 15 | 14 | 14 | 17 | 19 | 11.8 |
| Office of the United Nations Special Coordinator for Lebanon | 72 | 70 | 70 | 72 | 72 | _ |
| UNOCA | 42 | 35 | 35 | 54 | 56 | 3.7 |
| UNSMIL | 423 | 386 | 386 | 401 | 446 | 11.2 |
| United Nations Verification Mission in Colombia | 615 | 548 | 548 | 633 | 656 | 3.6 |
| BINUH | 116 | 108 | 108 | 130 | 139 | 6.9 |
| UNAMA | 836 | 755 | 755 | 1 038 | 1 063 | 2.4 |
| Subtotal | 2 222 | 2 013 | 2 013 | 2 447 | 2 563 | 4.7 |
| Total | 2 624 | 2 380 | 2 380 | 2 891 | 3 018 | 4.4 |

aIncludes desktop computers, laptops and netbook computers.

bIncludes international and national staff, United Nations Volunteers, United Nations police, United Nations military observers, government-provided personnel, military staff officers, international contractors and duty station-based experts.

c	Based on standard requirements as outlined in the Standard Cost and Ratio Manual.

Similarly, the guidelines issued by the Office of Information and Communications Technology (OICT) reinforced the “one computing device per user” policy as a best-practice reference to improve budget discipline, cost-effectiveness and alignment with Secretariat-wide ICT governance. Individual missions may deviate from the guidelines on the basis of operational requirements. Additionally, Missions have aligned their asset management practices with the updated lifecycle guidance issued by OICT, which extends the standard useful life of computing devices from four years to five-seven years. Decisions are based on assessments of security, operational, and performance considerations associated with operating devices beyond their traditional lifecycle. The total proposed computing device holdings for special political missions are 4.4 per cent higher than the standard allocation. Explanations for computing device holdings that are higher than the standard allocation in specific missions are as follows:

(a)	The computing device holdings at the Office of the Special Envoy of the Secretary-General for Syria are 12.7 per cent higher than the standard allocation, which is attributable to requirements for training purposes, security monitoring systems and servers;

(b)	The computing device holdings at the Office of the Special Envoy of the Secretary-General for Yemen are 12.7 per cent higher than the standard allocation, which is attributable to requirements for training purposes, conference and meeting rooms, and servers;

(c)	The computing device holdings at UNOWAS are 14.5 per cent higher than the standard allocation, which is attributable to additional holdings required to provide for training purposes, conference and meeting rooms, data transmission and connectivity and servers and the CarLog system;

(d)	The computing device holdings for United Nations support for the Cameroon-Nigeria Mixed Commission are 211.8 per cent or two computers higher than the standard allocation, which is attributable to additional holdings required to provide for training and meeting rooms;

(e)	The computing device holdings for UNOCA are 3.7 per cent or 2 computers higher than the standard allocation, which is attributable to requirements for servers;

(f)	The computing device holdings for UNSMIL are 11.2 per cent higher than the standard allocation, which is attributable to requirements for training, the CarLog system, data transmission and connectivity and servers;

(g)	The computing device holdings at the United Nations Verification Mission in Colombia are 3.6 per cent higher than the standard allocation, which is attributable to requirements for training purposes, Internet booths, data transmission and connectivity and servers;

(h)	The computing device holdings at BINUH are 6.9 per cent higher than the standard allocation, which is attributable to requirements for training purposes and servers;

(i)	The computing device holdings at UNAMA are 2.4 per cent higher than the standard allocation, which is attributable to additional holdings required to provide for training purposes, the CarLog system and servers, as well as provision for other personnel, including contractors.

The holdings are influenced by factors such as the need to provide for consultants and individual contractors, training facilities, Internet booths, information technology maintenance services, CarLog systems, programming of radios and fieldwork. Furthermore, based on the lessons learned during the coronavirus disease (COVID-19) pandemic, which saw a substantial increase in the use of virtual communications and remote working, it is critical to ensure the reliability of information technology equipment and infrastructure and their accessibility to all personnel, both staff and non-staff, to enable business continuity, mandate delivery and the safety and security of staff members, especially in the harsh environments where many special political missions operate.

The effective governance of information and communications technology (ICT) assets is a critical enabler of the Secretariat’s ability to deliver mandates efficiently, transparently and sustainably. OICT is advancing a Secretariat wide initiative to strengthen the integrity of ICT asset data recorded in Umoja, with the support of UNLB, Property Management and Inventory Control Unit of DOS and Global Asset Management Policy Service of the Field Operations Finance Division, DMSPC. This initiative is aligned with the ICT Strategy and is designed to support enterprise level visibility and oversight, while fully respecting the continued accountability of individual entities under the Delegation of Authority framework (ST/SGB/2019/2).

To this end, OICT is implementing a Global ICT Asset Management Project from 2026 to 2027. The objectives of this initiative are to: (a) establish an ICT Asset Lifecycle Management standard operating procedure (SOP) to harmonize how ICT assets are effectively managed across the Secretariat, leveraging on existing SOPs, guidance and practices already in place; (b) establish a reliable and authoritative dashboard in Umoja Analytics that provides visibility of ICT assets at both the enterprise and the entity levels; (c) improve the accuracy, completeness and integrity of ICT asset data in Umoja through data cleansing and validation; (e) enable analytical insights that support senior management and entity level decision making to support medium  and long term ICT planning; and (f) strengthen data governance and accountability related to ICT assets.

IV.		Budget formulation and management of resources

1.	Strengthening a culture of efficiency

The Secretariat continues to build on its strategic approach to developing and strengthening its culture of efficiency, launched in January 2025 at a Secretary-General’s seminar with all Special Representatives of the Secretary-General of peacekeeping and special political missions as well as Personal and Special Envoys of the Secretary-General. The theme of a culture of efficiency was once again on the agenda at the 2026 meeting, which stressed the importance of leadership in deepening the culture of efficiency at both the organizational and individual staff levels, especially in light of the particularly difficult financial environment for the Organization. The Field Operations Finance Division in the Department of Management Strategy, Policy and Compliance is collaborating with the Leadership Support Section of the Departments of Political and Peacebuilding Affairs and Peace Operations to plan further support to the Special Representatives of the Secretary-General of peacekeeping and special political missions to strengthen implementation of this culture of efficiency in the field, including by conducting webinars with mission senior leaders and sharing best practices across missions.

To support the strategic approach across missions, the Field Operations Finance Division has also: (a) organized global briefings and individual workshops with missions to guide them through the efficiency methodology; (b) collate each mission’s main efficiency initiatives into an aide-memoire to inspire and inform efforts across missions; (c) developed standardized templates for missions to calculate efficiencies, including one-time efficiency initiatives, initiatives requiring upfront investments, and related break-even points. Missions have been encouraged to continue reflecting and reporting on these and to consider adding or expanding others. This includes considering repurposing vacant or long vacant posts with the same mandate delivery or output. Missions were also requested to identify cost avoidance and cost reductions, which will involve taking proactive action to avoid future expenses, such as the inter-mission transfer of assets.

In quantifiable terms, enhancements in budgeting policy and efficiency initiatives resulted in actual savings of $16.8 million in 2025 for special political missions as compared to the $9.3 million projected. Similarly, the projected quantifiable savings and costs avoided amount to approximately $14.7 million for 2027, representing 3.6 per cent of the 2026 appropriation for the continuing missions. This represents sustainable savings for the Organization.

The major management improvements and efficiency measures applied and efforts to achieve sustained cost reductions and cost avoidance are reflected in the following areas:

      - civilian personnel, resulting from (i) the proposed abolishment of 61 posts and the downward reclassification of two posts (1 P‑5 and 1 P‑4) in UNAMA, reflecting targeted efficiency measures through organizational optimization, functional streamlining and improved resource allocation, (ii) the reduction of high level posts (D-1 and above), comprising the abolishment of 1 USG in Support to the implementation of Security Council resolution 1559 (2004), 1 D-1 in the United Nations Verification Mission in Colombia and 1 D-1 in BINUH, and the downward reclassification  of 1 D-1 post to the P-5 level in the Office of the Special Envoy of the Secretary-General for Syria, (iii)); the nationalization of two international posts (1 P‑3 and 1 P‑2) to National Professional Officers in the United Nations Verification Mission in Colombia, and (iv) the promotion of national capacity for the delivery of critical mandated activities in UNSMIL;

      - air operations, reflecting the discontinuation of the rental and operation of fixed‑wing aircraft and the consolidation of aviation requirements in the United Nations Verification Mission in Colombia; the establishment of a cost‑recovery arrangement for the use of air assets of the United Nations Support Office in Haiti (UNSOH) in lieu of a separate aviation contract in BINUH; and the use of commercial airlines in UNOCA in lieu of the use of special flights associated with its cost-shared fixed wing aircraft;

      - facilities and infrastructure, reflecting reduced fuel consumption for generators resulting from project upgrades in UNAMA and fuel‑optimization measures in UNSCOL; and

      - cost avoidance related to the non-acquisition of vehicles, equipment or supplies owing to the transfer of assets from UNIFIL in UNSCOL.

Further details of the efficiency measures achieved by mission are provided in the proposed budget reports of the respective thematic clusters.

Most missions are also reducing the proposed resources for official travel and are instead encouraging the use of virtual meetings where feasible, optimizing travel schedules, coordinating with partners to maximize impact while minimizing costs and prioritizing the use of online training options’ and the budgets also reflect economies of scale vis-à-vis the provision of materials and services and substantive support as part of mandated activities in the context of various cost-sharing arrangements.

2.	Improved budgeting methodologies

Within the framework of the Secretary-General’s UN80 Initiative, missions were requested to explore opportunities  to recalibrate their operations with a view to delivering mandates efficiently with reduced resources, while maintaining due regard for the security and safety of personnel and facilities. Maintaining the momentum, the formulation of the 2027 budget proposals emphasized enhanced discipline and accountability, supported by data-driven analysis.  In this context, the following principles were applied:

      - Enhancing the overall effectiveness by accommodating, where appropriate, the resource implications of new and expanded mandates within existing resources, with additional costs offset through efficiency gains, reprioritization or redeployment of existing resources;

      - Applying a data-driven approach to budget formulation, taking into account operational necessity, actual utilization and implementation capacity,  in the context of the current financial situation. This included analysis of the cancellation of prior period commitments and, where appropriate, the application of zero-based budgeting to reduce reliance on historic budget levels;

      - Adopting a multi-year perspective for construction planning and oversight of major capital projects, as well as a multi-year approach for asset management as a core component of mission budget planning, particularly with respect to air assets, and replacement planning for vehicles and information and communications technology projects; and

      - Prioritizing the use of existing assets, including the United Nations Reserve, strategic deployment stocks (SDS), the return, refurbishment and reuse programme (3R), and identified surplus property from other entities, prior to proposing the procurement of new items.

With respect to air operations, missions were requested to review carefully their requirements for air assets and to maximize opportunities for the sharing of air assets across missions, with support from the Department of Operational Support. The 2027 budgetary proposals reflect requirements for air assets that are assessed as necessary and well-utilized air assets. Budgeting for flight hours continues to be guided by the aviation budgeting policy introduced in 2025 and informed by the latest utilization data.

To strengthen oversight of ICT projects and activities and related resource requirements, the budget proposals from the special political missions were subject to review and technical clearance by the Office of Information and Communications Technology. The process is intended to support strategic planning, align demand plans with budget proposals and implementation capacity, avoid duplication of efforts and promote efficiency gains.

To ensure consistency and coherence, the proposed post actions adhere consistently to definitions pertaining to changes in staffing, and the proposals are fully justified in terms of changes in mandates or operational circumstances and workload requirements.

In addition, the Secretariat has ensured that all general temporary assistance positions are fully justified under each mission, providing the reasons for their proposed retention in 2027. In addition, no proposals have been made to convert these positions to regular posts. Should future assessment lead to a determination that such capacities should be regularized, proper proposals will be made in future budgets.

3.	Consistent application of the latest standard rates

With regard to international staff costs in field locations, the budgetary rates for net salary and staff assessment for 2027 were determined for each grade level and for each special political mission according to the following methodology:

(a)	With regard to international staff, the most recent salary scale, effective 1 January 2026, as approved by the General Assembly in its resolution 80/236, was used for net salary and staff assessment for each level in the Professional and higher categories. Similarly, the net base salary scale for staff in the Field Service category is adjusted, effective 1 January 2026 (in accordance with standing practice in line with the ICSC decision contained in A/45/30, para. 270 (e));

(b)	The step levels selected for each grade are based on the actual average step levels for each mission as at 31 December 2025, using actual incumbency data for international staff;

(c)	The post adjustment multiplier for each duty station as of April 2026 was applied to the net base salary rates.

With regard to national staff, the most recent salary scales as of April 2026 were used for net salary and staff assessment, with common staff costs as a percentage of net salaries, based on actual expenditure for the period from 1 January to 31 December 2025, applied to the average grade and step of national staff.

With regard to common staff costs, the actual expenditure from 1 January to 31 December 2025 was used to calculate common staff costs as a percentage of net salaries (inclusive of post adjustment but net of staff assessment) to determine the percentage of common staff costs for 2027. However, considering the significant and exceptional expenditures related to separation costs in the context of the two early separation programmes in 2025, actual expenditures for the period were adjusted to exclude one-time separation costs arising from the early separation programme exercises. A multi-year comparative analysis and a more detailed analysis by commitment item was used for each mission to determine if there were any other substantive or operational reasons for any significant changes.

With regard to danger pay, the proposed requirements reflect the discontinuation of danger pay, effective 1 April 2026, for all areas and duty station in Syria, and Benghazi and Sirte in Libya, as in line with the latest updates from the International Civil Service Commission (ICSC).

For United Nations Headquarters, offices away from Headquarters and the regional commission duty stations (New York, Geneva, Nairobi, Addis Ababa, Bangkok and Beirut), the standard costs for salaries and common staff costs for the programme budget were used.

With regard to military contingents (United Nations Guard Units), the latest single rate of reimbursement to countries contributing contingent personnel to United Nations field operations in the amount of $1,448 per person per month effective 1 July 2022, and the recreation leave allowance of $11.50 per day for up to 15 days of leave taken during each six-month period, as approved by the General Assembly in its resolutions 76/274 and 76/276, were applied. Reimbursement related to contingent-owned equipment is based on the rates adopted by the Assembly in its resolution 77/303. In this regard, the recommendations of the 2026 Working Group on Contingent-Owned Equipment (A/80/636) are currently under consideration by the General Assembly. Should the Assembly approve the recommended net average increase of 1.58 per cent in the wet lease rates for major equipment and the reimbursement rates for self-sustainment proposed to take effect on 1 July 2026, the related additional financial implications have not been included in the present budget proposal.

With regard to military advisers, observers, United Nations police and government-provided personnel, the latest applicable mission subsistence allowance rates for each country and mission area effective from 1 January 2026 were applied, as per the rates promulgated by the Office of Human Resources in December 2025.

With regard to experts, the estimates considered the latest fee ranges issued by the Office of Human Resources. The cost-of-living allowance for non-home-based experts in the Security Council sanctions committee panels and other support mechanisms, the latest monthly rates of $6,600 (New York) as approved by the Office of Human Resources, which took effect from 1 March 2023, have been applied to the five missions that have such requirements.

With regard to rental of premises in New York, the latest unit rate of $15,000 per person per year, effective 1 January 2025, has been applied to those missions accommodated on the Headquarters premises in New York.

With respect to fuel costs, the average price per litre for the different types of fuel in the six-month period from October 2025 to March 2026 have been used as the basis for calculating the provisions for fuel costs under the respective budget classes for 2027.

For ICT, the budget proposals also reflect the latest standard rates and service charges issued by the Office of Information and Communications Technology.

4.	Standardized methodology of budgeted vacancy rates

The Field Operations Finance Division provided guidance to all special political missions to improve the accuracy and consistency of the vacancy rate factors applied in the proposed budgets for 2027, to ensure that the proposed vacancy rates are based, as much as possible, on actual rates.

The proposed vacancy rates applied in the budget for 2027, for all types of personnel, have taken into account the experience to date. The assumptions considered for the proposed vacancy rates include: (a) the 12-month average vacancy rate from January to December in 2025; and (b) the actual vacancy rate as at 31 March 2026. The lower of the two was used as the budgeted vacancy rate.  For missions with a high number of abolitions included in the proposed 2027 budget, namely BINUH and UNAMA, the proposed vacancy rates for civilian personnel categories with abolishments were estimated using the total number of vacant posts and positions as of 31 March 2026 (exclusive of posts approved for phased abolishment in 2026), net of the number of posts and positions proposed for abolition. For the Office of the Special Envoy of the Secretary-General for Yemen, the proposed vacancy rates reflect their planned deployment during the period, following the closure of UNMHA. This is in line with the policy guidance to improve the accuracy and consistency of the vacancy factors applied in the proposed budgets for 2027 and to ensure that the proposed vacancy rates are based, as much as possible, on actual rates.

For proposed establishment of new posts or positions, or posts or positions proposed for reassignment, a vacancy rate of 50 per cent has been applied in the calculation of costs of such posts. In addition, a vacancy rate of 50 per cent has been used for posts proposed for conversion.

In addition, all special political missions were requested to take into full consideration the recommendations of the Advisory Committee on Administrative and Budgetary Questions and requests from the General Assembly that vacant posts and positions should be filled expeditiously. While efforts continue to fill vacant posts as expeditiously as possible, the current liquidity situation also requires careful planning of recruitment and onboarding to minimize the financial impacts.

The Field Operations Finance Division provided guidance to all special political missions to take the opportunity offered during the preparation of the 2027 budget to critically review long-vacant posts with a view to abolishing vacant posts that can be covered by existing capacities, or to propose reassignment or abolishment with the aim of facilitating the establishment of another function to address a more critical need, or to propose conversion to a national post.

Information on all posts vacant for more than two years and posts encumbered through special post allowances for more than one year is included in the supplementary information under each thematic cluster, which details the vacancy or special post allowance start dates, level and functional title of the posts, organizational unit and current status of recruitment, and provides justification for the retention of long-vacant posts.

5. 	Harmonization of budget presentation of cluster III missions

In line with the recommendation of the ACABQ as contained in A/59/569/Add.1, para. 6, that the Secretary-General should consider ways and means to present the budgets of large missions in a manner that would be more suitable for their size and complexity, the Secretariat has reassessed the optimum ways to present the budget requirements for UNAMA, in view of the evolution of mandates and resources over the last two decades. Given that UNAMA thematically belongs to cluster III, and its shares many similar characteristics with similarly-sized field missions under cluster III, the Secretary-General considers that integrating UNAMA into the report on thematic cluster III offers a more harmonized structure and presentation across missions of similar magnitude and size. This also leads to efficiencies in report production as well as reviews by the legislative bodies, in line with the objectives of the UN80 initiative.

At the same time, the presentation of cluster III has been further enhanced through the inclusion of addition tables, annexes and narratives. The key benefits of the adjustments include:

- Greater consistency: A harmonized structure and presentation across UNAMA and the other missions within thematic cluster III is expected to enhance clarity and improve comparability of information for Member States, the Advisory Committee, oversight bodies and the Secretariat, thereby supporting more efficient analysis and review.

- Fewer but higher-quality reports: A reduced number of reports, from five to four, and the corresponding outputs of the Advisory Committee is expected to streamline deliberations and ease the documentation burden for legislative bodies, including the Fifth Committee. It is further expected to enhance readability and generate savings in editorial, translation and text-processing costs.

- Maintained analytical depth: Detailed mission-specific budget information will continue to be provided to ensure full visibility of resource requirements and support informed oversight. In this regard, more focused and analytical information is presented in tabular format in both the fascicles and the supplementary information, including -summary views of and detailed data on all post actions by mission, as well as expanded financial information by class of expenditure.

6.	Improved presentation of financial performance

In response to the recommendations of the Advisory Committee on Administrative and Budgetary Questions (see A/80/7/Add.10, para. 70 and A/80/7/Add.1 para. 29) and endorsed by the General Assembly in it resolution 80/243 A, the Secretariat is continuing its efforts to enhance the financial performance reporting of the special political missions in the context of the present report, the financial performance report of the programme budget and the supplementary information provided for the special political missions. To this end, more comprehensive and detailed information on the financial performance is being provided. For supplementary information, analyses of variances for the performance and the proposed budget period are presented together in all relevant tables and sections. Information and justifications for unliquidated obligations and the cancellation of prior-period obligations is provided in table 6 and paragraphs 144 and 145 below, with further detailed information included in the financial performance report on the programme budget for 2025 (A/81/89) and the supplementary information.  In addition, for air operations, mine actions and construction projects for field-based special political missions under thematic cluster III, information has been included in the supplementary information for those missions, as is done for peacekeeping operations, in response to the recommendations of the Advisory Committee (see A/78/7/Add.1, para. 56).

Additional information on the evolution of financial resources by mission over the most recent five years is provided in table 11 of the present report. Additional information on the evolution of financial resources for each mission, broken down by budget class, over that period, including both appropriation and expenditure, is provided in the supplementary information for each thematic cluster, similar to the rest of the regular budget, in response to the recommendations of the Advisory Committee on Administrative and Budgetary Questions (see A/78/7, para. 7).

  - Proposed resource requirements for 2027

  - Financial resources

Proposed resources for 2027

The total proposed resource requirements for 2027 relating to the 36 continuing special political missions covered in the present report amount to $422.7 million net of staff assessment and are inclusive of the provision for the share of special political missions in the budget of RSCE. Overall, the resource level for 2027 reflects a decrease of $113.5 million, including the impact of closing missions (with a decrease of 577 posts and positions) compared with the appropriation for 2026. Details of the financial resource requirements by cluster, by mission and by category of expenditure are presented in tables 7 to 9, while the evolution of resources over the most recent five years is provided in table 11.

Table 7

Overview of financial resources by cluster

(Thousands of United States dollars)

|  | 2026 appropriationa | 2027 requirements |  | Variance |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Amount |  | Percentage |
|  | (1) | (2) | (3)=(2)-(1) |  | (4)=(3)/(1) |
| Cluster I | 51 367.6 | 56 331.2 | 4 963.6 |  | 9.7 |
| Cluster II | 36 431.4 | 37 726.8 | 1 295.4 |  | 3.6 |
| Cluster III | 324 549.9 | 325 353.9 | 804.0 |  | 0.2 |
| Subtotal (net of staff assessment) | 412 348.9 | 419 411.9 | 7 063.0 |  | 1.7 |
| Discontinuing and discontinued missionsb | 121 473.1 | – | (121 473.1) |  | (100.0) |
| Provision for the share of special political missions for the Regional Service Centre | 2 323.0 | 3 259.1 | 936.1 |  | 40.3 |
| Total (net of staff assessment) | 536 145.0 | 422 671.0 | (113 474.0) |  | (21.2) |

a	The 2026 appropriation of $536,145,000 includes an amount of $412,348,900 for the 36 continuing special political missions, an amount of $2,323,000 for the share of special political missions in the budget of RSCE, approved by the General Assembly in resolutions 80/243 A and 80/254.

b	The 2026 appropriation for these missions relates to: (i) the United Nations Transitional Assistance Mission in Somalia, the mandate of which expired 31 March 2026; (ii) the liquidation of UNAMI, approved by the General Assembly in resolution  80/243 A; and (iii) the United Nations Mission to Support the Hudaydah Agreement, the mandate of which expired 31 March 2026, approved by the General Assembly in resolution 80/254.

Table 8

Summary of resource changes between 2026 and 2027, by major factor

(Thousands of United States dollars)

|  | Amount | Comments |
| --- | --- | --- |
| Appropriation for 2026 | 536 145.0 |  |
| Technical adjustments | (682.9) | Provisions at continuing rates for posts and general temporary assistance positions established in 2026, with a 50 per cent vacancy rate, the phased abolishment of posts in 2026, as well as a full-year provision instead of nine months for operational costs in the Office of the Special Envoy of the Secretary-General for Yemen |
| New and expanded mandates (closure) | (121 473.1) | Changes in mandate attributable to the end of mandates of UNTMIS UNTMIS, pursuant to Council resolution 2753 (2024); and United Nations Mission to Support the Hudaydah Agreement pursuant to Council resolution 2813 (2026), and the liquidation of UNAMI |
| Other changes | 8 682.0 | Includes adjustments to reflect the latest salary rates and vacancy rates (22.7 million), latest contractual rates and latest standard rates, increased share for RSCE (0.9 million) and provision for cost recovery to UNSOH in BINUH following the discontinuation of mission support posts ($4 million); offset by the net impact of the abolishment and downward reclassifications of posts mostly in UNAMA, the United Nations Verification Mission in Colombia and BINUH (reduction of $10.8 million), reduced troop costs and revised lease contractual arrangement in UNSMIL ($5.4 million), the reconfiguration of aviation fleet in the United Nations Verification Mission in Colombia ($3.8 million), reduced requirements for air operations in BINUH ($1.4 million), and overall lower requirements for ICT services mainly due to reduced staffing levels and OICT rates ($1.7 million) |
| Total changes | (113 474.0) |  |
| Proposed programme budget for 2027 | 422 671.0 |  |

Table 9

Overview of financial resources by mission

(Thousands of United States dollars)

|  | 2025 |  |  | 2026 |  | 2027 |  | Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Appropriation | Expenditure | Appropriation |  | Requirements |  | Amount |  | Percentage |
| Mission | (1) | (2) | (3) |  | (4) |  | (5)=(4)-(3) |  | (6)=(5)/(3) |
| A. Continuing missions |  |  |  |  |  |  |  |  |  |
| Cluster I |  |  |  |  |  |  |  |  |  |
| 1. Mission of the Secretary-General’s Good Offices in Cyprus | 2 979.4 | 3 411.6 | 1 979.6 |  | 2 177.0 |  | 197.4 |  | 10.0 |
| 2. Office of the Special Adviser to the Secretary-General on the Prevention of Genocide | 3 386.7 | 2 718.3 | 3 263.4 |  | 3 118.4 |  | (145.0) |  | (4.4) |
| 3. Personal Envoy of the Secretary-General for Western Sahara | 502.7 | 313.9 | 529.8 |  | 544.1 |  | 14.3 |  | 2.7 |
| 4. Support to the implementation of Security Council resolution 1559 (2004) | 359.6 | 400.9 | 422.2 |  | 431.3 |  | 9.1 |  | 2.2 |
| 5. Office of the United Nations Representative to the Geneva International Discussions | 1 930.5 | 1 858.2 | 952.4 |  | 997.2 |  | 44.8 |  | 4.7 |
| 6. Office of the Special Envoy of the Secretary-General for Syria | 12 551.7 | 12 429.3 | 12 477.0 |  | 14 392.2 |  | 1 915.2 |  | 15.3 |
| 7. Office of the Special Envoy of the Secretary-General for the Horn of Africa | 2 056.1 | 1 786.6 | 1 918.4 |  | 2 013.0 |  | 94.6 |  | 4.9 |
| 8. Office of the Special Envoy of the Secretary-General for the Great Lakes Region | 4 941.7 | 4 760.3 | 4 724.7 |  | 4 940.3 |  | 215.6 |  | 4.6 |
| 9. Office of the Special Envoy of the Secretary-General for Yemen | 16 096.5 | 13 150.9 | 21 771.7 |  | 24 100.0 |  | 2 328.3 |  | 10.7 |
| 10. Office of the Special Envoy of the Secretary-General on Myanmar | 949.9 | 753.4 | 957.2 |  | 1 314.2 |  | 357.0 |  | 37.3 |
| 11. Office of the Personal Envoy of the Secretary-General for the Sudan | 1 282.4 | 1 309.3 | 1 979.8 |  | 1 702.6 |  | (277.2) |  | (14.0) |
| 12. Senior Representative for the Implementation of Security Council resolution 2792 (2025) | – | – | 391.4 |  | 600.9 |  | 209.5 |  | 53.5 |
| Subtotal, cluster I | 47 037.2 | 42 892.7 | 51 367.6 |  | 56 331.2 |  | 4 963.6 |  | 9.7 |
| Cluster II |  |  |  |  |  |  |  |  |  |
| 13. Group of Experts on the Democratic Republic of the Congo | 1 549.7 | 1 113.9 | 1 313.7 |  | 1 418.5 |  | 104.8 |  | 8.0 |
| 14. Panel of Experts on the Sudan | 1 132.6 | 436.6 | 1 145.3 |  | 1 186.0 |  | 40.7 |  | 3.6 |
| 15. Support to the Security Council Committee established pursuant to resolution 1718 (2006)a | 591.3 | 688.6 | 445.6 |  | 455.1 |  | 9.5 |  | 2.1 |
| 16. Panel of Experts on Libya | 1 376.4 | 1 092.8 | 1 529.7 |  | 1 574.4 |  | 44.7 |  | 2.9 |
| 17. Panel of Experts pursuant to resolution 2745 (2024) | 1 300.7 | 877.6 | 1 192.9 |  | 1 206.4 |  | 13.5 |  | 1.1 |
| 18. Panel of Experts on Yemen | 2 389.0 | 2 134.8 | 2 084.5 |  | 2 026.2 |  | (58.3) |  | (2.8) |
| 19. Panel of Experts on South Sudan | 1 435.4 | 1 123.8 | 1 504.1 |  | 1 538.3 |  | 34.2 |  | 2.3 |
| 20. Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities | 6 158.1 | 5 575.8 | 5 366.7 |  | 5 569.0 |  | 202.3 |  | 3.8 |
| 21. Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009) | 729.8 | 642.8 | 770.3 |  | 785.5 |  | 15.2 |  | 2.0 |
| 22. Panel of Experts pursuant to resolution 2713 (2023) | 1 960.2 | 965.6 | 1 421.3 |  | 1 477.1 |  | 55.8 |  | 3.9 |
| 23. Panel of Experts on Haiti | 1 553.0 | 1 427.9 | 1 731.8 |  | 1 744.1 |  | 12.3 |  | 0.7 |
| 24. Office of the Focal Point for Delisting | 774.8 | 510.3 | 680.7 |  | 731.2 |  | 50.5 |  | 7.4 |
| 25. Panel of Experts on the Islamic Republic of Iran | – | – | 2 432.4 |  | 2 511.4 |  | 79.0 |  | 3.2 |
| 26. Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction | 3 465.9 | 2 654.2 | 3 429.1 |  | 3 541.1 |  | 112.0 |  | 3.3 |
| 27. Counter-Terrorism Committee Executive Directorate | 12 815.7 | 10 977.9 | 11 383.3 |  | 11 962.5 |  | 579.2 |  | 5.1 |
| Subtotal, cluster II | 37 232.6 | 30 222.6 | 36 431.4 |  | 37 726.8 |  | 1 295.4 |  | 3.6 |
| Cluster III |  |  |  |  |  |  |  |  |  |
| 28. UNOWAS | 15 702.1 | 14 616.0 | 13 444.0 |  | 14 106.3 |  | 662.3 |  | 4.9 |
| 29. United Nations Regional Centre for Preventive Diplomacy for Central Asia | 3 555.7 | 3 204.7 | 2 890.0 |  | 2 979.9 |  | 89.9 |  | 3.1 |
| 30. United Nations support for the Cameroon-Nigeria Mixed Commission | 3 719.4 | 2 812.0 | 3 159.0 |  | 3 253.1 |  | 94.12 |  | 3.0 |
| 30. Office of the United Nations Special Coordinator for Lebanon | 11 122.4 | 10 322.5 | 9 709.3 |  | 10 386.8 |  | 677.5 |  | 7.0 |
| 31. UNOCA | 7 868.1 | 7 610.2 | 6 750.4 |  | 6 878.6 |  | 128.2 |  | 1.9 |
| 32. UNSMIL | 90 588.7 | 83 795.8 | 78 738.9 |  | 83 067.4 |  | 4 328.5 |  | 5.5 |
| 33. United Nations Verification Mission in Colombia | 86 582.3 | 74 109.1 | 71 752.4 |  | 75 896.9 |  | 4 144.5 |  | 5.8 |
| 35. BINUH | 35 705.0 | 33 266.2 | 32 329.8 |  | 31 614.9 |  | ( 714.9) |  | (2.2) |
| 36. UNAMA | 124 695.0 | 111 238.6 | 105 776.1 |  | 97 167.8 |  | (8 608.3) |  | (8.1) |
| Subtotal, cluster III | 379 538.7 | 340 975.1 | 324 549.9 |  | 325 353.9 |  | 804.0 |  | 0.2 |
| Subtotal, continuing missions | 463 808.5 | 414 090.4 | 412 348.9 |  | 419 411.9 |  | 7 063.0 |  | 1.7 |
| B. Discontinuing and discontinued missionsa |  |  |  |  |  |  |  |  |  |
| Implementation of Security Council resolution 2231 (2015) | 355.4 | 476.0 | – |  | – |  | – |  | – |
| UNTMIS | 100 177.3 | 86 934.3 | 86 646.8 |  | – |  | – |  | – |
| UNMHA | 31 002.1 | 23 893.4 | 11 618.7 |  | – |  | – |  | – |
| UNAMI | 95 399.1 | 104 657.1 | 23 207.6 |  | – |  | – |  | – |
| Office of the Special Envoy of the Secretary-General for Burundi | – | 46.8 | – |  | – |  | – |  | – |
| UNIOGBIS | – | 8.0 | – |  | – |  | – |  | – |
| Panel of Experts on Mali | – | 0.3 | – |  | – |  | – |  | – |
| UNITAD | – | 0.1 | – |  | – |  | – |  | – |
| C. Provision for the share of special political missions for RSCE | 2 298.8 | 2 298.8 | 2 323.0 |  | 3 259.1 |  | 936.1 |  | 40.3 |
| Total (A+B+C) | 693 041.2 | 632 404.9 | 536 145.0 |  | 422 671.0 |  | (113 474.0) |  | (21.2) |

a	The Office of the Special Envoy of the Secretary-General for Burundi and UNIOGBIS closed in 2021, the Panel of Experts on Mali closed in 2024 and UNITAD and UNITAMS closed in 2024,  Some payroll adjustments for separated staff were posted in 2025.

Table 10

Overview of financial resources by category of expenditure

(Thousands of United States dollars)

|  | 2025 |  |  | 2026 |  | 2027 |  | Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Appropriation | Expenditure | Appropriation |  | Requirements |  | Amount |  | Percentage |
| Category of expenditure | (1) | (2) | (3) |  | (4) |  | (5)=(4)-(3) |  | (6)=(5)/(3) |
| A. Continuing missions |  |  |  |  |  |  |  |  |  |
| I. Military and police personnel |  |  |  |  |  |  |  |  |  |
| 1. Military observers | 4 355.5 | 5 185.5 | 4 382.5 |  | 4 420.0 |  | 37.5 |  | (0.9) |
| 2. Military contingents | 6 744.1 | 6 590.6 | 6 609.0 |  | 5 109.0 |  | (1 500.0) |  | (22.7) |
| 3. United Nations police | 1 968.4 | 384.2 | 1 139.1 |  | 307.2 |  | (831.9) |  | (73.0) |
| Subtotal, military and police personnel | 13 068.0 | 12 160.3 | 12 130.6 |  | 9 836.2 |  | (2 294.4) |  | (18.9) |
| II. Civilian personnel |  |  |  |  |  |  |  |  |  |
| 1. International staff | 220 507.8 | 223 817.1 | 186 137.8 |  | 194 208.4 |  | 8 070.6 |  | 4.3 |
| 2. National Professional Officers | 23 832.3 | 25 009.0 | 20 070.8 |  | 22 959.0 |  | 2 888.2 |  | 14.4 |
| 3. National General Service staff | 39 674.6 | 43 427.7 | 34 667.9 |  | 36 598.7 |  | 1 930.8 |  | 5.6 |
| 4. United Nations Volunteers | 11 688.4 | 11 307.6 | 9 437.5 |  | 9 635.1 |  | 197.6 |  | 2.1 |
| 5. General temporary assistance | 2 758.7 | 2 939.3 | 3 080.2 |  | 3 929.0 |  | 848.8 |  | 27.6 |
| 6. Government-provided personnel | 277.0 | 114.2 | 234.4 |  | 401.3 |  | 166.9 |  | 71.2 |
| Subtotal, civilian personnel | 298 738.8 | 306 614.9 | 253 628.6 |  | 267 731.5 |  | 14 102.9 |  | 5.6 |
| III. Operational costs |  |  |  |  |  |  |  |  |  |
| 1. Experts | 12 537.7 | 8 256.3 | 11 919.3 |  | 13 690.4 |  | 111.5 |  | 0.8 |
| 2. Consultants and consulting services | 1 577.3 | 501.2 | 2 703.9 |  | 1 011.7 |  | (32.6) |  | (3.1) |
| 3. Official travel | 10 240.0 | 3 928.6 | 9 818.6 |  | 9 762.5 |  | (56.1) |  | (0.6) |
| 4. Facilities and infrastructure | 66 948.5 | 48 027.4 | 60 937.0 |  | 57 635.0 |  | (3 302.0) |  | (5.4) |
| 5. Ground transportation | 5 355.6 | 2 546.0 | 3 917.4 |  | 4 403.6 |  | 486.2 |  | 12.4 |
| 6. Air operations | 22 191.4 | 13 638.7 | 27 571.1 |  | 22 433.3 |  | (5 137.8 |  | (18.6) |
| 7. Marine operations | 177.0 | 63.7 | 462.0 |  | 340.3 |  | (121.7) |  | (26.3) |
| 8. Communications and information technology | 20 673.7 | 12 615.2 | 18 516.6 |  | 16 729.1 |  | (1 787.5) |  | (9.7) |
| 9. Medical | 2 167.8 | 685.7 | 1 935.8 |  | 1 588.2 |  | (347.6) |  | (18.0) |
| 10. Other supplies, services and equipment | 10 132.7 | 5 052.4 | 8 758.0 |  | 14 200.1 |  | 5 42. |  | 62.1 |
| 11. Quick-impact projects | – | – | 50.0 |  | 50.0 |  | — |  | — |
| Subtotal, operational costs | 152 001.7 | 95 315.2 | 146 589.7 |  | 141 844.2 |  | (4 745.5) |  | (3.2) |
| Subtotal, continuing missions | 463 808.5 | 414 090.3 | 412 348.9 |  | 419 411.9 |  | 7 063.0 |  | 1.7 |
| B. Discontinuing and discontinued missions |  |  |  |  |  |  |  |  |  |
| Mission for the implementation of Security Council resolution 2231 (2015) | 355.4 | 476.0 | – |  | – |  | – |  | – |
| UNTMIS | 100 177.3 | 86 934.3 | 86 646.8 |  | – |  | – |  | – |
| UNMHA | 31 002.1 | 23 893.4 | 11 618.7 |  | – |  | – |  | – |
| UNAMI | 95 399.1 | 104 657.1 | 23 207.6 |  | – |  | – |  | – |
| Office of the Special Envoy of the Secretary-General for Burundi | – | 46.8 | – |  | – |  | – |  | – |
| UNIOGBIS | – | 8.0 | – |  | – |  | – |  | – |
| Panel of Experts on Mali | – | 0.3 | – |  | – |  | – |  | – |
| UNITAD | – | 0.1 | – |  | – |  | – |  | – |
| C. Provision for the share of special political missions for RSCE | 2 298.8 | 2 298.8 | 2 332.0 |  | 3 259.1 |  | 936.1 |  | 40.3 |
| Total (A+B+C) | 693 041.2 | 632 404.9 | 536 145.0 |  | 422 671.0 |  | (113 474.0) |  | (21.2) |

Table 11

Evolution of financial resources, 2022–2027, by mission

(Thousands of United States dollars)

|  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025 |  |  | 2026 |  | 2027 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mission | Appropriation | Expenditure | Appropriation |  | Expenditure | Appropriation |  | Expenditure | Appropriation |  | Expenditure | Appropriation |  | Requirements |  |
| A. Continuing missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cluster I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Mission of the Secretary-General’s Good Offices in Cyprus | 2 955.0 | 2 523.5 | 3 036.3 |  | 2 840.4 | 3 056.5 |  | 2 901.0 | 2 979.4 |  | 3 411.6 | 1 979.6 |  | 2 177.0 |  |
| 2. Office of the Special Adviser to the Secretary-General on the Prevention of Genocide | 2 698.3 | 2 393.6 | 2 816.4 |  | 2 888.7 | 2 815.7 |  | 2 896.9 | 3 386.7 |  | 2 718.3 | 3 263.4 |  | 3 118.4 |  |
| 3. Personal Envoy of the Secretary-General for Western Sahara | 476.5 | 267.9 | 475.2 |  | 264.2 | 561.8 |  | 302.4 | 502.7 |  | 313.9 | 529.8 |  | 544.1 |  |
| 4. Support to the implementation of Security Council resolution 1559 (2004) | 338.6 | 393.4 | 372.2 |  | 299.2 | 414.2 |  | 172.1 | 359.6 |  | 400.9 | 422.2 |  | 431.3 |  |
| 5. Office of the United Nations Representative to the Geneva International Discussions | 2 045.0 | 1 745.4 | 1 950.0 |  | 1 770.4 | 2 032.1 |  | 1 719.7 | 1 930.5 |  | 1 858.2 | 952.4 |  | 997.2 |  |
| 6. Office of the Special Envoy of the Secretary-General for Syria | 16 132.6 | 12 630.3 | 15 001.6 |  | 12 817.6 | 13 660.7 |  | 12 188.7 | 12 551.7 |  | 12 429.3 | 12 477.0 |  | 14 392.2 |  |
| 7. Office of the Special Envoy of the Secretary-General for the Horn of Africa | 1 763.6 | 1 586.1 | 1 754.5 |  | 1 805.6 | 1 638.1 |  | 1 863.2 | 2 056.1 |  | 1 786.6 | 1 918.4 |  | 2 013.0 |  |
| 8. Office of the Special Envoy of the Secretary-General for the Great Lakes Region | 5 133.9 | 4 406.1 | 5 737.9 |  | 4 672.9 | 4 977.8 |  | 5 246.0 | 4 941.7 |  | 4 760.3 | 4 724.7 |  | 4 940.3 |  |
| 9. Office of the Special Envoy of the Secretary-General for Yemen | 17 202.0 | 16 240.6 | 17 051.3 |  | 16 087.0 | 16 570.8 |  | 14 928.7 | 16 096.5 |  | 13 150.9 | 21 771.7 |  | 24 100.0 |  |
| 10. Office of the Special Envoy of the Secretary-General on Myanmar | 1 153.5 | 1 223.8 | 1 408.6 |  | 1 084.7 | 1 365.3 |  | 805.1 | 949.9 |  | 753.4 | 957.2 |  | 1 314.2 |  |
| 11. Office of the Personal Envoy of the Secretary-General for the Sudan | – | – | – |  | – | – |  | – | 1 282.4 |  | 1 309.3 | 1 979.8 |  | 1 702.6 |  |
| 12. Senior Representative for the Implementation of Security Council resolution 2792 (2025) | – | – | – |  | – | – |  | – | – |  | – | – |  | 600.9 |  |
| Subtotal, cluster I | 49 899.0 | 43 410.8 | 49 604.0 |  | 44 530.7 | 47 093.0 |  | 43 023.8 | 47 037.2 |  | 42 892.7 | 51 367.6 |  | 56 331.2 |  |
| Cluster II |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. Group of Experts on the Democratic Republic of the Congo | 1 419.5 | 1 272.4 | 1 524.2 |  | 1 366.8 | 1 556.7 |  | 1 112.8 | 1 549.7 |  | 1 113.9 | 1 313.7 |  | 1 418.5 |  |
| 14. Panel of Experts on the Sudan | 1 073.1 | 956.9 | 1 120.4 |  | 1 012.0 | 1 151.5 |  | 894.3 | 1 132.6 |  | 436.6 | 1 145.3 |  | 1 186.0 |  |
| 15. Support to the Security Council Committee established pursuant to resolution 1718 (2006) | 3 094.5 | 2 943.9 | 3 110.6 |  | 3 065.8 | 3 407.9 |  | 1 454.1 | 591.3 |  | 688.6 | 445.6 |  | 455.1 |  |
| 16. Panel of Experts on Libya | 1 431.5 | 1 223.3 | 1 410.4 |  | 1 178.3 | 1 456.2 |  | 1 072.9 | 1 376.4 |  | 1 092.8 | 1 529.7 |  | 1 574.4 |  |
| 17. Panel of Experts pursuant to resolution 2745 (2024) | 1 163.8 | 789.2 | 1 193.2 |  | 890.6 | 1 281.6 |  | 893.7 | 1 300.7 |  | 877.6 | 1 192.9 |  | 1 206.4 |  |
| 18. Panel of Experts on Yemen | 2 302.2 | 1 926.2 | 2 210.0 |  | 2 106.1 | 2 307.7 |  | 1 985.3 | 2 389.0 |  | 2 134.8 | 2 084.5 |  | 2 026.2 |  |
| 19. Panel of Experts on South Sudan | 1 253.8 | 1 013.0 | 1 257.6 |  | 1 024.6 | 1 246.0 |  | 897.5 | 1 435.4 |  | 1 123.8 | 1 504.1 |  | 1 538.3 |  |
| 20. Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities | 5 871.5 | 5 827.5 | 5 854.9 |  | 6 091.6 | 6 516.9 |  | 5 729.2 | 6 158.1 |  | 5 575.8 | 5 366.7 |  | 5 569.0 |  |
| 21. Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009) | 668.1 | 621.3 | 617.3 |  | 778.3 | 711.1 |  | 718.5 | 729.8 |  | 642.8 | 770.3 |  | 785.5 |  |
| 22. Panel of Experts pursuant to resolution 2713 (2023) | 1 878.2 | 1 472.2 | 1 839.4 |  | 1 632.4 | 1 963.2 |  | 1 611.3 | 1 960.2 |  | 965.6 | 1 421.3 |  | 1 477.1 |  |
| 23. Panel of Experts on Haiti | – | 1.5 | 1 405.7 |  | 1 402.6 | 1 548.5 |  | 1 291.1 | 1 553.0 |  | 1 427.9 | 1 731.8 |  | 1 744.1 |  |
| 24. Office of the Focal Point for Delisting | – | – | – |  | – | – |  | – | 774.8 |  | 510.3 | 680.7 |  | 731.2 |  |
| 25. Panel of Experts on the Islamic Republic of Iran | – | – | – |  | – | – |  | – | – |  | – | 2 432.4 |  | 2 511.4 |  |
| 26. Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction | 3 137.7 | 2 598.2 | 3 135.5 |  | 2 280.1 | 3 415.1 |  | 2 442.1 | 3 465.9 |  | 2 654.2 | 3 429.1 |  | 3 541.1 |  |
| 27. Counter-Terrorism Committee Executive Directorate | 11 278.7 | 11 250.7 | 11 424.8 |  | 10 815.4 | 11 669.1 |  | 11 173.3 | 12 815.7 |  | 10 977.9 | 11 383.3 |  | 11 962.5 |  |
| Subtotal, cluster II | 34 572.6 | 31 896.3 | 36 104.0 |  | 33 644.6 | 39 421.9 |  | 31 276.0 | 37 232.6 |  | 30 222.6 | 36 431.4 |  | 37 726.8 |  |
| Cluster III |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28. UNOWAS | 14 658.6 | 14 526.5 | 14 835.2 |  | 14 806.1 | 15 900.1 |  | 14 699.8 | 15 702.1 |  | 14 616.0 | 13 444.0 |  | 14 108.5 |  |
| 29. United Nations Regional Centre for Preventive Diplomacy for Central Asia | 2 894.2 | 3 011.1 | 3 292.7 |  | 3 244.1 | 3 233.2 |  | 3 222.3 | 3 555.7 |  | 3 204.7 | 2 890.0 |  | 2 979.9 |  |
| 30. United Nations support for the Cameroon-Nigeria Mixed Commission | 3 525.0 | 3 686.8 | 3 781.3 |  | 3 542.3 | 3 821.7 |  | 3 022.7 | 3 719.4 |  | 2 812.0 | 3 159.0 |  | 3 253.1 |  |
| 31. Office of the United Nations Special Coordinator for Lebanon | 9 558.4 | 10 275.7 | 10 183.1 |  | 10 924.0 | 11 303.4 |  | 10 716.0 | 11 122.4 |  | 10 322.5 | 9 709.3 |  | 10 386.8 |  |
| 32. UNOCA | 8 530.1 | 8 044.2 | 9 074.1 |  | 8 158.5 | 8 410.5 |  | 7 695.3 | 7 868.1 |  | 7 610.2 | 6 750.4 |  | 6 878.6 |  |
| 33. UNSMIL | 69 262.0 | 82 340.9 | 88 046.5 |  | 86 197.7 | 87 763.6 |  | 85 563.5 | 90 588.7 |  | 83 795.8 | 78 738.9 |  | 83 067.4 |  |
| 34. United Nations Verification Mission in Colombia | 66 800.6 | 61 117.6 | 67 244.3 |  | 68 380.1 | 78 336.7 |  | 80 104.5 | 86 582.3 |  | 74 109.1 | 71 752.4 |  | 75 896.9 |  |
| 35. BINUH | 21 841.3 | 23 017.3 | 27 902.1 |  | 28 560.9 | 36 540.1 |  | 33 718.2 | 35 705.0 |  | 33 266.2 | 32 329.8 |  | 31 614.9 |  |
| 36. UNAMA | 131 390.3 | 134 130.3 | 132 479.2 |  | 129 065.0 | 127 324.7 |  | 116 932.9 | 124 695.0 |  | 111 238.6 | 105 776.1 |  | 97 167.8 |  |
| Subtotal, cluster III | 328 460.5 | 340 150.4 | 356 838.5 |  | 352 878.7 | 372 634.0 |  | 355 675.2 | 379 538.7 |  | 340 975.1 | 324 549.9 |  | 325 353.9 |  |
| Subtotal, continuing missions | 412 932.1 | 415 457.4 | 442 546.5 |  | 431 054.0 | 457 958.5 |  | 429 975.1 | 463 808.5 |  | 414 090.4 | 412 348.9 |  | 419 411.9 |  |
| B. Discontinuing and discontinued missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mission for the implementation of Security Council resolution 2231 (2015) | 1 392.6 | 1 230.6 | 1 533.5 |  | 1 397.4 | 1 190.4 |  | 959.6 | 355.4 |  | 476.0 | – |  | – |  |
| UNTMIS | 98 507.2 | 100 000.8 | 96 571.3 |  | 95 986.5 | 101 136.8 |  | 92 411.2 | 100 177.3 |  | 86 934.3 | 86 646.8 |  | – |  |
| UNMHA | 42 292.0 | 29 531.0 | 36 071.6 |  | 32 870.7 | 33 640.2 |  | 28 873.4 | 31 002.1 |  | 23 893.4 | 11 618.7 |  | – |  |
| UNAMI | 97 673.2 | 98 214.8 | 96 910.6 |  | 98 999.8 | 98 126.5 |  | 90 095.8 | 95 399.1 |  | 104 657.1 | 23 207.6 |  | – |  |
| UNITAD | 24 461.0 | 24 351.0 | 25 283.8 |  | 24 938.7 | 25 673.1 |  | 19 996.1 | – |  | – | – |  | – |  |
| UNITAMS | 56 319.6 | 56 649.0 | 66 128.0 |  | 62 391.3 | 22 162.6 |  | 17 834.7 | – |  | – | – |  | – |  |
| Panel of Experts on Mali | 1 144.7 | 852.6 | 1 148.6 |  | 690.9 | – |  | 0.3 | – |  | – | – |  | – |  |
| Office of the Special Envoy of the Secretary-General for Burundi | – | (20.3) | – |  | 78.7 | – |  | 84.5 | – |  | – | – |  | – |  |
| UNIOGBIS | – | 10.5 | – |  | 26.7 | – |  | 68.6 | – |  | – | – |  | – |  |
| OPCW-United Nations joint mission in the Syrian Arab Republic | – | – | – |  | – | – |  | 1.7 | – |  | – | – |  | – |  |
| United Nations Mission in Colombia | – | – | – |  | – | – |  | 23.7 | – |  | – | – |  | – |  |
| United Nations Electoral Observer Mission in Burundi | – | – | – |  | – | – |  | 1.4 | – |  | – | – |  | – |  |
| C. Provision for the share of special political missions for RSCE | 1 820.2 | 1 820.2 | 2 141.1 |  | 2 141.1 | 2 128.8 |  | 2 128.8 | 2 298.8 |  | 2 298.8 | 2 323.0 |  | 3 259.1 |  |
| Total (A+B+C) | 736 542.6 | 728 097.8 | 768 335.0 |  | 750 575.9 | 742 016.9 |  | 682 454.9 | 693 041.2 |  | 632 404.9 | 536 145.0 |  | 422 671.0 |  |

Variance analysis

Overall

The General Assembly in its resolutions 80/243 A and 79/254 approved resources in the amount of $536.1 million for special political missions for 2026.

The vacancy rates for 2026 were those included in the initial proposed programme budget and were not updated in the context of the revised estimates, as a result of the reduction in the number of posts and positions proposed for 2026. The magnitude of changes proposed, which included a combination of both vacant and encumbered posts, the impact of the ongoing recruitment freeze, the early separation programme exercises made it challenging to present updated proposed vacancy rates as part of the revised estimates proposal within the expected timeframes for the submission of the report.

As special political missions were not part of the recosting exercise carried out for the regular budget, the lack of update to the vacancy rates means that the 2026 appropriation was under-budgeted by $19.3 million, which was noted by the Advisory Committee in its report (A/80/7/Add.10, para. 26). This amount includes an estimated increase of $11.4 million for continuing missions (excluding UNTMIS and UNMHA), which had to be absorbed within the approved 2026 budget.

For 2027, the proposed budget amounts to $419.4 million, representing an increase of $7.1 million or 1.7 per cent, compared to the approved budget for 2026 for these continuing missions. Within this context, the special political missions are proposing to absorb $4.3 million of the estimated additional requirements of $11.4 million referred to in paragraph 123 above, through efficiency measures, reprioritization and the redeployment of existing post and non-post resources.

Cluster I

The proposed resource requirements for the 12 missions under thematic cluster I for 2027 amount to $56.3 million, representing a net increase of $5.0 million (9.7 per cent) compared with 2026. The overall increase is attributable primarily to: (a) increased requirements under civilian personnel, owing to the application of lower vacancy rates and revised salary rates; and (b) increased operational costs, mainly due to the provisioning of a full year in 2027, compared to nine months budgeted in 2026, of requirements under air operations for the rental and operation of one fixed-wing aircraft, and under facilities and infrastructure for the rental of premises and security services, for the Office of the Special Envoy for Yemen following the transfer as of 1 April 2026 of residual tasks previously performed by the United Nations Mission to Support the Hudaydah Agreement (UNMHA) pursuant to Security Council resolution 2813 (2026). The increase was offset in part by: (a) reduced requirements under communications and information technology, owing to lower needs for the acquisition of equipment and reduced subscription costs for periodicals and publications; and (b) reduced requirements underground transportation, owing to lower needs for rental of vehicles and spare parts.

Cluster II

The proposed resource requirements for the 15 continuing missions under thematic cluster II for 2027 amount to $37.7 million, representing a net increase of $1.3 million (3.6 per cent) compared with 2026. The overall increase is attributable primarily to: (a) increased requirements for civilian personnel resulting from the application of lower vacancy rates and the application of the latest salary rates; and (b) increased requirements for expert fees, reflecting changes in the budgeted average monthly fees based on the current composition of expert teams. The increase was offset in part by: (a) lower estimated common staff costs for national staff, based on actual past expenditures related staff entitlements; and (b) reduced requirements for communications and information technology, reflecting the non-recurrent provision for the acquisition of equipment included in the 2026 approved budget, as well as lower requirements for subscriptions to specialized databases and news resources to support and supplement investigations and research.

Cluster III

The proposed resource requirements for the nine continuing missions under thematic cluster III amount to $325.4 million, representing a net increase of $0.8 million f (0.2 per cent) compared with 2026. The overall increase is attributable primarily to increased requirements for civilian personnel resulting from the application of lower vacancy rates and the application of the latest salary rates. The increase was offset in part by reduced requirements: (a) resulting from the proposed net abolishment of 89 posts and positions, especially in UNAMA and BINUH; (b) the reduction of the BINUH’s footprint due to the handover of support functions to UNSOH and the downsizing of the mandate; (c) reduced rental and maintenance costs for the  premises in Tripoli based on latest contractual arrangement, as well as well as exclusion of a non-recurrent provision for security construction approved in 2026 in UNSMIL; (d) reduced requirements under air operations owing to the downsizing of the mission’s fleet by two aircraft in UN Verification Mission in Colombia, and a reduction in flight hours based on the latest utilization rates in UNSMIL and UNAMA; (e) lower communication carrier and connectivity costs, as well as reduced centralized services costs, resulting from efficiency measures taken since 2025 that included the lower staffing levels and the closure of 10 sub-regional offices in the UN Verification Mission in Colombia;  (f) reduced requirements for fuel for generators reflecting energy-efficiency measures and a reduced mission footprint following the closure and nationalization of field offices approved in 2026 in UNAMA; and (g) reduced requirements for military and police personnel resulting from the reconfiguration of deployments in UNSMIL and BINUH.

Share of the cost of the Regional Service Centre in Entebbe

The special political missions’ share of the cost of RSCE reflects an increase of $0.9 million, attributable mainly to an increase of the share of special political missions in the cost of the Centre, from 5.10 per cent in the 2025/26 period to 7.17 per cent in the 2026/27 period. This reflects the expanded client base of the Centre, following the integration of former clients of KJSO of which seven are continuing special political missions.

The variance analysis of each mission is further provided in table 12.

Table 12

Variance analysis, by mission

(Thousands of United States dollars)

| Mission | 2026 appropriation | 2027 requirements | Variance |  | Main contributing factors |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Amount | Percentage |  |
|  | (1) | (2) | (3)=(2)-(1) | (4)=(3)/(1) |  |
| A. Continuing missions |  |  |  |  |  |
| Cluster I |  |  |  |  |  |
| 1. Mission of the Secretary-General’s Good Offices in Cyprus | 1 979.6 | 2 177.0 | 197.4 | 10.0 | The increase is attributable primarily to the application of lower vacancy rates for international and national staff compared with the rates applied in 2026 and updated rates for salaries and common staff costs (excluding one-time costs). The increase is offset in part by reduced requirements for under communications and information technology for the maintenance of equipment and support services, adjusted to align with actual consumption, as well as for information and publication services, based on patterns of utilization in previous years, and (b) reduced requirements for ground transportation for the rental of vehicles and related costs, due to efforts to optimize expenditure. |
| 2. Office of the Special Adviser to the Secretary-General on the Prevention of Genocide | 3 263.4 | 3 118.4 | (145.0) | (4.4) | The decrease is attributable primarily to reduced requirements for civilian personnel, resulting from the application of a higher vacancy rate of 16.7 per cent for international staff, compared with 5.8 per cent applied in 2026; and lower estimates for common staff costs for national staff based on actual past expenditures. |
| 3. Personal Envoy of the Secretary-General for Western Sahara | 529.8 | 544.1 | 14.3 | 2.7 | The increase is attributable primarily to the application of the latest salary scales and higher estimates for common staff costs based on actual past expenditures, which is offset in part by the reduced requirements for facilities and infrastructure, owing to lower provisions for security services following the closure of the office for the Special Envoy in 2026, and spare parts and supplies in line with utilization patterns. |
| 4. Support to the implementation of Security Council resolution 1559 (2004) | 422.2 | 431.3 | 9.1 | 2.2 | The increase is attributable primarily to higher requirements for international staff resulting from the application of the latest salary scales and higher estimates for common staff costs based on actual past expenditures, which is offset in part by reduced requirements for national staff resulting from the application of lower estimates for common staff costs based on actual past expenditures. |
| 5. Office of the United Nations Representative to the Geneva International Discussions | 952.4 | 997.2 | 44.8 | 4.7 | The increase is attributable primarily to the establishment of one General Service post at a 50 per cent vacancy rate. The increase is offset in part by: (a) reduced requirements for international staff due to the application of a higher vacancy rate of 22.2 per cent compared with 16.7 applied in 2026, as well as lower salary cost following the proposed relocation of the Political Affairs Officer (P-3) from Geneva to New York, and (b) reduced requirements for telecommunication and network services, as well as software licenses, to align with actual consumption. |
| 6. Office of the Special Envoy of the Secretary-General for Syria | 12 477.0 | 14 392.2 | 1 915.2 | 15.3 | The increase is attributable primarily to: (a) the application of lower vacancy rates for international and national staff, compared with the rates applied in 2026; (b) the latest salary scales; and (c) higher estimates for common staff costs based on actual past expenditures. These increases are offset in part by the discontinuation of danger pay for all areas and duty station in Syrian as per latest updates from the International Civil Service Commission (ICSC). |
| 7. Office of the Special Envoy of the Secretary-General for the Horn of Africa | 1 918.4 | 2 013.0 | 94.6 | 4.9 | The increase is attributable primarily to: (a) higher requirements for civilian personnel, resulting from the application of a lower vacancy rate of zero per cent for international staff compared with 5.0 per cent applied in 2026, updated salary scales and higher estimates for common staff costs for international staff and National Professional Officer based on actual past expenditures; (b) increased requirements for communication and information technology, reflecting updated charges for centralized services provided by UNOAU which were not provisioned for previously, as well as higher telecommunication costs due to increased prices for local services; and (c) increased requirements under ground transportation for the lease of an electric vehicle to replace one of the four ageing vehicles, which is more than 18 years old |
| 8. Office of the Special Envoy of the Secretary-General for the Great Lakes Region | 4 724.7 | 4 940.3 | 215.6 | 4.6 | The increase is attributable primarily to: (a) the application of a lower vacancy rate for national staff of zero per cent compared with 12.5 applied in 2026; and (b) the application of the latest salary scales. The increase is offset in part by the reduced requirements under communications and information technology due to lower subscription costs for periodicals, resulting from a shift to a more cost-efficient co-financing arrangement; (c) reduced requirements for official travel, owing to lower ticket costs and daily subsistence allowance; and (d) reduced requirements for other supplies, services and equipment owing to lower requirements for individual contractors and other service |
| 9. Office of the Special Envoy of the Secretary-General for Yemen | 21 771.7 | 24 100.0 | 2 328.3 | 10.7 | The increase is attributable primarily to: (a) higher requirements for civilian personnel, resulting from the delayed impact of 27 new posts and positions approved in the 2026 budget at a 50 per cent vacancy rate for six months, application of lower vacancy rates for all category of civilian personnel, updated salary scales and higher estimates for common staff costs for national staff based on actual past expenditure; (b) increased requirements under operational costs primarily under facilities and infrastructure and air operations reflecting requirements to cover the full year of contractual responsibilities for the rental and security services for offices, premises and air craft previously cost-shared with UNMHA, rather than the nine months budgeted in 2026. These increases were partially offset by: (f) lower estimates for common staff costs for international staff based on actual past expenditures; (g) reduced requirements under ground transportation owing to lower needs for spare parts; and (h) decreased requirements under communications and information technology owing to lower requirements for the acquisition of communications and IT equipment. |
| 10. Office of the Special Envoy of the Secretary-General on Myanmar | 957.2 | 1 314.2 | 357.0 | 37.3 | The increase is attributable primarily to the application of lower vacancy rates for international and national staff; (b) updated salary scales; and (c) higher estimates for common staff costs based on actual past expenditures. |
| 11. Office of the Personal Envoy of the Secretary-General on the Sudan | 1 979.8 | 1 702.6 | (277.2) | (14.0) | The decrease is attributable primarily to the application of a higher vacancy rate of 16.7 per cent for international staff, compared with zero per cent applied in 2026. The decrease is offset in part by increased requirements for communication and information technology, reflecting updated charges for centralized services provided by UNOAU which were not provisioned for previously, as well as higher telecommunication costs due to increased prices for local services. |
| 12. Senior Representative for the Implementation of Security Council resolution 2792 (2025) | 391.4 | 600.9 | 209.5 | 53.5 | The increase is attributable primarily to the application of a lower vacancy rate of zero percent compared to 50 per cent applied in 2026, offset in part by reduced requirements under communications and information technology owing to the removal of the one-time provision for information and technology equipment approved in 2026. |
| Subtotal, cluster I | 51 367.6 | 56 331.2 | 4 963.6 | 9.7 |  |
| Cluster II |  |  |  |  |  |
| 13. Group of Experts on the Democratic Republic of the Congo | 1 313.7 | 1 418.5 | 104.8 | 8.0 | The increase is attributable primarily to higher requirements for civilian personnel owing to the application of a zero per cent vacancy rate for international staff compared with the rate of 50 per cent applied in 2026. The increase is offset in part by the lower requirements for expert fees based on the current composition of expert teams, as well as lower requirements for communications and information technology resulting from reduced cost-shared portion of subscriptions to specialized databases and news resources to support and supplement investigations and research. |
| 14. Panel of Experts on the Sudan | 1 145.3 | 1 186.0 | 40.7 | 3.6 | The increase is attributable primarily to increased requirements for expert fees based on the current composition of expert teams, as well as the increased civilian personnel costs resulting from the application of the latest salary rates. The increase is offset in part by the lower requirements under communications and information technology resulting from a reduced cost-shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 15. Support to the Security Council Committee established pursuant to resolution 1718 (2006) | 445.6 | 455.1 | 9.5 | 2.1 | The increase is attributable primarily to the increased international staff costs resulting from the application of the latest salary rates. The increase is offset in part by: (a) lower estimated common staff costs for national staff based on actual past expenditures; (b) and lower requirements under operational costs due to efficiency gains achieved through the consolidation of several rental spaces into a single flexible office space which negates the need for rental of office equipment. |
| 16. Panel of Experts on Libya | 1 529.7 | 1 574.4 | 44.7 | 2.9 | The increase is attributable primarily to the application of a zero per cent vacancy rate for national staff compared with 50.0 per cent applied in 2026 and the application of the latest salary rates. The increase is offset in part by the decreased requirements for expert fees based on the current composition of expert teams, as well as the lower requirements under communications and information technology resulting from a reduced cost-shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 17. Panel of Experts pursuant to resolution 2745 (2024) | 1 192.9 | 1 206.4 | 13.5 | 1.1 | The increase is attributable primarily to increased requirements for expert fees based on the current composition of expert teams, as well as the increased international staff costs resulting from the application of the latest salary rates. The increase is offset in part by the lower common staff costs for national staff based on actual 2025 expenditure patterns, compared with the rate applied in 2026, as well as lower requirements under communications and information technology resulting from a reduced cost shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 18. Panel of Experts on Yemen | 2 084.5 | 2 026.2 | (58.3) | (2.8) | The decrease is attributable primarily to: (a) lower requirements for expert fees based on the current composition of expert teams; (b) reduced requirements for danger pay at duty stations in Yemen; and (c) lower requirements under communications and information technology resulting from a reduced cost shared portion of subscriptions to specialized databases and news resources supporting investigations and research, as well as efficiency gains achieved and the increased reliance on internet-based communication technology. |
| 19. Panel of Experts on South Sudan | 1 504.1 | 1 538.3 | 34.2 | 2.3 | The increase is attributable primarily to increased requirements for expert fees, based on the current composition of expert teams, as well as the increased requirements under civilian personnel costs resulting from the application of the latest salary rates. The increase is offset in part by lower estimated common staff costs for national staff based on actual past expenditures and the lower requirements under information and communications technology resulting from a reduced cost shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 20. Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities | 5 366.7 | 5 569.0 | 202.3 | 3.8 | The increase is attributable primarily to: (a) the application of a lower vacancy rate for international staff compared with 2026; and (b) increased requirements for expert fees based on the current composition of expert teams. The increase is offset in part by: (a) reduced requirements for national staff resulting from the application of a higher vacancy rate compared with 2026; (b) reduced requirements for the rental of office equipment through the consolidation of several rental spaces into a single flexible office space; and (c) lower requirements under communications and information technology resulting from the application of the latest ICT standard rates and the increased reliance on internet-based communication technology. |
| 21. Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009) | 770.3 | 785.5 | 15.2 | 2.0 | The increase is attributable primarily to application of the latest salary rates, as well as higher requirements for expert fees based on the current composition of expert teams, offset in part by lower estimated common staff costs for national staff based on actual past expenditures. |
| 22. Panel of Experts pursuant to resolution 2713 (2023) | 1 421.3 | 1 477.1 | 55.8 | 3.9 | The increase is attributable primarily to: (a) higher requirements for expert fees based on the current composition of expert teams; (b) increased requirements under civilian personnel costs resulting from the application of the latest salary rates; and (c) increased requirements for telecommunications services resulting from the experts being home-based. The increase is offset in part by lower estimated common staff costs for national staff based on actual past expenditures, as well as the lower requirements under information and communications technology resulting from a reduced cost shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 23. Panel of Experts on Haiti | 1 731.8 | 1 744.1 | 12.3 | 0.7 | The increase is attributable primarily to higher requirements for expert fees owing based on the current composition of expert teams, as well as the increased requirements under civilian personnel costs resulting from the application of the latest salary rates. The increase is offset in part by lower estimated common staff costs for national staff based on actual past expenditures, lower requirements for security services reflecting reduced close protection support during visits to Haiti taking in to account the inter-mission cooperation with BINUH for the partial provision of such support, as well as the lower requirements under information and communications technology resulting from a reduced cost shared portion of subscriptions to specialized databases and news resources supporting investigations and research. |
| 24. Office of the Focal Point for Delisting | 680.7 | 731.2 | 50.5 | 7.4 | The increase is attributable primarily to lower requirements for civilian personnel costs owing to the application of a lower vacancy rate for international staff compared with 2026, offset in part by lower estimated common staff costs for national staff based on actual past expenditures as well as efficiency gains achieved through the discontinuation of fixed telephone communication services and increased reliance on internet-based communication technology. |
| 25. Panel of Experts on the Islamic Republic of Iran | 2 432.4 | 2 511.4 | 79.0 | 3.2 | The increase is attributable primarily to higher civilian personnel costs, reflecting the full-year cost of the P-3 general temporary assistance position, compared with six months approved in 2026, as well as the application of a lower vacancy rate of 41.7 per cent for international staff, compared with a vacancy rate of 50.0 per cent applied in 2026. The increase is offset in part by lower requirements under information and communications technology resulting from the exclusion of non-recurrent requirements approved in 2026 for the purchase of IT equipment |
| 26. Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction | 3 429.1 | 3 541.1 | 112.0 | 3.3 | The increase is attributable primarily to the application of a zero per cent vacancy rate for national staff, compared with 33.3 per cent applied in 2026, as well as the application of the latest salary rates for international staff. |
| 27 Counter-Terrorism Committee Executive Directorate | 11 383.3 | 11 383.3 | 579.2 | 5.1 | The increase is attributable primarily to higher civilian personnel costs, resulting from the application of the latest salary rates for international staff. The increase is offset in part by the application of 14.3 per cent vacancy rate for international staff compared with 14.0 per cent applied in 2026, and the application of 14.6 per cent vacancy rate for national staff compared with 8.3 per cent applied in 2026, as well as lower estimated common staff costs for national staff based on actual past expenditures. |
| Subtotal, cluster II | 36 431.4 | 37 726.8 | 1 295.4 | 3.6 |  |
| Cluster III |  |  |  |  |  |
| 28. UNOWAS | 13 444.0 | 14 108.5 | 664.5 | 4.9 | The increase is attributable primarily to: (a) increased requirements for civilian personnel costs due to the application of the latest salary rates and a lower vacancy rate of 10.5 per cent compared with the rate of 15.6 per cent applied in 2026 for international staff, offset in part by the application of higher vacancy rates for national staff compared with 2026; (b) a net increase in requirements under military observers due to the application of the latest mission subsistence rates; and (c) a combine and net increase in requirements under operational costs primarily due to:(a) higher fees for individual contractors and increased costs associated with the organization of events; (b) reduced requirements under facilities and infrastructure due to reduced staffing levels in 2026, as well as the closure of the UNOWAS presence in Mauritania; (c) reduced requirements for official travel resulting attributable primarily efficiency gains resulting from a review of the travel plans in light with the reduced number of staff in 2026; and (d) reduced requirements for ground transportation owing to lower estimated consumption of fuel. |
| 29. United Nations Regional Centre for Preventive Diplomacy for Central Asia | 2 890.0 | 2 979.9 | 89.9 | 3.1 | The increase is attributable primarily to higher requirements for civilian personnel costs, owing to the application of updated salary rates and increased estimated common staff costs (common staff costs as a percentage of salary costs) for all categories of personnel, based on actual past expenditures. |
| 30. United Nations support for the Cameroon-Nigeria Mixed Commission | 3 159.0 | 3 253.1 | 94.1 | 3.0 | The increase is attributable primarily to increased requirements for civilian personnel costs due to the application of the latest salary rates. The increase is offset in part by the (a) application of higher vacancy rates of 14.3 per cent, compared with 11.1 per cent applied in 2026 for international staff; and (b) the reduced requirements under operational costs due to the net effect of: (i) lower estimated contribution towards the United Nations House contribution in 2027 and reduced requirements for individual contractual services following to the closure of the office in Nouakchott; and (ii) an increase in facilities and infrastructure attributable primarily to increased contractual prices for cleaning and gardening services following the review of the minimum wages in the mission area and the appreciation of the local currency in Nigeria against the dollar, one-time maintenance costs for the offices in Yaoundé and Abuja, as well as additional requirements for security services based on utilization patterns and the inclusion of entity’s share of costs for the security services provided by the Department for Safety and Security. |
| 31. Office of the United Nations Special Coordinator for Lebanon | 9 709.3 | 10 386.8 | 677.5 | 7.0 | The increase is attributable primarily to is attributable primarily to higher requirements for civilian personnel costs, owing to the application of lower vacancy rates of 7.1 per cent for international staff and 1.9 per cent for national General Service staff, compared with 11.1 per cent and 5 per cent applied in the 2026 budget, respectively, as well as to higher estimated salary costs for National General Service staff. The increase is further attributable to a net increased in operational cost requirements resulting from: (a) higher requirements for public information and publication services, as well as higher requirements for telecommunications and network services related to leased line, video conferencing, and satellite services; (b) higher requirements for individual contractual services including photography and other services supporting joint activities related to the United Nations Communications Group aimed at enhancing awareness of its importance and implementation, as well as to expanded communications and outreach efforts following the planned closure of the United Nations Interim Force in Lebanon (UNIFIL); and (c) higher costs of repairs and maintenance and spare parts owing to an ageing vehicle fleet. The increase is offset by reduced requirements under facilities and infrastructure owing to reduced needs for furniture acquisitions, lower requirements for alterations and renovations, and lower estimated fuel consumption. |
| 32. UNOCA | 6 750.4 | 6 878.6 | 128.2 | 1.9 | The increase is attributable to increased requirements for civilian personnel costs due to application of the latest salary scales for international and national staff, as well as operational costs attributable primarily to prioritization of commercial airlines for official travel across the mission area as a more cost-effective logistics solution, in lieu of the use of special flights associated with the co-shared fixed-wing aircraft, and higher costs associated with the sustainment of the United Nations House, including maintenance and security services managed by the United Nations Development Programme. The increase requirements were offset in part by the removal of all provisions under air operation attributable to the non-utilization of the fixed wing during 2024 and 2025 owing to liquidity constraints and the high cost of special flights. |
| 33. UNSMIL | 78 738.9 | 83 067.4 | 4 328.5 | 5.5 | The increase requirements is attributable primarily to increased requirements for civilian personnel costs resulting from : (a) the application of the latest salary rates for international staff, National Professional Officers; (b) the application of the lower vacancy rates for international staff and national General Service staff, compared with the rates applied in 2026; (c) the proposed establishment of 10 posts (1 P-5, 1 FS, 6 National Professional Officers and 2 Local level). The increase in requirements are offset in part by reduced requirements under operational costs and military contingents attributable primarily to: (a) reduced rental and maintenance costs for the Mission’s premises in Tripoli based on latest contractual arrangement, as well as well as non-recurrent provision for security construction approved in 2026, (b) reduction in the flight hours for air operations based on the latest utilization rates; lower planned deployment of the United Nations Guard Unit personnel from 234 authorized strength to 167 and reduced costs for rotation of the Guard Unit personnel owing to the utilization of commercial airlines rather than charter flights. The decrease in operational costs was offset by additional requirements for individual contractors in line with operational requirements to support the establishment and sustainment of the field offices in Sabha and Benghazi as well as expansion of the UNSMIL activities related to organization of an additional mine action conference in line with the recommendation contained in the Strategic Review. |
| 34. United Nations Verification Mission in Colombia | 71 752.4 | 75 896.9 | 4 144.5 | 5.8 | The increase is attributable primarily to: (a) to higher requirements under civilian personnel costs owing to the application of lower vacancy rates for all category of personnel compared with the rates applied in 2026, together with updated salary scales and higher estimates for common staff costs for national staff based on actual past expenditures; and (b) higher requirements under military observers resulting from the application of the latest mission subsistence allowance rates. The increases are offset in part by a decrease in operational costs owing primarily to: (a) a decrease in requirements under air operations due to the downsizing of the mission’s fleet by two aircraft; (b) lower communication carrier and connectivity costs, as well as reduced centralized services costs, resulting from efficiency measures taken since 2025 that included the lower staffing levels and the closure of 10 sub-regional offices; (c) reduced requirements under marine operations reflecting a reduction in riverine activities following the closure of three sub-regional offices that relied on riverine vessels for missions transportation to locations not accessible by land. These decrease in operational costs were in part by higher requirements for maintenance services and individual contractors owing to higher labour and service contract rates reflecting latest local wage levels and currency appreciation; additional requirements for facility improvements and modifications to ensure compliance with minimum security standards, as recommended by the United Nations Department of Safety and Security (UNDSS); and provision for the acquisition of three armoured vehicles, not available through the United Nations fleet. |
| 35. BINUH | 32 329.8 | 31 614.9 | (714.9) | (2.2) | The decrease is attributable to primarily to reduced requirements for civilian personnel costs, resulting from: (a) the proposed net abolishment of 41 posts and positions, comprising the abolishment of mission support staff as UNSOH started providing, on a cost-recovery basis; (b) abolishment of posts dedicated to implementation of police-related BINUH mandate, which has been discontinued pursuant to Security Council resolution 2814 (2026); and (c) the application of higher vacancy rates for Local level staff. The decrease is further attributable to reduced requirements under military and police personnel attributable primarily to the reduction in the deployment of United Nations police officers from 48 to 5 personnel. The decrease in civilian personnel costs was offset in part by a net increase in requirements under operational costs primarily due to the provision of $4.0 million to cover the cost reimbursement to UNSOH or the delivery of the standard range of mission support services to BINUH on a cost-recovery basis. With the reduction of the mission’s footprint and handover of support functions to UNSOH, requirements under official travel, air operations, communication and information technology, ground transportation and medical were reduced. |
| 36. UNAMA | 105 776.1 | 97 167.8 | (8 608.3) | (8.1) | The decrease is attributable primarily to: (a) reduced requirements for civilian personnel costs, owing to the abolishment of 61 posts and positions (, the absence in 2027 of a one-time provision included in the 2026 appropriation for separation costs related to the abolishment of 38 posts in the Kuwait Joint Support Office, and the application of a higher vacancy rate of 13.9 per cent for international staff, compared with a vacancy rate of 10.4 per cent applied in 2026; (b) reduced requirements for fuel for generators reflecting energy-efficiency measures and a reduced mission footprint following the closure and nationalization of field offices approved in 2026; (c) reduced requirements for air operations due to a crease in the flight hours based on historical utilization patterns: (d) removal of the one-time provision for acquisition of vehicle workshop equipment approved in 2026; and lower costs for medical services based on new contractual terms and operating modality. The decrease is offset by additional requirements or mine detection and mine clearing services to strengthen the mine action coordination, including support to the Mine Action Technical Cell in line with para 5(j) of Security Council resolution 2626 (2022). |
| Subtotal, cluster III | 324 549.9 | 325 353.9 | 804.0 | 0.2 |  |
| Subtotal, continuing missions | 412 348.9 | 419 411.9 | 7 063.0 | 1.7 |  |
| B. Discontinuing and discontinued missions |  |  |  |  |  |
| UNTMIS | 86 646.8 | – | (86 646.8) | – | The mission’s mandate is set to expire in October 2026. |
| UNMHA | 23 421.9 | – | (23,421.9) | – | The mission’s mandate expired 31 March 2026 pursuant to Security Council resolution 2813 (2026) |
| UNAMI | 23 207.6 | – | (23 207.6) | – | The Mission’s field-based liquidation is scheduled for completion by 30 September 2026 |
| C. Provision for the share of special political missions for RSCE | 2 323.0 | 3 259.1 | 936.1 | 40.3 | The increase is attributable primarily to an increase of the share of special political missions in the cost of the Centre, from 5.10 per cent in the 2025/26 period to 7.17 cent in the 2026/27 period, reflecting the expanded client base of the Centre, following the integration of former clients from KJSO of which seven are continuing special political missions. |
| Total (A+B+C) | 536 145.0 | 422 671.0 | (113 474.0) | (21.2) |  |

Contribution of extrabudgetary resources to mandate implementation in special political missions

Extrabudgetary resources, in particular voluntary contributions, continue to be used for bolstering backstopping, surge requirements for good offices, crisis situations and other activities related to the mandates of special political missions. Such resources have also been critical for support for inter-mission activities and for visits by desk officers and senior officials to missions.

Voluntary contributions have been important in enabling special political missions to implement targeted projects in pursuit of the implementation of their mandates. In the Great Lakes region, the Office of the Special Envoy of the Secretary-General utilizes extrabudgetary resources to support the implementation of the project for the reduction of small arms circulation in the Great Lakes region. The Office of the Special Adviser to the Secretary-General on the Prevention of Genocide utilizes extrabudgetary resources to support the capacity-building and technical assistance programme and the preparation of the 2026 report of the Secretary-General on the responsibility to protect. The Office of the Special Envoy of the Secretary-General for Yemen continues to utilize extrabudgetary resources to support the Special Envoy’s efforts to reach sustainable and inclusive agreements to end the conflict in country.  The Office of the Personal Envoy of the Secretary-General for the Sudan utilizes extrabudgetary resources to support the provision of critical expertise on security arrangements and ceasefires, as well as support for communication strategies and media engagement for the Personal Envoy. UNSMIL continues to utilize extrabudgetary resources to support activities focused on facilitating an inclusive intra-Libyan political process, an economic track and capacity-building on human rights. UNAMA utilizes extrabudgetary resources to support; climate change, activities in local peace initiatives and political engagement and meetings with regional governments, and the advancement of international engagement on Afghanistan in a more coherent, coordinated, and structured manner in line with the recommendations of the Independent Assessment on Afghanistan (S/2023/856).

In addition, voluntary contributions fund specific mission initiatives. The mission in support of the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction to non-State actors used extrabudgetary resources in 2025 to support the participation of Member States in activities aimed at advancing the implementation of the resolution, including capacity- building and outreach initiatives. Furthermore, the Counter-Terrorism Committee Executive Directorate utilizes extrabudgetary resources to support the implementation of Committee-mandated activities and relevant projects, including the organization of meetings in line with the Committee’s approved programme of work and the promotion of international cooperation in counter-terrorism. This includes targeted capacity-building initiatives, such as projects aimed at strengthening national capabilities to detect and disrupt terrorist activities, including through the use of information and communications technologies, as well as specialized initiatives on forensics and biometrics in Africa.

Voluntary contributions also bolster backstopping capacity at Headquarters, including by funding regular visits to the field, thereby enabling the development of closer collaboration with missions. Such visits have facilitated a better understanding and analysis of the context in which missions are operating and how they can be better supported to implement their mandates.

In addition, cost-recovery revenue in some missions, such as UNAMA, enabled them to provide shared common services to other agencies, funds and programmes in the same location, to benefit from economies of scale. This is in line with the direction of consolidating support services at country level and the requirement for integrated support across the United Nations system for the 2030 Agenda. Cost recovery is governed by rule 105.11 of the Financial Regulations and Rules of the United Nations, in addition to policy guidance issued by the Controller.

Extrabudgetary resources (including both voluntary contributions and cost-recovery revenue) are estimated at $33.0 million for 2027, compared with an estimated $33.3 million in 2026. The projected decrease of $0.3 million for 2027 is attributable to the anticipated conclusion or non-extension of some projects or activities in the Office of the Special Envoy of the Secretary-General on Myanmar, United Nations support for the Cameroon-Nigeria Mixed Commission and UNAMA, offset by increases in contributions in Office of the Special Envoy of the Secretary-General for the Great Lakes Region and Office of the Special Envoy of the Secretary-General for Yemen, based on current projections. Extrabudgetary resources have been important in enabling special political missions to implement targeted projects in pursuit of their mandates. However, while missions continue to engage actively in fundraising activities, it remains a challenge to secure funding or pledges for 2027 sufficiently in advance to enable projections to be made with greater certainty.

  - Human resources

The number of civilian personnel proposed for 2027, including international and national staff, United National Volunteers and general temporary assistance positions, reflects an overall decrease of 89 posts and positions, from 2,393 to 2,304. Details of the human resources requirements by cluster, by mission and by category of personnel are presented in tables 13 to 16.

Backstopping support at Headquarters

Special political missions rely on Headquarters for backstopping support for a wide range of functions. The Department of Political and Peacebuilding Affairs is leading and providing substantive backstopping to 34 of the 36 continuing special political missions by ensuring regular and effective communication between the missions and United Nations entities in New York and regular liaison with Member States through their permanent missions to the United Nations and preparing a wide range of substantive material, including briefing material for the Security Council and regular reports of the Secretary-General, among other functions. Administrative support is being provided by the one-Executive-Office of DOS.

Special political missions also benefit from operational support and advisory services in the areas of human resources and supply chain management provided by DOS; budgetary and financial services, asset and property management policy support and assistance with accountability systems provided by DMSPC; and information technology support delivered by the OICT. Special political missions also rely on support from Headquarters in thematic and operational areas such as constitution-making, electoral assistance, mediation, best practices, military and police planning/force generation, rule of law and security institutions.

As outlined in detail in the report of the Secretary-General on the review of arrangements for funding and backstopping special political missions (A/66/340), which remained pending before the General Assembly, there is no dedicated mechanism to ensure relevant capacities for backstopping special political missions at Headquarters, in contrast to peacekeeping operations, which can draw on the support account for peacekeeping operations.

In 2026, a total of 36 posts (1 D-1, 8 P-5, 18 P-4, 3 P-3, and 6 General Service (Other level)) are being funded from special political missions. In 2027, a total of 30 such posts (1 D-1, 7 P-5, 14 P-4, 2 P-3 and 6 General Service (Other level)) are proposed, reflecting the abolishment of 6 posts in 2026 due to the mandate termination, comprising of 2 posts (1 P-4 and 1 P-3), effective 31 March 2026, funded from UNMHA, and 4 posts (1 P-5, and 3 P-4) funded from UNTMIS.

While the resources included in the budgets of special political missions for backstopping support are fundamental for the Secretariat to provide support to special political missions, the regular budget and extra budgetary resources of the Department of Political and Peacebuilding Affairs are often also required to ensure adequate support. Similarly, the regular budget and extrabudgetary resources of the Office for Disarmament Affairs are used to provide administrative support to the mission in support of the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction.

Table 13

Human resources: summary of changes by cluster

|  | Posts |  |  | United Nations Volunteer positions | General temporary assistance positions | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | International | National | Subtotal |  |  |  |
| A. Continuing missions |  |  |  |  |  |  |
| Cluster I |  |  |  |  |  |  |
| Approved 2026a | 142 | 106 | 248 | – | 5 | 253 |
| Proposed 2027 | 141 | 107 | 248 | – | 5 | 253 |
| Change | (1) | 1 | – | – | – | – |
| Cluster II |  |  |  |  |  |  |
| Approved 2026 | 73 | 25 | 98 | – | 1 | 99 |
| Proposed 2027 | 73 | 25 | 98 | – | 1 | 99 |
| Change | – | – | – | – | – | – |
| Cluster III |  |  |  |  |  |  |
| Approved 2026b | 776 | 1 026 | 1 802 | 223 | 16 | 2 041 |
| Proposed 2027 | 733 | 975 | 1 708 | 225 | 19 | 1 952 |
| Change | (43) | (51) | (94) | 2 | 3 | (89) |
| Total, continuing missions |  |  |  |  |  |  |
| Approved 2026 | 991 | 1 157 | 2 148 | 223 | 22 | 2 393 |
| Proposed 2027 | 947 | 1 107 | 2 054 | 225 | 25 | 2 304 |
| Change | (44) | (450) | (94) | 2 | 3 | (89) |
| B. Discontinuing mission |  |  |  |  |  |  |
| UNTMIS |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | 131 | 110 | 241 | 7 | – | 248 |
| Abolishments in 2026c | (131) | (110) | (241) | (7) | – | (248) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |
| Change | – | – | – | – | – | – |
| UNMHA |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | 48 | 77 | 125 | – | 2 | 127 |
| Abolishments in 2026d | (48) | (77) | (125) | – | (2) | (127) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |
| Change | – | – | – | – | – | – |
| UNAMI |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | 49 | 64 | 113 | – | – | 113 |
| Abolishments in 2026e | (49) | (64) | (113) | – | – | (113) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |
| Change | – | – | – | – | – | – |
| Total, discontinuing missions |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | 228 | 251 | 479 | 7 | 2 | 488 |
| Abolishments in 2026e | (228) | (251) | (479) | (7) | (2) | (488) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |

a	Includes 1 P-4 post established effective 1 April 2026, and 24 posts (1 D-1, 1 P-4, 1 P-3, 6 FS, 1 NPO and 14 LL) established effective 1 July 2026.

b Excludes 42 posts abolished as of 1 July 2026 (1 P-5 post in the United Nations Verification Mission in Colombia; 38 Kuwait Joint Support Office posts (1 P-5, 1 P-4, 2 P-3, 1 P-2, 14 FS and 19 LL) and 1 P-5 non-KJSO post) in UNAMA; and 2 Local level posts in the Kuwait Joint Support Office in BINUH)

c As per phased abolishment of 234 posts (1 USG, 2 ASG, 5 D-1, 17 P-5, 30 P-4, 23 P-3, 46 FS, 73 NPO and 37 LL) and 7 United Nations Volunteer positions (6 international and 1 national) abolished as of 31 October 2026, and 7 posts (1 D-1, 1 P-5, 3 P-4 and 2 FS) abolished as at 31 December 2026.

d As per phased abolishment of 125 posts comprising: (i) as at 31 March 2026 of 70 posts: 1 D-2, 3 P-5,8 P-4, 7 P-3, 8 FS, 10 NPO and 33 LL; (ii) as at 30 April 2026 of 6 posts: 2 FS and 4 LL; (iii)  as at 31 May 2026 of 1 post (FS); (iv) as at 30 June 2026 of 48 posts (1 D-1, 1 P-5, 1 P-4, 3 P-3, 12 FS, 1 NPO and 29 LL); and 2 general temporary positions (1 P-4 and 1 P-3) abolished as of 31 March 2026

e As per phased abolishment, comprising: (i) as at 31 March 2026 of 9 posts: 1 ASG, 1 P-4, 3 FS, 1 NPO and 3 LL; (ii) as at 30 June 2026 of 37 posts: 3 P-4, 1 P-3, 6 FS, 5 NPO and 22 LL; and as at 30 September 2026 of 67 posts (1 D-1, 2 P-5, 10 P-4, 3 P-3, 18 FS, 8 NPO and 25 LL).

Table 14

Human resources: international and national posts and United Nations Volunteer positions

|  | International staff posts |  |  |  |  |  |  |  |  |  |  |  | National staff posts |  |  |  |  |  | United Nations Volunteer positions |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG | ASG | D-2 | D-1 | P-5 | P-4 | P-3 | P-2 | Subtotal | FS | Subtotal | NPO |  | PL | OL | LL | Subtotal | International |  | National | Subtotal | Total |
| Cluster I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 Mission of the Secretary-General’s Good Offices in Cyprus |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | 1 | 2 | 1 | 2 | – | 6 | 3 | 9 | – |  | – | 1 | 3 | 4 | – |  | – | – | 13 |
| Proposed 2027 | – | – | – | 1 | 2 | 1 | 2 | – | 6 | 3 | 9 | – |  | – | 1 | 3 | 4 | – |  | – | – | 13 |
| 2 Office of the Special Adviser to the Secretary-General on the Prevention of Genocide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 1b | – | – | 2 | 3 | 2 | 1 | 10 | – | 10 | – |  | – | 2 | – | 2 | – |  | – |  | 12 |
| Proposed 2027 | 1 | 1b | – | – | 2 | 3 | 3 | 2 | 12 | – | 12 | – |  | – | 2 | – | 2 | – |  |  |  | 12 |
| 3 Personal Envoy of the Secretary-General for Western Sahara |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1a | – | – | – | – | – | 1 | – | 2 | – | 2 | – |  | – | – | – | – | – |  | – | – | 2 |
| Proposed 2027 | 1a | – | – | – | – | – | 1 | – | 2 | – | 2 | – |  | – | – | – | – | – |  | – | – | 2 |
| 4 Support to the implementation of Security Council resolution 1559 (2004) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1c | – | – | – | – | 1 | – | – | 2 | – | 2 | – |  | – | 1 | – | 1 | – |  | – | – | 3 |
| Abolishment | (1) | – | – | – | – | – | – | – | (1) | – | (1) | – |  | – | – | – | – | – |  | – | – | (1) |
| Proposed 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| 5 Office of the United Nations Representative to the Geneva International Discussions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | 2 | 1 | – | 3 | – | 3 | – |  | – | – | – | – | – |  | – | – | 3 |
| Establishment | – | – | – | – | – | – | – | – | – | – | – | – |  | – | 1 | – | 1 | – |  | – | – | 1 |
| Proposed 2027 | – | – | – | – | – | 2 | 1 | – | 3 | – | 3 | – |  | – | 1 | – | 1 | – |  | – | – | 4 |
| 6 Office of the Special Envoy of the Secretary-General for Syria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 1 | 1 | 3 | 5 | 10 | 4 | – | 25 | 5 | 30 | 1 |  | – | 5 | 29 | 35 | – |  | – | – | 65 |
| Reclassification | – | – | – | (1) | 1 | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Proposed 2027 | 1 | 1 | 1 | 2 | 6 | 10 | 4 | – | 25 | 5 | 30 | 1 |  | – | 5 | 29 | 35 | – |  | – | – | 65 |
| 7 Office of the Special Envoy of the Secretary-General for the Horn of Africa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | – | – | 1 | – | 2 | 1 | – | 5 | – | 5 | 2 |  | – | – | 2 | 4 | – |  | – | – | 9 |
| Proposed 2027 | 1 | – | – | 1 | – | 2 | 1 | – | 5 | – | 5 | 2 |  | – | – | 2 | 4 | – |  | – | – | 9 |
| 8 Office of the Special Envoy of the Secretary-General for the Great Lakes Region |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | – | – | 2 | 4 | 5 | 5 | – | 17 | 1 | 18 | - |  | – | - | 5 | 5 | – |  | – | – | 23 |
| Proposed 2027 | 1 | – | – | 2 | 4 | 5 | 5 | – | 17 | 1 | 18 | - |  | – | - | 5 | 5 | – |  | – | – | 23 |
| 9 Office of the Special Envoy of the Secretary-General for Yemen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026d | 1 | – | – | 3 | 3 | 15 | 8 | 1 | 31 | 20 | 51 | 11 |  | – | – | 43 | 54 | – |  | – | – | 105 |
| Proposed 2027 | 1 | – | – | 3 | 3 | 15 | 8 | 1 | 31 | 20 | 51 | 11 |  | – | – | 43 | 54 | – |  | – | – | 105 |
| 10 Office of the Special Envoy of the Secretary-General on Myanmar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1a | – | – | 1 | 1 | 1 | – | – | 4 | – | 4 | – |  | – | – | – | – | – |  | – | – | 4 |
| Proposed 2027 | 1a | – | – | 1 | 1 | 1 | – | – | 4 | – | 4 | – |  | – | – | – | – | – |  | – | – | 4 |
| 11 Office of the Personal Envoy of the Secretary-General for the Sudan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | – | – | – | 2 | 3 | – | – | 6 | – | 6 | – |  | – | – | 1 | 1 | – |  | – | – | 7 |
| Proposed 2027 | 1 | – | – | – | 2 | 3 | – | – | 6 | – | 6 | – |  | – | – | 1 | 1 | – |  | – | – | 7 |
| 12 Senior Representative for the Implementation of Security Council resolution 2792 (2025) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | 1a | – | – | – | 1 | – | – | 2 | – | 2 | – |  | – | – | – | – | – |  | – | – | 2 |
| Proposed 2027 | – | 1a | – | – | – | 1 | – | – | 2 | – | 2 | – |  | – | – | – | – | – |  | – | – | 2 |
| Cluster II |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 Group of Experts on the Democratic Republic of the Congo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | – | – | – | – |  | – | – | 1 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | – | – | – | – |  | – | – | 1 |
| 14 Panel of Experts on the Sudan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | – | – | – | – |  | – | – | 1 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | – | – | – | – |  | – | – | 1 |
| 15 Support to the Security Council Committee established pursuant to resolution 1718 (2006) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | 1 | – | – | 1 | – |  | – | – | 2 |
| Proposed 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | 1 | – | – | 1 | – |  | – | – | 2 |
| 16 Panel of Experts on Libya |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| 17 Panel of Experts pursuant to resolution 2745 (2024) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| 18 Panel of Experts on Yemen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | 3 | 4 | – |  | – | – | – | – | – |  | – | – | 4 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | 3 | 4 | – |  | – | – | – | – | – |  | – | – | 4 |
| 19 Panel of Experts on South Sudan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 2 | – | 2 | – |  | – | – | 3 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 2 | – | 2 | – |  | – | – | 3 |
| 20 Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | 1 | 4 | 6 | – | 11 | – | 11 | – |  | – | 5 | – | 5 | – |  | – | – | 16 |
| Proposed 2027 | – | – | – | – | 1 | 4 | 6 | – | 11 | – | 11 | – |  | – | 5 | – | 5 | – |  | – | – | 16 |
| 21 Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| Proposed 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| 22 Panel of Experts pursuant to resolution 2713 (2023) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | 2 | 3 | – |  | – | – | 4 |
| Proposed 2027 | – | – | – | – | – | – | 1 | – | 1 | – | 1 | – |  | – | 1 | 2 | 3 | – |  | – | – | 4 |
| 23 Panel of Experts on Haiti |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | 1 | – | 1 | – | 2 | – | 2 | – |  | – | 1 | – | 1 | – |  | – | – | 3 |
| Proposed 2027 | – | – | – | – | 1 | – | 1 | – | 2 | – | 2 | – |  | – | 1 | – | 1 | – |  | – | – | 3 |
| 24 Office of the Focal Point for Delisting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | 1 | 1 | – | 2 | – | 2 | – |  | – | 1 | – | 1 | – |  | – | – | 3 |
| Proposed 2027 | – | – | – | – | – | 1 | 1 | – | 2 | – | 2 | – |  | – | 1 | – | 1 | – |  | – | – | 3 |
| 25 Panel of Experts on the Islamic Republic of Iran |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | 1 | – | – | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| Proposed 2027 | – | – | – | – | 1 | – | – | – | 1 | – | 1 | – |  | – | 1 | – | 1 | – |  | – | – | 2 |
| 26 Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | 1 | – | 2 | – | 3 | – | 3 | – |  | – | 2 | – | 2 | – |  | – | – | 5 |
| Proposed 2027 | – | – | – | – | 1 | – | 2 | – | 3 | – | 3 | – |  | – | 2 | – | 2 | – |  | – | – | 5 |
| 27 Counter-Terrorism Committee Executive Directorate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | 1 | 1 | 2 | 8 | 18 | 9 | 3 | 42 | – | 42 | – |  | – | 6 | – | 6 | – |  | – | – | 48 |
| Proposed 2027 | – | 1 | 1 | 2 | 8 | 18 | 9 | 3 | 42 | – | 42 | – |  | – | 6 | – | 6 | – |  | – | – | 48 |
| Cluster III |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 UNOWAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 1 | – | 1 | 6 | 13 | 10 | 1 | 33 | 5 | 38 | 9 |  | – | – | 18 | 27 | – |  | – | – | 65 |
| Proposed 2027 | 1 | 1 | – | 1 | 6 | 13 | 10 | 1 | 33 | 5 | 38 | 9 |  | – | – | 18 | 27 | – |  | – | – | 65 |
| 29 United Nations Regional Centre for Preventive Diplomacy for Central Asia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | 1 | – | – | 1 | 2 | 1 | – | 5 | 1 | 6 | 4 |  | – | – | 14 | 18 | – |  | – | – | 24 |
| Proposed 2027 | – | 1 | – | – | 1 | 2 | 2 | – | 5 | 1 | 6 | 4 |  | – | – | 14 | 18 | – |  | – | – | 24 |
| 30 United Nations support for the Cameroon-Nigeria Mixed Commission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | 1 | 5 | – | – | 6 | 1 | 7 | – |  | – | – | 2 | 2 | – |  | – | – | 9 |
| Proposed 2027 | – | – | – | – | 1 | 5 | – | – | 6 | 1 | 7 | – |  | – | – | 2 | 2 | – |  | – | – | 9 |
| 31 Office of the United Nations Special Coordinator for Lebanon |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 1 | – | 1 | 2 | 5 | 1 | – | 11 | 3 | 14 | 5 |  | – | – | 52 | 57 | – |  | – | – | 71 |
| Proposed 2027 | 1 | 1 | – | 1 | 2 | 5 | 1 | – | 11 | 3 | 14 | 5 |  | – | – | 52 | 57 | – |  | – | – | 71 |
| 32 UNOCA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | – | – | 2 | 2 | 10 | 4 | – | 19 | 7 | 26 | 3 |  | – | – | 10 | 13 | – |  | 1 | 1 | 40 |
| Proposed 2027 | 1 | – | – | 2 | 2 | 10 | 4 | – | 19 | 7 | 26 | 3 |  | – | – | 10 | 13 | – |  | 1 | 1 | 40 |
| 32 UNSMIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 2 | – | 7 | 10 | 40 | 29 | 2 | 91 | 124 | 215 | 17 |  | – | 1 | 91 | 109 | 5 |  | – | 5 | 329 |
| Establishment | – | – | – | – | 1 | – | – | – | 1 | 1 | 2 | 6 |  | – | – | 2 | 8 | – |  | – | – | 10 |
| Conversion | – | – | – | – | – | – | (1) | – | (1) | – | (1) | 1 |  | – | – | – | 1 | – |  | – | – | – |
| Proposed 2027 | 1 | 2 | – | 7 | 11 | 40 | 28 | 2 | 91 | 125 | 216 | 24 |  | – | 1 | 93 | 118 | 5 |  | – | 5 | 339 |
| 33 United Nations Verification Mission in Colombia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026e | 1 | 1 | – | 5 | 23 | 36 | 53 | 1 | 120 | 45 | 165 | 93 |  | – | 1 | 80 | 174 | 100 |  | 20 | 120 | 459 |
| Abolishment | – | – | – | (1) | – | – | – | – | (1) | – | (1) | – |  | – | – | – | – | – |  | – | – | (1) |
| Establishment | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | 1 | 1 |  |  |  | - | 1 |
| Conversion | – | – | – | – | – |  | (1) | (1) | (2) | – | (2) | 2 |  | – | – | – | 2 | – |  | – | – | – |
| Proposed 2027 | 1 | 1 | – | 4 | 23 | 35 | 53 | – | 117 | 45 | 162 | 95 |  | – | 1 | 81 | 177 | 100 |  | 20 | 120 | 459 |
| 35 BINUH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026f | 1 | – | 1 | 4 | 9 | 16 | 8 | 2 | 41 | 42 | 83 | 19 |  | – | – | 35 | 54 | 1 |  | – | 1 | 138 |
| Abolishment | – | – | – | (1) | (1) | (1) | (6) | (2) | (11) | (8) | (19) | (1) |  | – | – | (24) | (25) | (1) |  | – | (1) | (45) |
| Proposed 2027 | 1 | – | 1 | 3 | 8 | 15 | 2 | – | 30 | 34 | 64 | 18 |  | – | – | 11 | 29 | – |  | – | – | 93 |
| 36 UNAMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 2 | 1 | 5 | 21 | 48 | 44 | 5 | 127 | 95 | 222 | 103 |  | - | 1 | 468 | 572 | 60 |  | 36 | 96 | 890 |
| Abolishment | – | – | – | – | – | (5) | (2) |  | (7) | (15) | (22) | (10) |  |  |  | (28) | (38) |  |  |  | - | (60) |
| Establishment | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | 3 |  | – | 3 | 3 |
| Reclassification | – | – | – | – | (1) | – | 1 | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Proposed 2027 | 1 | 2 | 1 | 5 | 20 | 43 | 43 | 5 | 120 | 80 | 200 | 200 |  | – | 1 | 440 | 534 | 63 |  | 36 | 99 | 833 |
| Total, continuing missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 16 | 12 | 4 | 38 | 105 | 245 | 200 | 16 | 636 | 355 | 991 | 267 |  | 1 | 34 | 855 | 1 157 | 166 |  | 57 | 223 | 2 371 |
| Abolishment | (1) | – | – | (2) | (1) | (6) | (8) | (2) | (20) | (23) | (43) | (11) |  | – | – | (52) | (63) | (1) |  | – | (1) | (107) |
| Establishment | – | – | – | – | 1 | – | – | – | 1 | 1 | 2 | 6 |  | – | 1 | 3 | 10 | 3 |  | – | 3 | 15 |
| Reclassification | – | – | – | (1) | – | – | 1 | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Conversion | – | – | – | – | – | – | (2) | (1) | (3) | – | (3) | 3 |  | – | – | – | 3 | – |  | – | – | – |
| Proposed 2027 | 15 | 12 | 4 | 35 | 105 | 239 | 191 | 13 | 614 | 333 | 947 | 265 |  | 1 | 35 | 806 | 1 107 | 168 |  | 57 | 225 | 2 279 |
| Discontinuing missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UNTMIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | 1 | 2 | – | 6 | 18 | 33 | 23 | – | 83 | 48 | 131 | 73 |  | – | – | 37 | 110 | 6 |  | 1 | 7 | 248 |
| Abolishment in 2026h | (1) | (2) | – | (6) | (18) | (33) | (23) | – | (83) | (48) | (131) | (73) |  | – | – | (37) | (110) | (6) |  | (1) | (7) | (248) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Proposed 2027 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| UNMHA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | – | – | 1 | 1 | 4 | 9 | 10 | – | 25 | 23 | 48 | 11 |  | – | – | 66 | 77 | – |  | – | – | 125 |
| Abolishment in 2026i | – | – | (1) | (1) | (4) | (9) | – | (1) | (25) | (23) | (48) | (11) |  | – | – | (66) | (77) | – |  | – | – | (125) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Proposed 2027 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| UNAMI |  |  |  | – |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | – | 1 | – | 1 | 2 | 14 | 4 | – | 22 | 27 | 49 | 14 |  | – | – | 50 | 64 | – |  | – | – | 113 |
| Abolishment in 2026j | – | (1) | – | (1) | (2) | (14) | (4) | – | (22) | (27) | (49) | (14) |  | – | – | (50) | (64) | – |  | – | – | (113) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |
| Proposed 2027 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – | – |  | – | – | – |

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; LL, Local level; NPO, National Professional Officer; OL, Other level; PL, Principal level; USG, Under-Secretary-General.

a	The Under-Secretary-General is on a when-actually-employed contract.

b	The Assistant Secretary-General is on a $1-a-year contract.

c	The Under-Secretary-General is on a $1-a-year contract.

d	Includes 1 P-4 post established effective 1 April 2026, and 24 posts (1 D-1, 1 P-4, 1 P-3, 6 FS, 1 NPO and 14 LL) established effective 1 July 2026.

e Excludes 1 P-5 post abolished as of 1 July 2026.

f Excludes 2 Local level posts in the Kuwait Joint Support Office abolished as of 1 July 2026.

g Excludes 39 posts abolished effective 1 July 2026: (38 Kuwait Joint Support Office posts (1 P-5, 1 P-4, 2 P-3, 1 P-2, 14 FS and 19 LL) and 1 P-5 non-KJSO post).

h As per phased abolishment of 234 posts (1 USG, 2 ASG, 5 D-1, 17 P-5, 30 P-4, 23 P-3, 46 FS, 73 NPO and 37 LL) and 7 United Nations Volunteer positions (6 international and 1 national) abolished as of 31 October 2026, and 7 posts (1 D-1, 1 P-5, 3 P-4 and 2 FS) abolished as at 31 December 2026.

i As per phased abolishment comprising: (i) as at 31 March 2026 of 70 posts: 1 D-2, 3 P-5,8 P-4, 7 P-3, 8 FS, 10 NPO and 33 LL; (ii) as at 30 April 2026 of 6 posts: 2 FS and 4 LL; (iii)  as at 31 May 2026 of 1 post (FS); and (iv) as at 30 June 2026 of 48 posts (1 D-1, 1 P-5, 1 P-4, 3 P-3, 12 FS, 1 NPO and 29 LL)

jAs per phased abolishment, comprising: (i) as at 31 March 2026 of 9 posts: 1 ASG, 1 P-4, 3 FS, 1 NPO and 3 LL; (ii) as at 30 June 2026 of 37 posts: 3 P-4, 1 P-3, 6 FS, 5 NPO and 22 LL; and as at 30 September 2026 of 67 posts (1 D-1, 2 P-5, 10 P-4, 3 P-3, 18 FS, 8 NPO and 25 LL).

Table 15

Human resources: general temporary assistance positions and other personnel

|  | General temporary assistance positions |  |  |  |  |  |  |  |  |  | Other personnel |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | International staff |  |  |  |  |  | National staff |  |  | Military advisers/ observers |  | United Nations Guard Unit personnel | United Nations police | Government- provided personnel |  |
|  | D-1 | P-5 | P-4 | P-3 | P-2 | NPO |  | GS | LL |  |  |  |  |  |  |
| Office of the Special Adviser to the Secretary-General on the Prevention of Genocide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026a | – | – | 1 | – | 1 | – |  | – | – | – |  | – | – | – | 2 |
| Proposed 2027 | – | – | 1 | – | 1 | – |  | – | – | – |  | – | – | – | 2 |
| Office of the Special Envoy of the Secretary-General for Yemen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026b | – | – | – | 1 | 1 | – |  | – | – | – |  | – | – | – | 2 |
| Proposed 2027 | – | – | – | 1 | 1 | – |  | – | – | – |  | – | – | – | 2 |
| Office of the Special Envoy of the Secretary-General on Myanmar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – |  | – | 1 | – |  | – | – | – | 1 |
| Proposed 2027 | – | – | – | – | – | – |  | – | 1 | – |  | – | – | – | 1 |
| Panel of Experts on the Islamic Republic of Iran |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026c | – | – | – | 1 | – | – |  | – | – | – |  | – | – | – | 1 |
| Proposed 2027 | – | – | – | 1 | – | – |  | – | – | – |  | – | – | – | 1 |
| UNOWAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026d | – | – | – | – | – | – |  | – | 1 | 1 |  | – | 1 | – | 3 |
| Proposed 2027 | – | – | – | – | – | – |  | – | 1 | 1 |  | – | 1 | – | 3 |
| United Nations support for the Cameroon-Nigeria Mixed Commission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – |  | – | – | 1 |  | – | – | – | 1 |
| Proposed 2027 | – | – | – | – | – | – |  | – | – | 1 |  | – | – | – | 1 |
| UNSMIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026e | – | 1 | 2 | 1 | – | 3 |  | – | – | – |  | 234 | – | 7 | 248 |
| Proposed 2027 | – | 1 | 2 | 1 | – | 3 |  | – | – | – |  | 234 | – | 7 | 248 |
| United Nations Verification Mission in Colombia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | – | – | – | – | – | – |  | – | – | 120 |  | – | – | – | 120 |
| Proposed 2027 | – | – | – | – | – | – |  | – | – | 120 |  | – | – | – | 120 |
| BINUH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026f | 1 | 1 | 1 | – | – | – |  | 1 | – | – |  | – | 48 | 3 | 55 |
| Proposed 2027 | 1 | 1 | 1 | 2 | – | 1 |  | 1 | 1 | – |  | – | 5 | 10 | 23 |
| UNAMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026g | – | – | 2 | – | – | 1 |  | – | 1 | 1 |  | – | – | – | 5 |
| Proposed 2027 | – | – | 1 | – | – | 1 |  | – | 1 | 1 |  | – | – | – | 4 |
| Subtotal, continuing missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026 | 1 | 2 | 7 | 3 | 1 | 4 |  | 1 | 3 | 123 |  | 234 | 49 | 10 | 438 |
| Abolishment | – | – | (1) | – | – | – |  | – | – | – |  | – | (43) | – | (44) |
| Establishment | – | – | – | 2 | – | 1 |  | – | 1 | – |  | – | – | 7 | 11 |
| Proposed 2027 | 1 | 2 | 6 | 5 | 1 | 5 |  | 1 | 4 | 123 |  | 234 | 6 | 17 | 405 |
| Discontinuing missions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UNTMIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | – | – | – | – | – | – |  | – | – | – |  | 625 | 12 | 20 | 657 |
| Abolishments in 2026h | – | – | – | – | – | – |  | – | – | – |  | (625) | (12) | (20) | (657) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |  | – | – | – |  | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |  | – | – | – |  | – | – | – | – |
| UNMHA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2026: as at 1 January 2026 | – | – | 1 | 1 | – | – |  | – | – | – |  | 9 | – | – | 11 |
| Abolishments in 2026i | – | – | (1) | (1) | – | – |  | – | – | – |  | (9) | – | – | (11) |
| Approved 2026: as at 31 December 2026 | – | – | – | – | – | – |  | – | – | – |  | – | – | – | – |
| Proposed 2027 | – | – | – | – | – | – |  | – | – | – |  | – | – | – | – |

Abbreviations: NPO, National Professional Officer; GS, General Service; LL, Local level.

a	The P-4 and P-2 positions were approved as general temporary assistance by the General Assembly in resolution 77/263 A, section V, on the recommendations of the Advisory Committee on Administrative and Budgetary Questions (A/77/7/Add.2, paras. 10 and 11).

b	The P-2 position was approved (effective 1 April 2026) as general temporary assistance by the Assembly in resolution 80/254, and the P-3 position was approved (effective 1 April 2026) as general temporary assistance by the Assembly in resolution 80/254, on the recommendations of the Advisory Committee on Administrative and Budgetary Questions (A/80/7/Add.30, para. 41)

c	The P-3 position was approved as general temporary assistance by the Assembly in resolution 80/254, on the recommendations of the Advisory Committee on Administrative and Budgetary Questions (A/80/7/Add.30, para. 26 (b)).

d	The Local level position was approved as general temporary assistance by the Assembly in resolution 73/279 A, section XIV, para. 28.

e	The P-5 position was approved as general temporary assistance by the Assembly in resolution 76/246 A, section X, on the recommendation of the Advisory Committee (A/76/7/Add.1, para. 29).

f	The D-1 position was approved as general temporary assistance by the Assembly in resolution 74/263, section XVIII, para. 28. The P-5, P-4 and General Service (Other level) positions were approved as general temporary assistance by the Assembly in resolution 74/263, section XVIII, on the recommendation of the Advisory Committee (A/74/7/Add.24, para. 30).

g	The P-5 position was approved as general temporary assistance by the Assembly in resolution 77/4, on the recommendation of the Advisory Committee (A/76/7/Add.41, para. 21). The P-4 position was approved as general temporary assistance by the Assembly in resolution 77/263 A, section V, on the recommendation of the Advisory Committee (A/77/7/Add.5, para. 18).

h  		Reflects the repatriation of 625 UN guard unit personnel, 12 United Nations police personnel and 20 government-provided personnel by 31 October 2026.

I  Reflects the abolishment of 1 P-4 and 1 P-3 general temporary positions as of 31 March 2026, and 9 United Nations monitors repatriated by 28 February 2026.

Table 16

Human resources: posts funded from extrabudgetary resources

|  | International staff posts |  |  |  |  |  |  |  |  |  |  |  | National staff posts |  |  |  |  | United Nations Volunteer positions |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG | ASG | D-2 | D-1 | P-5 | P-4 | P-3 | P-2 | Subtotal | FS | Subtotal | NPO |  | GS | LL | Subtotal | International |  | National | Subtotal | Total |
| Office of the Special Adviser to the Secretary-General on the Prevention of Genocide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| Projected 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| Office of the Special Envoy of the Secretary-General for the Horn of Africa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | 1 | – | – | 1 | 2 | – | 2 | – |  | – | 1 | 1 |  |  | 1 | 1 | 4 |
| Projected 2027 | – | – | – | – | 1 | – | – | 1 | 2 | – | 2 | – |  | – | 1 | 1 |  |  | 1 | 1 | 4 |
| Office of the Special Envoy of the Secretary-General for the Great Lakes Region |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| Projected 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | 1 |  | – | 1 | 2 | – |  | – | – | 3 |
| Office of the Special Envoy of the Secretary-General for Yemen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | 1 | 1 | 3 | 2 | – | 7 | – | 7 | 4 |  | – | 1 | 5 | – |  | – | – | 12 |
| Projected 2027 | – | – | – | 1 | 1 | 3 | 2 | – | 6 | – | 6 | 4 |  | – | 1 | 5 | – |  | – | – | 11 |
| Office of the Special Envoy of the Secretary-General on Myanmar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | – | 1 | 1 | 2 | – | 3 | – |  | – | – | – | – |  | – | – | 2 |
| Projected 2027 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | – | – | – |  | – | – | – |
| Office of the Personal Envoy of the Secretary-General for the Sudan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | 1 | – | – | 1 | – | 2 | 1 | 3 | – |  | – | – | – | – |  | – | – | 3 |
| Projected 2027 | – | – | – | 1 | – | – | 1 | – | 2 | 1 | 3 | – |  | – | – | – | – |  | – | – | 3 |
| Cluster II |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non‑proliferation of all weapons of mass destruction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | 2 | 1 | – | 3 | – | 3 | – |  | – | – | – | – |  | – | – | 3 |
| Projected 2027 | – | – | – | – | – | 2 | 1 | – | 3 | – | 3 | – |  | – | – | – | – |  | – | – | 3 |
| Cluster III |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UNOWAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| Projected 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| UNOCA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| Projected 2027 | – | – | – | – | – | 1 | – | – | 1 | – | 1 | – |  | – | – | – | – |  | – | – | 1 |
| UNSMIL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | 3 | 3 | – |  | – | – | 3 |
| Projected 2027 | – | – | – | – | – | – | – | – | – | – | – | – |  | – | 3 | 3 | – |  | – | – | 3 |
| UNAMA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | – | 1 | 2 | 7 | – | 10 | 5 | 15 | – |  | – | – | – | – |  | – | – | 15 |
| Projected 2027 | – | – | – | – | – | 1 | 5 | – | 6 | 4 | 10 | – |  | – | – | – | – |  | – | – | 10 |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Projected 2026 | – | – | – | 2 | 3 | 11 | 11 | 2 | 29 | 6 | 35 | 4 |  | – | 5 | 9 | 1 |  | – | 1 | 45 |
| Projected 2027 | – | – | – | 1 | 2 | 10 | 8 | 1 | 22 | 5 | 27 | 5 |  | – | 6 | 11 | 1 |  | – | 1 | 39 |

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; GS, General Service; LL, Local level; NPO, National Professional Officer; USG, Under-Secretary-General.

Note: Posts indicated in table 16 are those funded or projected to be funded from extrabudgetary resources in the current and forthcoming year, based on the latest information available and projections made at the time of reporting. In keeping with established practice, the table does not include extrabudgetary general temporary assistance positions, positions that are billed to a third party or project posts that are not expected to be funded continuously for more than one year.

  - Financial performance of special political missions for 2025

The General Assembly approved an overall appropriation for 2025 of $693.0 million for the special political missions (resolutions 79/258 A and 79/258 B). The expenditure for 2025 amounted to $632.4 million, resulting in an overall unencumbered balance of $60.6 million, or 8.7 per cent. The overall implementation rate of 91.3 remains consistent with the previous year (92 per cent in 2024) owing to continued spending restrictions imposed due to the liquidity constraints and the efforts to curtail expenditure across special political missions. An analysis of the main factors affecting budget performance is provided in table 17. Performance reporting has been enhanced through the inclusion of information for field-based missions in the financial performance report on the programme budget for 2025 (A/81/89), in line with the recommendation of the Advisory Committee on Administrative and Budgetary Questions (see A/79/7/Add.1, para. 10). Further details are also included in the supplementary information under each thematic cluster.

Table 17

Main factors affecting budget performance in 2025

| Group of expenditure | Main factors for variance |
| --- | --- |
| Military and police personnel (under-expenditure of $2.4 million) | The variance was attributable primarily to: (a) lower-than-planned deployment of United Nations police officers in BINUH; (b) lower costs for rations due to the use of existing stock reserve and lower-than-estimated costs for contingent-owned equipment self-sustainment due to the non-deployment of the minor engineering category in UNTMIS; (c) lower-than-estimated costs for the rotation of military contingent personnel in UNAMI; and (d) lower-than-estimated requirements for claims for death and disability compensation. The under-expenditure was offset in part by additional expenditure for military observers in the United Nations Verification Mission in Colombia attributable to an increase in mission subsistence allowance rates. |
| Civilian personnel (over-expenditure of $20.7million) | The variance was attributable primarily to the higher-than-budgeted staff costs upon separation from services in UNAMI for which only a partial provision was approved in the 2025 budget; (b) unbudgeted separation of staff costs as part of the two early separation programmes launched and approved in the Secretariat in 2025; (c) an increase in the contribution costs towards Health Plan subsidy costs for national staff; and (d) updated salary scales for national staff. The over-expenditure was offset in part by broadly higher-than-budgeted average vacancy rates as a result of hiring restrictions. |
| Operational costs (under-expenditure of $78.9 million) | The variance reflects the austerity measures implemented to contain expenditures as well as lower-than-budgeted consumption in certain areas, attributable primarily to: (a) lower requirements for facilities and infrastructure in UNTMIS, UNSMIL, UNAMA, the United Nations Verification Mission in Colombia, UNMHA and the Office of Special Envoy of the Secretary-General for Yemen; (b) reduced requirements for air operations in UNAMA, UNTMIS, the United Nations Verification Mission in Colombia, UNOWAS and UNSMIL, and; (c) reduced requirements for communications and information technology owing to lower costs for communication carrier and network services, curtailed maintenance and support services, renewal only of essential licenses and software, and the suspension of public information and publication services for outreach; (d) postponed acquisition of equipment, supplies and spare parts with the related reduction in freight costs; (e) cancellation of planned official travel; (f) suspension of planned workshops and retreats; and (g) reduced requirements for experts due to vacancies in some panels of experts and mechanisms supporting sanctions. |

Table 18 provides an analysis of the overall financial performance for special political missions for the period from 2023 to 2025.

Table 18

Synopsis of financial performance for special political missions, 2023–2025

(Thousands of United States dollars)

| Category | 2023 | 2024 | 2025 |
| --- | --- | --- | --- |
| Appropriation | 768 335.0 | 742 016.9 | 693 041.2 |
| Expenditure | 750 575.9 | 682 454.9 | 632 404.9 |
| Unencumbered balance | 17 759.1 | 59 562.0 | 60 635.3 |
| Unencumbered balance as a percentage of appropriation | 2.3 | 8.0 | 8.7 |
| Unliquidated obligations | 45 438.2 | 23 422.5 | 29 258.9 |
| Unliquidated obligations as a percentage of appropriation | 5.9 | 3.2 | 4.2 |
| Cancelled prior-period obligations | 10 292.3 | 11 224.1 | 3 607.0 |

Cancelled prior-period commitments in 2025 amounting to $3.6 million in special political missions were due primarily to: (a) the cancellation of the construction of a perimeter wall in Al Khawka due to uncertainty of funding in future periods to complete the project in UNMHA; (b) lower-than-estimated actual costs for the Mission’s cost-shared portion of rental space at the Benghazi hub in UNSMIL; (c) the cancellation of commitments for the construction of overhead protection and medical supplies due to inability of the vendors to deliver in UNTMIS; and (e) reduced commitments for ground transportation owing to the security situation in Haiti which led to lower-than-estimated actual costs for the maintenance of vehicles and non-requirement for custom and freight costs for vehicles that were acquired but had to be transshipped to UNLB; (f) the lower actual travel costs, compared with the amounts initially obligated for Military observers in the United Nations Verification Mission in Colombia owing to changes in travel duration; and lower‑than‑estimated costs for termination indemnity, repatriation grant, commutation of annual leave and other entitlements that were due to staff upon their separation of service from UNITAD which closed in September 2024.

Unliquidated commitments, which remained open at the end of 2025 in special political missions, amounts to $29.3 million or 4.2 per cent of the appropriation. Of the $29.3 million, $19 million or 65.9 per cent relates to a fund commitment raised in UNAMI for separation costs and salaries obligations which were due to staff upon their separation of service in 2025.  Other commitments relates to liabilities for standard troop reimbursements and contingent-owned equipment: major equipment raised in UNTMIS, UNSMIL and UNAMI, accruals for recreational leave allowance in UNTMIS and the United Nations Verification Mission in Colombia due to late submission of expense reports, accruals for contractual services rendered in UNTMIS, UNSMIL and the United Nations Verification Mission in Colombia, which were pending submission of invoices at year end, as well as for open purchase orders which were pending delivery of goods or receipt of invoices at year end, mainly in UNAMA.

Annex I

Definitions

A.	Terminology related to proposed changes in human resources

1.	The following terms have been applied with respect to proposed changes in human resources:

•	Post establishment: a new post is proposed to be established when additional resources are necessary and when it is not possible to redeploy resources from other offices or otherwise accommodate specific activities from within existing resources.

•	Post reassignment: an approved post that was intended to cover a certain function is proposed to implement other priority mandated activities unrelated to the original function. While a post reassignment may involve a change of location or office, it does not change the category or level of the post.

•	Post redeployment: an approved post is proposed to be redeployed to cover comparable or related functions in another office.

•	Post reclassification: an approved post is proposed to be reclassified (upgraded or downgraded) when the duties and responsibilities of the post have changed substantially.

•	Post abolishment: an approved post is proposed to be abolished if it is no longer needed to implement the activities for which it was approved or to implement other priority mandated activities within the mission.

•	Post conversion: three possible options for post conversion are as follows:

–	Conversion of general temporary assistance positions to posts: approved positions financed under general temporary assistance are proposed for conversion to posts if the functions being performed are of a continuing nature.

–	Conversion of international staff posts to national staff posts: approved international staff posts are proposed for conversion to national staff posts.

–	Conversion of the approved source of funding: positions funded under extrabudgetary resources are proposed for conversion to be funded under the regular budget. Other attributes of the positions would remain unchanged.

B.	Terminology related to variance analysis

2.	The contributing factors for the resource variance according to specific standard options encompass the following categories listed below:

•	New and expanded mandates: variances caused by changes in the scale or scope of the mandate.

•	Technical adjustments: variances caused by adjustments due to increased provisions for posts approved for the preceding budget proposals with a 50 per cent vacancy rate that are subject to the proposed vacancy rate for continuing posts in the current proposed budget period. Other adjustments of a technical nature include changes in salary rates, vacancy rates, contractual rates or other changes in cost parameters as a result of United Nations regulations, rules and policies.

•	Other changes: variances caused by resource changes that do not fall under the above factors.

Annex II

Summary of follow-up action taken to implement decisions and requests made by the General Assembly, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly

A.	General Assembly

| Brief description of the recommendation or request | Action taken to implement the recommendation or request |
| --- | --- |
| Resolution 80/243 |  |
| Stresses that the UN80 Initiative is not a liquidity management measure, and requires going beyond a one-time reform exercise to also incorporate a culture of efficiency to ensure long-term effective and efficient mandate delivery, affirms the respective roles of the General Assembly and the Security Council with regard to special political missions, and requests the Secretary-General to pursue synergies to achieve greater efficiency in the management of post and non‑post resources, and to this end present proposals in his next budget submissions, while taking into account the different sizes, complexities and operational environments of special political missions (sect. XVII, para. 4). | Information on the efforts of the Secretariat to pursue synergies is detailed under the section on building and strengthening a culture of efficiency, paragraphs 88 to 93. |
| Recognizes the need to assess the impact of the reform efforts on mandate implementation, requests the Secretary-General to reflect thereon in his future budget submissions for special political missions, and also requests the Secretary-General to explore measures to apply zero-based budgeting, based on mandated activities (sect. XVII, para. 5). | Where applicable, the proposed programme plan for 2027 reflects changes arising from the UN80 Initiative. In particular, the tables of deliverables for each mission reflect updated planned deliverables for 2026, in line with the approved programme budget for 2026. Such changes, as applicable, are articulated in the respective thematic cluster report. Information on improved budgeting methodologies, including the continued application of zero-based budgeting is detailed in paragraph 95 of the present report. |

B.	Advisory Committee on Administrative and Budgetary Questions

| Brief description of the recommendation or request | Action taken to implement the recommendation or request |
| --- | --- |
| Advisory Committee on Administrative and Budgetary Questions (A/80/7/Add.10), as endorsed by the General Assembly in its resolution 80/243 A |  |
| The Advisory Committee notes that there are 3 posts proposed for conversion from international to national posts (including 2 National Professional Officer) and 11 national posts proposed for establishment for 2026. The Committee notes, however, that eight of the new posts proposed for establishment are proposed in conjunction with the proposed abolishment of eight national posts (see A/80/7/Add.14, paras. 21 and 25). The Committee notes with concern that the revised estimates contain only a limited number of proposals aimed at nationalization and the creation of national posts. The Committee is of the view that the current proposals do not take advantage of the review exercise to enhance national capacity development while adopting cost effective measures. The Committee trusts that a more strategic approach, including the identification of functions conducive to nationalization, will guide continuing efforts in the context of the UN80 Initiative and beyond and that information in that regard will be presented in future budget reports. (para. 32). | As part of the budget formulation process, missions were required to consider options for greater nationalization of functions, commensurate with mandate requirements and operational needs. The section on promoting national capacities (paras. 60- 63) contains information on the continued efforts by the special political missions to promote the nationalization of posts in response to the recommendation of the Advisory Committee. |
| The Advisory Committee has acknowledged the efforts made by the Secretariat to achieve cost efficiency, including by strengthening a data-driven approach in formulating budgetary requirements for air operations for special political missions. The Committee notes the measures undertaken to seek efficiencies and enhance the utilization of air fleets by maximizing opportunities for the sharing of air assets across missions and a portfolio of standby air solutions. The Committee trusts that efforts will be continued to ensure that the air fleets in the missions are used in the most effective and efficient manner, such as by exploring the possibility of refining the applied methodology to attribute greater weight to the latest utilization data, and that information in that regard will be provided in the next budget report. The Committee considers that there are possibilities for more cooperation among missions, in particular those located within the same proximity, with a view to ensuring the efficient and effective use of missions’ resources, as an important element of consolidation of the culture of efficiency in field operations, without prejudice to the implementation of mandates of individual missions. The Committee is also of the view that enhanced system-wide cooperation in the context of the UN80 Initiative presents an opportunity also to explore opportunities for further cooperation in the use of air assets, as appropriate. The Committee considers that Headquarters should provide guidance and proposals to missions on possible optimal arrangements of their air fleet and mechanisms for inter-mission cooperation with a view to promoting optimization and cost effectiveness of the use of resources (see A/79/724, paras. 41–42; and A/79/7/Add.1, para. 48) (para. 38). | The Secretariat has taken measures to seek efficiencies and enhance the utilization of the air fleets. The Secretariat continues to implement the category management strategy for commercial and military aviation, which is intended to improve aviation support efficiency and effectiveness, while meeting clients’ demands. To increase the Secretariat’s agility and responsiveness, DOS has expanded its portfolio of air solutions. In addition to the long-term air charter agreements and military aircraft services under letters of assistance, DOS has increased options for air services to include standby charter agreements, air ambulance services, and aircraft services under letters of assistance. Additionally, the Secretariat established the On-Call Logistics Capabilities Augmentation initiative in January 2025. The initiative enhances the United Nations’ ability to respond swiftly in emergencies by leveraging on-call support through pre-established arrangements with Member States. This includes critical resources such as aircraft for evacuation and delivery of supplies. In doing so, the initiative significantly boosts the United Nations’ surge capacity during crises and its ability to respond to ad hoc requests, thereby offering improved, efficient and timely support. Missions continue to make efforts to ensure that their air operation requirements are fulfilled in the most effective and efficient manner, including through inter-mission cooperation with other special political missions or peacekeeping missions, when possible. In UNOCA, the Office has reviewed its operational requirement for a dedicated aircraft in view of the non-utilization of the fixed wing during 2024 and 2025 owing to liquidity constraints and the high cost of special flights. In response, the Office has prioritized the use of commercial airlines for official travel during the preceding two financial periods and plans to continue this approach, resulting in the removal of the provision for air operations. UNAMA continues to explore the use of the regional on-call aircraft charter agreements such as those for the provision of air ambulance, aero-medical and aero-casualty evacuation services. Further the mission uses a data-driven approach to plan its air fleet taskings and flight routing, aimed to optimize the use of its aircraft. Under the established memorandum of understanding with the United Nations Humanitarian Air Service on cooperation in air operations, UNAMA uses their services when it is more cost-effective to transport its passengers and cargo with UNHAS aircraft rather than to task its dedicated aircraft. Because of its geographic location, opportunities for inter-mission cooperation, including with peacekeeping missions remain limited. Such support would entail long and empty positioning and dispositioning flights. UNAMA therefore requires dedicated aircraft to be deployed to the Mission area of responsibility on a continuous basis. |
| The Advisory Committee considers that efforts should be intensified to maximize the use of virtual meetings and to combine travel, with a view to limiting costs strictly to the minimum necessary. The Committee trusts that further efficiencies under official travel will continue to be explored and presented in the proposed programme budget for 2027 (para. 39). | Missions continue to implement measures to minimize their requirements under official travel, including prioritizing the appropriate use of technology to attend virtual meetings and online training and minimizing travel requirements to attend workshops, conferences and meetings. For the Panel of Experts, efficiency gains have been achieved for official travel of staff and expert travel requirements through the use of virtual meetings and the consolidation of travel itineraries, where feasible, as well as through the use of regional meeting formats with intelligence counterparts by the Analytical Support and Sanctions Monitoring Team. |
| The Advisory Committee, while noting the improvement made in the overall compliance rates during 2024, recalls that the General Assembly, in its resolution 77/263 B, reiterated its serious concern at the low compliance with the advance purchase policy directive in all travel categories and requested the Secretary-General to take more effective measures to improve the situation in order to reduce air travel costs, given that most official travel is not carried out for the purpose of emergency situations or unforeseen requirements (resolution 77/263 B, para. 8) (ibid.). (para. 41). | The overall performance for all special political missions has shown increases year on year from 18 per cent in 2019 to 50 per cent in 2025, reflecting continued efforts by Missions to comply with the advance purchase policy and monitor closely compliance to ensure full adherence to policy requirements. Such efforts include the strengthening of internal controls to ensured that official travel is planned sufficiently in advance to significantly reduce air travel costs, reduction of travel processing times, increased sensitization to staff members on compliance of the rule, enhanced monitoring of compliance enabled through timely follow up by travel focal points. |
| In its first report on the proposed programme budget for 2026 (A/80/7, chap. I, para. 69), the Advisory Committee recalled its recommendation endorsed by the General Assembly in its resolution 79/257 for the Secretary-General to make the arrangements necessary to track information on all expenditures corresponding to the appropriated amounts for training and to report thereon in future budget submissions and financial performance reports. The Committee notes that, while there have been adjustments in missions’ proposed resources for training in the context of the revised estimates for 2026, the per capita cost of training has increased in all missions, except UNAMI and the Office of the Special Envoy of the Secretary General for the Horn of Africa (para. 44). | Information on training expenditures is provided in the supplementary information packages. |
| The Advisory Committee acknowledges the efforts undertaken to identify efficiencies in the budget proposal for 2026 for the special political missions and further efforts in the revised estimates in the context of the UN80 Initiative. The Committee underscores the need for sustainable and quantifiable efficiency measures and gains, with transparent methodology, and an enhanced culture of efficiency for the Organization. The Committee has highlighted efficiencies that go beyond organizational restructuring and be anchored in a rigorous, transparent methodology applied by all entities to ensure consistency and comparability of results and be grounded in systematic workload and performance analysis (A/80/7, chap. I, para. 13). para. 46). | Information on the efforts undertaken and planned to strengthen a culture of efficiency is detailed under the section on building and strengthening a culture of efficiency, paragraphs 88 to 93. |
| Without prejudice to the distinct mandates of each entity, and subject to the decisions of the legislative bodies, as appropriate, the Advisory Committee trusts that the Secretary-General, in the context of the ongoing UN80 Initiative, will articulate a clearer strategic framework for identifying opportunities for consolidation of United Nations presence, in particular where multiple entities coexist, and for further rationalization of functions, in particular of senior and high-level positions required in special political missions with a smaller footprint, and for strengthened synergies among entities, including clear delineation of roles to be performed by the Missions and by the 25-16802 18/32 A/80/7/Add.10 Department of Political and Peacebuilding Affairs (see also A/80/7/Add.11, para. 8). The Committee considers that, in the context of constrained resources, efforts should be undertaken for comparative benchmarking among special political missions, enabling systematic assessment of their cost-effectiveness and comparative advantages in implementing mandates. (para. 48). | In the context of the UN80 Initiative, the report “Shifting the Paradigm: United to Deliver” outlines concrete steps towards a more streamlined and coherent field architecture. An initial set of measures has been advanced to consolidate and reconfigure selected presences, including: the integration of the United Nations Mission to Support the Hudaydah Agreement into the Office of the Special Envoy for Yemen, in line with Security Council resolution 2813 (2026); the closer alignment of the Mission of the Secretary-General’s Good Offices in Cyprus with the United Nations Peacekeeping Force in Cyprus, while preserving mandate delivery capacity; and the rationalization of the Office of the United Nations Representative to the Geneva International Discussions through optimized staffing and support structures. These measures, as articulated in the respective thematic cluster report reflect a broader shift towards more consolidated configurations, including the reduction of senior-level positions where appropriate. Overall, the proposed budget for 2027 for special political missions reflects a total decrease of 4 high level posts (D-1 and above) comprising 1 USG, and 3 D-1 posts. |
| The Advisory Committee considers that the revised estimates for 2026 do not provide comprehensive information on the impact of proposed budget reductions in the implementation of mandates, or on the organizational structure of the special political missions. The Committee trusts that detailed informed in that regard will be provided to the General Assembly at the time of consideration of the present report. The Committee underscores the importance of adopting effective mitigation measures to offset the decreased level of resources and reduce any potential adverse impact on mandate delivery. The Committee trusts that information on the implementation of mandate, along with impact-oriented performance metrics in comparison to past performance, will be provided in the proposed programme budget for 2027 (para. 49). | Detailed information on the impact of the proposed reductions on mandate implementation has been provided to the Fifth Committee during its consideration of the revised estimates. The Secretariat will be further guided by General Assembly resolution A/RES/80/251 on mandate creation, implementation and review, with a view to ensuring a more efficient and effective United Nations. |
| Taking into account the proposals in both the proposed programme budget and the revised estimates for 2026, the Advisory Committee notes that the backstopping posts at Headquarters will be 34 as at 1 January 2026 and 31 as at 1 November 2026, compared with 40 posts approved for 2025. The Committee reiterates its expectation that consolidated information on backstopping positions at Headquarters will continue to be provided in future budget submissions. The Committee trusts that the existing backstopping positions at Headquarters will continue to be reviewed annually, on the basis of workload analysis, in order to realign the capacities when changes in the mandates of the missions occur with a view to achieving more efficiency in backstopping support (see A/79/7/Add.1, para. 54) (para. 54). | Information on resources for backstopping is provided in paragraphs 137 to 141 with more detailed information included in the supplementary information package. |
| The Advisory Committee is of the view that, with the provision of full suite of services to the 10 clients who previously received only payroll and education grant services, administrative capacities in those 10 special political missions must be reviewed for possible streamlining and trusts that information and proposals in that regard will be provided in the next report. (para. 56). | Following the transition of KJSO clients to the RSCE, the Center will not be providing the full suite of services to all clients at this stage. |
| With the closure of the Kuwait Joint Support Office as of 30 June 2026, the Advisory Committee welcomes the proposed transfer of the client missions of the Support Office to the Regional Service Centre in Entebbe. The Committee trusts that the transfer will be well planned and coordinated under the leadership of the Department of Operational Support, with adequate resource planning and operational readiness, to ensure a seamless takeover of client missions and timely delivery of services. The Committee trusts that the impact on service provision to new client entities will be monitored and reported, to better assess both efficiencies and improvements in support to clients, and to track the challenges experienced in the process, to facilitate the adoption of mitigation measures, as appropriate (para. 58). | The Secretariat acknowledges the Committee’s observations regarding the transfer of KJSO client missions to the Regional Service Centre in Entebbe and affirms that the transition is being executed pursuant to a structured, risk‑based framework designed to ensure continuity of operations and adherence to established service standards. The phased sequencing of functions, supported by joint planning, parallel servicing arrangements, defined hyper‑care periods, and retained fallback capacity, is underpinned by robust governance through a dedicated transition oversight team and continuous performance monitoring using key performance indicators, consolidated risk registers, and strengthened internal controls. The RSCE will continue to systematically monitor and report on the impact of the transition on service provision—supported by enhanced feedback mechanisms and change‑management measures—ensuring that efficiencies, challenges, and required mitigation actions are transparently captured as RSCE assumes full responsibility for the expanded client base in accordance with its established shared‑services model. |
| The Advisory Committee trusts that special political missions will limit new acquisition of new vehicles and laptops, as possible, before undertaking the indicated comprehensive review of the composition of their ground fleet and laptop holdings in view of the reduced footprint, and that information on efficiencies achieved in that regard will be included in the next budget (para. 65). | For 2027, proposed acquisitions for new vehicles or equipment are made following a careful review of the Mission’s staffing levels and operational needs. Where such needs were identified, Missions were required to pprioritizing the use of existing assets, including the United Nations Reserve, strategic deployment stocks (SDS), the return, refurbishment and reuse programme (3R), and identified surplus property from other entities, prior to proposing the procurement of new item. In UNSCOL, efficiencies amounting to $438,100 were achieved through cost avoidance related to the non-acquisition of vehicles, equipment or supplies owing to the transfer of assets from UNIFIL in UNSCOL. |
| The Advisory Committee, while acknowledging specific requirements in field operations, highlights that most of the deviations arise from areas for which the Standard Cost and Ratio Manual does not provide guidance or specify ratios (see para. 67 above). The Committee recalls that the General Assembly expressed concern about the significant variance between the actual vehicle and computing device holdings and standard allocations in special political missions, and in this regard requested the Secretary-General to update the vehicle holding ratio and related guidance, as well as the computing device allocation ratio (in a way that allows the ratios to be relevant), to enable the missions to improve the transparency and accuracy of the relevant budget (see resolution 79/258 A). (para. 69). | The Vehicle Ratios previously developed require updates to ensure they remain relevant and reflect current realities, such as the need for vehicles for national staff and experts (in sanctions panels), and the categorization of duty stations which may give rise to varying safety and security requirements. Subject to availability of resources, the Secretariat will undertake a comprehensive assessment of client needs to ensure that the resulting ratios effectively support the implementation of their respective mandates. OICT has updated the distribution ratios of computing devices to better reflect realistic device allocations and identified areas and staff categories where additional computing devices may be required. This is communicated as part of the annual ICT budget guidelines to all field entities. |
| The Advisory Committee has expressed the view that it considers there is a need to enhance the performance information, including construction projects, for field-based special political missions under thematic cluster III (A/78/7/Add.1, para. 56; see also para. 58 above). The Committee concurs with the Board of Auditors on the need for more detailed information on construction projects in budget submissions and trusts that the recommendation of the Board of Auditors will be implemented expeditiously as soon as possible (para. 70). | Information on the efforts of the Secretariat to improve the presentation of financial performance, including construction projects is provided in paragraphs 18-119. |
| The Advisory Committee notes with concern that the requested information on annual appointments to geographical posts by special political missions, as endorsed by the General Assembly in its resolution 79/258 A, was not provided in the budget submission for 2026, and reiterates that information on annual appointments to geographical posts by mission, level, nationality and representation status should be provided in future budget submissions for the special political missions, with the information from 1 January to 31 December 2025 in the proposed programme budget for 2027 (see A/79/7/Add.1, para. 72) (para. 71). | Information on on annual appointments to geographical posts by special political missions is provided in the supplementary information package. |
| The Advisory Committee notes with concern that, during 2024, the first year since the widening of the posts subject to the desirable ranges system to all posts funded by the regular budget at the Professional and higher categories, including in special political missions, 40.8 per cent of the total appointments and reassignments with geographical status were nationals of overrepresented Member States, while only 20 per cent were of underrepresented Member States. The Committee recalls that the Assembly, in its resolution 77/278, encouraged the Secretary-General to work towards bringing each unrepresented and underrepresented Member State within its desirable range by 2030 and endorsed the recommendations of the Committee, which underscored that additional efforts are needed for progress to be achieved (see A/80/7, para. 52). (para. 72). | The Secretariat acknowledges the Advisory Committee’s observation and recognizes that improving geographical balance requires sustained and coordinated efforts. A key challenge remains the limited number of applications from nationals of unrepresented and underrepresented Member States. To address this, the Secretariat is strengthening targeted outreach through partnerships with Member States, universities, professional networks, and the broader UN country presence, including Resident Coordinators and UN Information Centres. It is also developing purposeful partnerships to build sustainable talent pipelines and support candidates through capacity-development initiatives that improve their preparedness for UN recruitment processes. At the same time, reforms under Staff Selection programme 2.0 aim to enhance transparency, efficiency, and skills-based recruitment, while improving access and fairness in selection processes. The Secretariat also notes that progress depends on adequate financial resources, as liquidity constraints can affect the timely filling of posts. Through strengthened outreach, recruitment reforms, strategic partnerships with Member States, and adequate resources, the Secretariat aims to achieve sustained progress toward equitable geographical distribution. |

__________________

__________________

The position of the Special Adviser was discontinued as of 1 January 2026 following the approval by the General Assembly of the proposal made in the revised estimates for the 2026 programme budget (A/80/400). Accordingly, the name of the mission is adjusted, from the Office of the Special Adviser of the Secretary General on Cyprus, to the current name.

The position of Special Envoy for the Implementation of Security Council resolution 1559 (2004), at the level of Under-Secretary-General, is proposed for abolishment as part of efforts to enhance coherence and synergies in line with the UN80 Initiative. The functions previously exercised by the Special Envoy will be assumed by the Department of Peacebuilding and Political Affairs led by the Under-Secretary-General for Peacebuilding and Political Affairs, supported by dedicated capacity to implement the mandate. Accordingly, the name of the mission is adjusted, from the Office of the Special Envoy for the Implementation of Security Council resolution 1559(2004), to the current name.

In that report, the Assembly endorsed the recommendation of the ACABQ in its report (A/78/744/Add.6) that “In view of the evolving landscape of peacekeeping operations, the Advisory Committee emphasizes the need to review the role of the Regional Service Centre within the comprehensive context of the global support architecture, with a view to potentially providing additional services to other entities, as well as developing broader cooperation with regional organizations, such as the African Union.”

United Nations Interim Force in Lebanon, United Nations Disengagement Observer Force, UNLB, United Nations Interim Administration Mission in Kosovo, United Nations Peacekeeping Force in Cyprus, United Nations Truce Supervision Organization (UNTSO), United Nations Military Observer Group in India and Pakistan (UNMOGIP), Office of the United Nations Special Coordinator for the Middle East Peace Process, Office of the Special Envoy of the Secretary-General for Syria, Office of the Special Envoy of the Secretary-General for Yemen, United Nations Regional Centre for Preventive Diplomacy for Central Asia, Office of the United Nations Special Coordinator for Lebanon, Verification Mission in Colombia, BINUH and UNAMA.

The Regional Service Centre will provide core services to the UNAMA, the United Nations Regional Centre for Preventive Diplomacy for Central Asia, the Office of the Special Envoy of the Secretary-General for Yemen, the Office of the Special Envoy of the Secretary-General for Syria, and BINUH, as well as the United Nations Interim Administration Mission in Kosovo and the United Nations Peacekeeping Force in Cyprus, which were receiving non-core services under the Kuwait Joint Support Office. The United Nations Interim Force in Lebanon, the United Nations Disengagement Observer Force, UNTSO, UNMOGIP, the Office of the United Nations Special Coordinator for the Middle East Peace Process, the Office of the United Nations Special Coordinator for Lebanon, the United Nations Verification Mision in Colombia and UNLB will receive non-core services effective 1 July 2026.

Excluding UNTSO, UNMOGIP, United Nations Educational, Scientific and Cultural Organization (UNSCO) which are funded under the programme budget. Their respective share of RSCE for 2027 is presented in the proposed programme budget of these three entities (A/81/6 (Sect.5) and A/81/6 (Sect.3) respectively).

In December 2021, DOS issued a guide on planning for the nationalization of the workforce. The guide provides practical information for conducting nationalization in the context of operational workforce planning at the entity level and is aimed at setting consistent standards and approaches on nationalization across entities.

A total of 12 posts were nationalized in 2016, 1 in 2017, 2 in 2018, 5 in 2019, 7 in 2020, 4 in 2021, 19 in 2022, 9 in 2023, 5 in 2024, 7 in 2025 and 15 in 2026.

Legislative reductions on official travel against the Secretary General budget proposals: 2020 - 0.9 per cent; 2021- 17.9 per cent, 2022 – 9.8 per cent; 2023 – 5.6 per cent; 2024 -  4.1 per cent; 2025-3.4 per cent; and 2026 – 4.6 per cent.

The standard ratio for vehicles ratio does not take into account the need for vehicles for national General service and Local level staff.

Analytical Support and Sanctions Monitoring Team pursuant to resolutions 1526 (2004) and 2253 (2015) concerning ISIL (Da’esh), Al-Qaida and the Taliban and associated individuals and entities; Office of the Ombudsperson established pursuant to Security Council resolution 1904 (2009); Office of the Focal Point for Delisting; Panel of Experts on the Islamic Republic of Iran; and Support to the Security Council Committee established pursuant to resolution 1540 (2004) on the non-proliferation of all weapons of mass destruction.

Office of the Special Envoy of the Secretary-General for Syria, Office of the Special Envoy of the Secretary-General for Yemen, United Nations Regional Centre for Preventive Diplomacy for Central Asia, Office of the United Nations Special Coordinator for Lebanon, United Nations Integrated Office in Haiti, United Nations Verification Mission in Colombia, and United Nations Assistance Mission in Afghanistan.