Eightieth session

Agenda item 156 (a)

Financing of the United Nations peacekeeping forces in the Middle East: United Nations Disengagement Observer Force

Budget performance for the period from 1 July 2024 to 30 June 2025 and budget for the period from 1 July 2026 to 30 June 2027 for the United Nations Disengagement Observer Force

Report of the Secretary-General

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Mandate, results achieved and planned outcome |  |  | 6 |
| - Mandate |  |  | 6 |
| - Budget implementation for 2024/25 |  |  | 6 |
| - Planning assumptions and mission support initiatives for 2026/27 |  |  | 7 |
| - Regional mission cooperation |  |  | 8 |
| - Human resources |  |  | 9 |
| - Proposed staffing changes |  |  | 10 |
| - Results-based budgeting frameworks |  |  | 11 |
| - Financial resources |  |  | 13 |
| - Overall |  |  | 13 |
| - Non-budgeted contributions |  |  | 14 |
| - Efficiency gains |  |  | 14 |
| - Unencumbered balance |  |  | 15 |
| - Cancellation of prior-period obligations |  |  | 15 |
| - Other revenue and adjustments, and borrowing |  |  | 16 |
| - Vacancy factors |  |  | 17 |
| - Quick-impact projects |  |  | 17 |
| - Analysis of variances |  |  | 18 |
| - Actions to be taken by the General Assembly |  |  | 20 |
| - Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/307, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly |  |  | 21 |
| - General Assembly |  |  | 21 |
| - Advisory Committee on Administrative and Budgetary Questions |  |  | 22 |
| Annex |  |  |  |
| Organization chart |  |  | 23 |
| Map |  |  | 24 |

Summary

The present report contains the budget performance of and the budget for the United Nations Disengagement Observer Force (UNDOF) for the period from 1 July 2024 to 30 June 2025 and 1 July 2026 to 30 June 2027, respectively.

The 2024/25 period posed significant challenges for UNDOF, characterized by heightened regional volatility and security developments in the Syrian Arab Republic that drastically altered the UNDOF area of operations and disrupted key supply routes. The fall of the Government in the Syrian Arab Republic created additional uncertainty and affected the operational environment, requiring the Force to identify and implement alternative measures to sustain its operations. Notwithstanding those developments, UNDOF adapted successfully to the changes and sustained its mandated activities in a continually volatile environment, achieving results in alignment with the Force’s key priorities for the period.

During the 2026/27 period, UNDOF will continue to implement its mandated activities, including observation from its positions, on both the Alpha and Bravo sides, and patrolling activities from Camp Ziouani and Camp Faouar into the area of separation.

Financial resources

The Force incurred $67.9 million in expenditure for the 2024/25 budget performance period, representing a resource utilization rate of 98.7 per cent, compared with $66.9 million in expenditure and a resource utilization rate of 96.5 per cent in the 2023/24 period.

The unencumbered balance of $0.9 million reflects the net impact of: (a) the reduced requirements for military contingents attributable primarily to less contingent-owned major equipment; (b) the increased requirements for civilian personnel attributable primarily to the higher actual requirements for international and national General Service staff; and (c) the reduced requirements for operational costs attributable to the lower actual costs of petrol, oil and lubricants and the reprioritization of resources in the light of liquidity challenges.

The budget proposed for the 2026/27 period in the amount of $61.6 million represents a decrease of $8.0 million, or 11.4 per cent, compared with the apportionment of $69.6 million approved for the 2025/26 period.

The estimates for the 2026/27 period reflect reduced requirements for: (a) military and police personnel, attributable primarily to the higher vacancy rate for military personnel; (b) civilian personnel, attributable primarily to the abolishment of posts and temporary positions; and (c) operational costs, attributable primarily to lower costs for fuel for generators and vehicles and communications and information technology equipment and services.

(Thousands of United States dollars; budget year is from 1 July to 30 June)

Category; 2024/25 apportionment; 2024/25 expenditure; Variance; 2025/26 apportionment; 2026/27 cost estimates; Variance. Unencumbered balance; Percentage; Amount; Percentage. Military and police personnel; 41 945.0; 41 386.3; 558.7; 1.3; 43 122.3; 36 680.1; (6 442.2); (14.9). Civilian personnel; 15 528.8; 16 504.8; (976.0); (6.3); 15 844.6; 15 322.7; (521.9); (3.3). Operational costs; 11 270.0; 9 981.1; 1 288.9; 11.4; 10 609.5; 9 612.3; (997.2); (9.4). Gross requirements; 68 743.8; 67 872.2; 871.6; 1.3; 69 576.4; 61 615.1; (7 961.3); (11.4). Category; 2024/25 apportionment; 2024/25 expenditure; Variance; 2025/26 apportionment; 2026/27 cost estimates; Variance. Unencumbered balance; Percentage; Amount; Percentage. Staff assessment income; 1 638.2; 1 977.1; (338.9); (20.7); 1 734.6; 1 582.9; (151.7); (8.7). Net requirements; 67 105.6; 65 895.1; 1 210.5; 1.8; 67 841.8; 60 032.2; (7 809.6); (11.5). Voluntary contributions in kind (budgeted); –; –; –; –; –; –; –; –. Total requirements; 68 743.8; 67 872.2; 871.6; 1.3; 69 576.4; 61 615.1; (7 961.3); (11.4).

Human resourcesa The proposed budget provides for the deployment of uniformed personnel and civilian staff as follows:

Military observers; Military contingents; United Nations police; Formed police units; Inter-national staff; National Professional Officers; National General Service; Temporary positionsb; United Nations Volunteers; Government-provided personnel; Total. Executive direction and management. Approved 2024/25; –; –; –; –; 5; –; 1; 1; –; –; 7. Actual 2024/25; –; –; –; –; 4; –; 1; 1; –; –; 6. Approved 2025/26; –; –; –; –; 5; –; 1; 1; –; –; 7. Proposed 2026/27; –; –; –; –; 4; –; 1; –; –; –; 5. Components. Operations. Approved 2024/25; –; 1 250; –; –; –; –; –; –; –; –; 1 250. Actual 2024/25; –; 1 175; –; –; –; –; –; –; –; –; 1 175. Approved 2025/26; –; 1 250; –; –; –; –; –; –; –; –; 1 250. Proposed 2026/27; –; 1 250; –; –; –; –; –; –; –; –; 1 250. Support. Approved 2024/25; –; –; –; –; 47; 1; 89; 1; –; –; 138. Actual 2024/25; –; –; –; –; 40; 1; 82; 1; –; –; 124. Approved 2025/26; –; –; –; –; 46; 1; 89; 1; –; –; 137. Proposed 2026/27; –; –; –; –; 46; 1; 85; –; –; –; 132. Total. Approved 2024/25; –; 1 250; –; –; 52; 1; 90; 2; –; –; 1 395. Actual 2024/25; –; 1 175; –; –; 44; 1; 83; 2; –; –; 1 305. Approved 2025/26; –; 1 250; –; –; 51; 1; 90; 2; –; –; 1 394. Proposed 2026/27; –; 1 250; –; –; 50; 1; 86; –; –; –; 1 387. Net change; –; –; –; –; (1); –; (4); (2); –; –; (7). a Represents the highest level of authorized/proposed strength. b Funded under general temporary assistance.

Legislative history (Thousands of United States dollars)

2024/25; 2025/26. Report; Date; Amount; Report; Date; Amount. Proposed budget – Secretary-General; A/78/720; 19 January 2024; 68 845.8; A/79/761; 30 January 2025; 70 100.9. Recommendation – Advisory Committee on Administrative and Budgetary Questions; A/78/744/Add.1; 4 April 2024; 68 743.8; A/79/724/Add.1; 28 March 2025; 69 836.4. Appropriationa – General Assembly; A/RES/78/304; 28 June 2024; 68 743.8; A/RES/79/307; 30 June 2025; 69 576.4. Appropriation (net); 67 105.6; 67 841.8.

a The total amount has been assessed on Member States. The actions to be taken by the General Assembly are set out in section IV of the present report.

I.	Mandate, results achieved and planned outcome

A.	Mandate

1.	The mandate of the United Nations Disengagement Observation Force (UNDOF) was established by the Security Council in its resolution 350 (1974). The mandate for the performance period was provided in its resolutions 2737 (2024) and 2766 (2024). The most recent extension of the mandate was authorized by the Council in its resolution 2811 (2025), by which it extended the Force’s mandate until 30 June 2026.

2.	The Force is mandated to help the Security Council to achieve the overall objective of advancing peace and security.

B.	Budget implementation for 2024/25

3.	During the 2024/25 period, the security situation in the UNDOF area of operations remained volatile, marked by continued violations of the 1974 Disengagement of Forces Agreement. The violations intensified during heightened regional tensions and following the fall of the Government of the Syrian Arab Republic on 8 December 2024. Notwithstanding complex challenges, UNDOF sustained full operational capability and prioritized the safety of its personnel by conducting systematic mine-clearance operations, also to the benefit of the civilian population in the area, reconnaissance patrols and risk-mitigation measures in previously vacated areas.

4.	UNDOF carried out six quick-impact projects during the reporting period related mainly to education and health. The projects provided tangible support to the local communities, while reinforcing the Force’s role in maintaining stability and fostering positive relations with the local population.

5.	The Force’s headquarters continued to be based at Camp Faouar, on the Bravo side, and logistical support and coordination were conducted through Camp Ziouani, on the Alpha side. Force protection and contingency planning remained a high priority, with regular evacuation and security drills conducted to address identified risks and maintain preparedness under evolving security dynamics.

6.	In discharging its mandate, UNDOF maintained its presence throughout the area of separation with 15 positions, 1 position on the Alpha side (Israeli-occupied Golan) and at its headquarters in Camp Faouar, logistics base in Camp Ziouani and the Charlie gate. Operational effectiveness was further enhanced by the activities of United Nations Truce Supervision Organization (UNTSO) military observers, serving in Observer Group Golan under UNDOF operational control, who provided static observation, strengthened situational awareness and supported investigations into incidents that occurred in the area of operations.

7.	During 2024/25, UNDOF established and maintained a constructive and cooperative relationship with the interim authorities in the Syrian Arab Republic. This positive engagement enabled effective operational coordination, facilitated the Force’s freedom of movement and supported its monitoring responsibilities under the ceasefire arrangements.

8.	On 7 December 2024, the Israeli Defense Forces entered the area of separation and established several positions in the area. UNDOF continued to maintain its regular reporting on developments in its area of operations, liaison with both parties to ensure that they upheld their obligations under the Disengagement of Forces Agreement and cease any action that was inconsistent with the Agreement, taking the measures necessary to prevent the risk of an escalation of tensions. Those efforts helped to preserve stability and supported adherence to the ceasefire arrangements.

C.	Planning assumptions and mission support initiatives for 2026/27

9.	The ceasefire between Israel and the Syrian Arab Republic, in general, has been maintained, notwithstanding multiple significant violations of the Disengagement of Forces Agreement by the parties and amid regional escalation. While the overall security situation in the UNDOF area of operations remains volatile, UNDOF liaison with both parties is crucial in ensuring that the parties uphold their obligations under the terms of the Agreement to maintain the ceasefire and prevent further violations and escalation across the ceasefire line.

10.	During the 2026/27 period, UNDOF will carry out its mandated tasks, including observation activities from its positions, on both the Alpha and Bravo sides and patrolling activities from Camp Ziouani and Camp Faouar into the area of separation. UNDOF will enhance its liaison with both sides to ensure that there is no military personnel or activity in the area of separation and that they accord UNDOF the freedom of movement in conducting its mandated activities safely and securely. The area of separation is approximately 80 km in length from north to south and varies in width from 12.5 km along the crest of Mount Hermon in the north to less than 400 m at the border between Jordan and the Syrian Arab Republic.

11.	UNDOF, assisted by the military observers of UNTSO serving in Observer Group Golan under UNDOF operational control, will continue to carry out fortnightly inspections of military positions on both the Alpha and Bravo sides, maintaining liaison with both parties in all sectors of the relevant sides of the areas of limitation. Subject to security conditions, the Force will continue to restore, repaint and refurbish the barrels marking the ceasefire line and the Bravo line. In addition, UNDOF will implement quick-impact projects on the Bravo side as a confidence-building measure.

12.	The Force will also clear mines, unexploded ordnance and improvised explosive devices within the area of separation for operational purposes, thereby enhancing the safety of its personnel. In line with the priorities of Action for Peacekeeping Plus, UNDOF will implement additional measures to further improve the safety and security of mission personnel in an integrated manner and enhance the overall effectiveness of the Force.

Mission support initiatives

13.	During the 2026/27 period, UNDOF will prioritize the refurbishment of one position and advance its environmental initiatives through the installation of solar power systems at one selected position, contributing to energy efficiency and sustainability.

14.	UNDOF will continue routine restoration and major maintenance and repairs to preserve the functionality of roads, fences, snow poles, watchtowers, sentry points, water wells and other force infrastructure. Some of the work approved in earlier periods was postponed owing to the liquidity challenges and the presence of the Israel Defense Forces in the Force’s area of operations, which will resume in the 2026/27 period.

15.	UNDOF will continue the implementation of its environmental projects, such as the installation of solar power systems that were postponed during the 2025/26 period, in order to enhance the self-sufficiency of all its positions while reducing its carbon footprint in line with the Organization’s environmental strategy.

16.	In the context of the Secretary-General’s UN80 Initiative, the budget proposal reflects efficiency measures implemented through organizational optimization, functional streamlining and allocative efficiencies. The efficiency will be achieved primarily through adjustments to personnel, based on the Force’s review of operational requirements and workload distribution. The Force proposes the reduced deployment of military contingent personnel and military staff officers and the abolishment of civilian posts and temporary positions, while maintaining a focus on the delivery of core mandated activities. Reductions in uniformed personnel reflect allocative efficiencies, whereby resources will be realigned to correspond with evolving operational priorities and refined task prioritization. Through optimized deployment, strengthened coordination and adjustments in the sequencing and modalities of activities, the Force has assessed that essential operational outputs can be delivered with the revised footprint. The corresponding decrease in major equipment requirements reflects the realignment of equipment with the reduced operational footprint. Civilian staffing reductions will be implemented through functional streamlining and organizational optimization, including the redistribution of responsibilities, merging of functions and adjustments to internal workflows. In some cases, functions associated with abolished posts and temporary positions will be absorbed, resulting in a leaner structure while preserving essential capacities.

17.	The proposed efficiency measures are expected to result in a more streamlined organizational structure; however, flexibility and expediency in responding to peaks in workload or unanticipated operational demands would be reduced. While all core mandated activities will continue, some tasks may be implemented with adjusted modalities or modified timelines. Similarly, reductions in major equipment are expected to have a minor operational impact, given that resources are aligned carefully with essential activities and force posture requirements. These adjustments reflect the need to balance operational effectiveness with the reduced level of personnel.

18.	To mitigate potential risks associated with the proposed efficiency measures, the Force has strengthened internal coordination, management oversight and prioritization mechanisms. The responsibilities will be redistributed among remaining personnel, and coordination between civilian and uniformed components will be reinforced to ensure continuity of operations. The Force will continue to monitor the impact of the efficiency measures, including the impact of changes in equipment allocation on the Force’s operations, and will take corrective action, as necessary, to ensure effective mandate delivery.

D.	Regional mission cooperation

19.	During the 2024/25 period, UNDOF continued to ensure coordination with other peacekeeping missions in the region, namely, UNTSO, the United Nations Interim Force in Lebanon (UNIFIL) and the United Nations Peacekeeping Force in Cyprus, to address issues of regional interest. UNDOF continued to receive field technology services and assistance from UNIFIL in the movement of its supplies and other logistical movements from Beirut, eliminating the duplication of effort between the peacekeeping missions. The Regional Conduct and Discipline Section based at UNIFIL continued to advise the head of mission of UNDOF, including on prevention activities related to sexual exploitation, sexual abuse, sexual harassment, fraud and other prohibited conduct.

20.	UNDOF continued to provide information and communications technology and procurement services to the Office of the Special Envoy of the Secretary-General for Syria in Damascus and to serve as the United Nations house bank for the Syrian Arab Republic to process payroll and vendor payments for that Office. UNDOF received support from the Kuwait Joint Support Office, in which one General Service staff member was embedded to process payroll for the Force’s national staff and military staff officers.

21.	UNDOF continued to work with the UNTSO liaison office in Damascus and provided logistical support, including in the provision of rations, fuel and medical services on a cost-recovery basis.

22.	During the 2026/27 period, the Force will continue the same regional cooperation from the 2024/25 period, apart from the cooperation with the Kuwait Joint Support Office. After the closure of the Office on 30 June 2026, the services thereafter would be provided by the Regional Service Centre in Entebbe, Uganda.

E.	Human resources

Executive direction and management

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | 1 | – | 1 | 2 | 1 | 5 | – |  | 1 | 1 | – |  | – | – | 6 |
| Actual posts 2024/25 | 1 | – | 1 | 1 | 1 | 4 | – |  | 1 | 1 | – |  | – | – | 5 |
| Approved posts 2025/26 | 1 | – | 1 | 2 | 1 | 5 | – |  | 1 | 1 | – |  | – | – | 6 |
| Proposed posts 2026/27 | 1 | – | – | 2 | 1 | 4 | – |  | 1 | 1 | – |  | – | – | 5 |
| Net change | – | – | (1) | – | – | (1) | – |  | – | – | – |  | – | – | (1) |
| Approved temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Actual temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Approved temporary positionsa 2025/26 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Proposed temporary positionsa 2026/27 | – | – | – | – | – | – | – |  | – | – | – |  | – | – | – |
| Net change | – | – | (1) | – | – | (1) | – |  | – | – | – |  | – | – | (1) |
| Total, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | 1 | – | 2 | 2 | 1 | 6 | – |  | 1 | 1 | – |  | – | – | 7 |
| Actual 2024/25 | 1 | – | 2 | 1 | 1 | 5 | – |  | 1 | 1 | – |  | – | – | 6 |
| Approved 2025/26 | 1 | – | 2 | 2 | 1 | 6 | – |  | 1 | 1 | – |  | – | – | 7 |
| Proposed 2026/27 | 1 | – | – | 2 | 1 | 4 | – |  | 1 | 1 | – |  | – | – | 5 |
| Net change | – | – | (2) | – | – | (2) | – |  | – | – | – |  | – | – | (2) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 546.9 |  |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 069.4 |  |

Component 1: operations

| Military personnel |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 1 250 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 1 175 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 1 250 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 1 250 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | – |

Component 2: support

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | – | 1 | 9 | 6 | 31 | 47 | 1 |  | 89 | 90 | – |  | – | – | 137 |
| Actual posts 2024/25 | – | 1 | 8 | 4 | 27 | 40 | 1 |  | 82 | 83 | – |  | – | – | 123 |
| Approved posts 2025/26 | – | 1 | 11 | 5 | 29 | 46 | 1 |  | 89 | 90 | – |  | – | – | 136 |
| Proposed posts 2026/27 | – | 1 | 11 | 5 | 29 | 46 | 1 |  | 85 | 86 | – |  | – | – | 132 |
| Net change | – | – | – | – | – | – | – |  | (4) | (4) | – |  | – | – | (4) |
| Approved temporary positionsa 2024/25 | – | – | – | 1 | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Actual temporary positionsa 2024/25 | – | – | – | 1 | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Approved temporary positionsa 2025/26 | – | – | – | 1 | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Proposed temporary positionsa 2026/27 | – | – | – | – | – | – | – |  | – | – | – |  | – | – | – |
| Net change | – | – | – | (1) | – | (1) | – |  | – | – | – |  | – | – | (1) |
| Total, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | – | 1 | 9 | 7 | 31 | 48 | 1 |  | 89 | 90 | – |  | – | – | 138 |
| Actual 2024/25 | – | 1 | 8 | 5 | 27 | 41 | 1 |  | 82 | 83 | – |  | – | – | 124 |
| Approved 2025/26 | – | 1 | 11 | 6 | 29 | 47 | 1 |  | 89 | 90 | – |  | – | – | 137 |
| Proposed 2026/27 | – | 1 | 11 | 5 | 29 | 46 | 1 |  | 85 | 86 | – |  | – | – | 132 |
| Net change | – | – | – | (1) | – | (1) | – |  | (4) | (4) | – |  | – | – | (5) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 255.1 |  |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 253.3 |  |

a	Funded under general temporary assistance.

F.	Proposed staffing changes

| Component/office/section/unit | Type | Number | Level | Functional title | Action |
| --- | --- | --- | --- | --- | --- |
| Executive direction and management |  |  |  |  |  |
| Office of the Force Commander |  |  |  |  |  |
| Post | International | (1) | P-4 | Legal Officer | Abolishment |
| Temporary position | International | (1) | P-4 | Military Liaison Officer | Abolishment |
| Subtotal, executive direction and management |  | (2) |  |  |  |
| Component 2: Support |  |  |  |  |  |
| Mission Support Division |  |  |  |  |  |
| Transport Section |  |  |  |  |  |
| Post | National | (1) | NGS | Vehicle Technician | Abolishment |
|  | National | (1) | NGS | Vehicle Technician | Abolishment |
| Subtotal |  | (2) |  |  |  |
| Engineering Section |  |  |  |  |  |
| Post | National | (1) | NGS | Electrician | Abolishment |
| Temporary position | International | (1) | P-3 | Engineer | Abolishment |
| Subtotal |  | (2) |  |  |  |
| Kuwait Joint Support Office |  |  |  |  |  |
| Post | National | (1) | NGS | Finance Assistant | Abolishment |
| Subtotal |  | (1) |  |  |  |
| Subtotal, support |  | (5) |  |  |  |
| Total, civilian personnel |  | (7) |  |  |  |

23.	The proposed abolishment of posts and temporary positions is due to efficiency gains achieved through functional streamlining and organizational optimization, including the redistribution of responsibilities, the merging of functions and adjustments to internal workflows. In some cases, the associated functions will be absorbed, resulting in a leaner structure and maintaining effective support services while aligning staffing levels with actual operational requirements.

24.	It is proposed that one post be abolished that was embedded in the Kuwait Joint Support Office, from where it provides services for the processing of payroll for UNDOF national staff and military staff officers. Following the decision by the General Assembly to close the Office on 30 June 2026, the support services would thereafter be provided by the Regional Service Centre in Entebbe.

G.	Results-based budgeting frameworks

Component 1: operations

| Expected accomplishment | Indicators of achievement |
| --- | --- |
| 1.1 The parties act in accordance with and comply with the Agreement on Disengagement between Israeli and Syrian Forces of 1974 | 1.1.1 Maintenance of the separation of forces and areas of limitation (2022/23: 766; 2023/24: 618; 2024/25: 558; 2025/26: no letters of protest; 2026/27: no letters of protest) |
| 1.2 Reduced threat of mines and improvised explosive devices in the area of separation | 1.2.1 No UNDOF personnel injured or killed by mines or unexploded ordnance (2022/23: no casualties; 2023/24: no casualties; 2024/25: no casualties; 2025/26: no casualties; 2026/27: no casualties) |
| 1.3 Increased awareness of UNDOF mandate among the civilian population | 1.3.1 No incidents of inadvertent crossing of the ceasefire line by civilians in the area of separation. (2022/23: no incidents; 2023/24: one incident; 2024/25: no incidents; 2025/26: no incidents; 2026/27: no incidents) |
| 1.4 Maintain the operational capability and readiness to enable the full implementation of the mandate | 1.4.1 Full implementation of the mandate |
| External factors |  |
| Security situation will remain stable within the UNDOF area of operations to allow full implementation of the mandate |  |

Component 2: support

| Expected accomplishment | Indicators of achievement |
| --- | --- |
| 2.1 Rapid, effective, efficient and responsible support services for the Force | 2.1.1 Average annual percentage of women international civilian staff (2022/23: 29 per cent; 2023/24: 28 per cent; 2024/25: 30 per cent; 2025/26: ≥ 28 per cent; 2026/27: ≥ 28 per cent) |
|  | 2.1.2 Average number of days for roster recruitments, from closing of the job opening to candidate selection, for international candidates (2022/23: ≤ 60; 2023/24: 30; 2024/25: 60; 2025/26: ≤ 60; 2026/27: ≤ 60) |
|  | 2.1.3 Average number of days for post-specific recruitments, from closing of the job opening to candidate selection, for international candidates (2022/23: 180; 2023/24: not applicable; 2024/25: not applicable; 2025/26: ≤ 120; 2026/27: ≤ 120) |
|  | 2.1.4 Overall score on the property management index based on 20 underlying key performance indicators (2022/23: 1,987; 2023/24: 1,962; 2024/25: 1,991; 2025/26: ≥ 1,800; 2026/27: ≥ 1,800) |
|  | 2.1.5 Percentage of contingent personnel in standard-compliant United Nations accommodations at 30 June, in accordance with memorandums of understanding (2022/23: 100 per cent; 2023/24: 100 percent: 2024/25: 100 per cent; 2025/26: 100 per cent; 2026/27: 100 per cent) |
|  | 2.1.6 Compliance of vendors with United Nations rations standards for delivery, quality and stock management (2022/23: 100 per cent; 2023/24: 100 per cent; 2024/25: 100 per cent; 2025/26: 100 per cent; 2026/27: 100 per cent) |
| External factors |  |
| Several factors may have an impact on the ability of the Force to deliver the mandated activities and outputs as planned, including changes in the political, security, economic and humanitarian contexts or weather conditions not foreseen in the planning assumptions; other instances of force majeure; and changes in mandate during the reporting period. |  |

Evaluation activities

25.	The following evaluation completed by the Office of Internal Oversight Services during the 2024/25 period has guided UNDOF planning for the 2026/27 period: “Evaluation of the United Nations Disengagement Observer Force, 28 May 2025”.

26.	In response to the results of the evaluation referenced above, the Force has undertaken the following actions: (a) developed a standard operating procedure for quick-impact projects, incorporating requirements for comprehensive needs assessments, compliant implementing strategies and monitoring and evaluation mechanisms to ensure the effective use of approved resources; and (b) established a plan to develop a structured knowledge management system by optimizing use of the Force’s SharePoint and training staff and explore the options to combine the Comprehensive Planning and Performance Assessment System, the Situational Awareness Geospatial Enterprise and Unite Aware to address the Force’s needs.

27.	No evaluation is planned for the 2026/27 period.

II.	Financial resources

A.	Overall

(Thousands of United States dollars; budget year is from 1 July to 30 June)

|  | 2024/25 apportionment | 2024/25 expenditure | Variance |  | 2025/26 apportionment | 2026/27 cost estimates | Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Unencumbered balance | Percentage |  |  | Amount | Percentage |
| Category | (1) | (2) | (3)=(1)-(2) | (4)=(3)÷(1) | (5) | (6) | (7)=(6)-(5) | (8)=(7÷5) |
| Military and police personnel |  |  |  |  |  |  |  |  |
| Military observers | – | – | – | – | – | – | – | – |
| Military contingents | 41 945.0 | 41 386.3 | 558.7 | 1.3 | 43 122.3 | 36 680.1 | (6 442.2) | (14.9) |
| United Nations police | – | – | – | – | – | – | – | – |
| Formed police units | – | – | – | – | – | – | – | – |
| Subtotal | 41 945.0 | 41 386.3 | 558.7 | 1.3 | 43 122.3 | 36 680.1 | (6 442.2) | (14.9) |
| Civilian personnel |  |  |  |  |  |  |  |  |
| International staff | 11 206.9 | 11 777.7 | (570.8) | (5.1) | 11 258.9 | 11 415.0 | 156.1 | 1.4 |
| National Professional Officer | 55.3 | 62.2 | (6.9) | (12.5) | 60.4 | 61.1 | 0.7 | 1.2 |
| National General Service staff | 4 014.8 | 4 245.0 | (230.2) | (5.7) | 4 028.2 | 3 846.6 | (181.6) | (4.5) |
| United Nations Volunteers | – | – | – | – | – | – | – | – |
| General temporary assistance | 251.8 | 419.9 | (168.1) | (66.8) | 497.1 | – | (497.1) | (100.0) |
| Government-provided personnel | – | – | – | – | – | – | – | – |
| Subtotal | 15 528.8 | 16 504.8 | (976.0) | (6.3) | 15 844.6 | 15 322.7 | (521.9) | (3.3) |
| Operational costs |  |  |  |  |  |  |  |  |
| Civilian electoral observers | – | – | – | – | – | – | – | – |
| Consultants and consulting services | 2.8 | 23.6 | (20.8) | (742.9) | – | – | – | – |
| Official travel | 187.7 | 211.9 | (24.2) | (12.9) | 298.4 | 297.5 | (0.9) | (0.3) |
| Facilities and infrastructure | 6 114.9 | 5 255.1 | 859.8 | 14.1 | 5 813.0 | 5 373.1 | (439.9) | (7.6) |
| Ground transportation | 1 565.0 | 1 299.9 | 265.1 | 16.9 | 1 135.5 | 956.8 | (178.7) | (15.7) |
| Air operations | – | – | – | – | – | – | – | – |
| Marine operations | 25.0 | 47.3 | (22.3) | (89.2) | 25.0 | 25.0 | – | – |
| Communications and information technology | 1 467.5 | 1 480.2 | (12.7) | (0.9) | 1 763.7 | 1 344.3 | (419.4) | (23.8) |
| Medical | 299.9 | 233.8 | 66.1 | 22.0 | 289.7 | 289.7 | – | – |
| Special equipment | – | – | – | – | – | – | – | – |
| Other supplies, services and equipment | 1 307.2 | 1 135.1 | 172.1 | 13.2 | 984.2 | 1 025.9 | 41.7 | 4.2 |
| Quick-impact projects | 300.0 | 294.2 | 5.8 | 1.9 | 300.0 | 300.0 | – | – |
| Subtotal | 11 270.0 | 9 981.1 | 1 288.9 | 11.4 | 10 609.5 | 9 612.3 | (997.2) | (9.4) |
| Gross requirements | 68 743.8 | 67 872.2 | 871.6 | 1.3 | 69 576.4 | 61 615.1 | (7 961.3) | (11.4) |
| Staff assessment income | 1 638.2 | 1 977.1 | (338.9) | (20.7) | 1 734.6 | 1 582.9 | (151.7) | (8.7) |
| Net requirements | 67 105.6 | 65 895.1 | 1 210.5 | 1.8 | 67 841.8 | 60 032.2 | (7 809.6) | (11.5) |
| Voluntary contributions in kind (budgeted) | – | – | – | – | – | – | – | – |
| Total requirements | 68 743.8 | 67 872.2 | 871.6 | 1.3 | 69 576.4 | 61 615.1 | (7 961.3) | (11.4) |

B.	Non-budgeted contributions

28.	The value of non-budgeted contributions for the period from 1 July 2024 to 30 June 2025 and from 1 July 2026 to 30 June 2027 is as follows:

(Thousands of United States dollars)

| Category | Actual value (2024/25) | Estimated value (2026/27) |
| --- | --- | --- |
| Status-of-forces agreementa | 1 035.0 | 1 035.0 |
| Voluntary contributions in kind (non-budgeted) | – | – |
| Total | 1 035.0 | 1 035.0 |

a	Represents land provided by the host country.

C.	Efficiency gains

29.	The cost estimates for the period from 1 July 2026 to 30 June 2027 take into account the following efficiency initiatives:

(Thousands of United States dollars)

|  |  | Estimated efficiency gains (2024/25) | Realized efficiency gains (2024/25) | Variance (2024/25) | Investment since inception to generate the efficiency gains of 2026/27 | Cumulated efficiency gains since inception and before 2026/27 | Estimated efficiency gains (2026/27) | Cumulated investment and efficiency gains as of 2026/27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Budget class | Description of the initiative | (1) | (2) | (3)=(2)-(1) | (4) | (5) | (6) | (7)=(4)+(5)+(6) |
| Military and police personnel | Improved mission-specific contractual arrangements and operational planning for rotations | – | – | – | – | – | 650.0 | 650.0 |
|  | Improved planning for volume of and meal type for rations | – | – | – | – | – | 480.9 | 480.9 |
|  | Efficiency measures through organizational optimization, functional streamlining and allocative efficiencies | – | – | – | – | – | 4 000.0 | 4 000.0 |
| Civilian personnel | Efficiency measures: abolishment of 6 posts | – | – | – | – | – | 836.7 | 836.7 |
|  | Replacement of overtime for driving services that will instead be provided by individual contractual personnel on an as-needed basis at a lower cost | – | – | – | – | – | 34.2 | 34.2 |
| Facilities and infrastructure | Increased electricity supply provided by solar panels and replacement of existing interior and exterior lighting with light emitting diode bulbs | 263.4 | 273.3 | 9.9 | (1 323.2) | 327.6 | 242.4 | (753.2) |
|  | Efficiency measures: reduced volume of fuel | – | – | – | – | – | 137.4 | 137.4 |
| Ground transportation | Forklifts and utility vehicles from MINUSMA (cost avoidance) | – | 194.4 | 194.4 | – | 900.2 | 149.6 | 1 049.8 |
|  | Efficiency measures: reduced volume of fuel | – | – | – | – | – | 47.4 | 47.4 |
| Total |  | 263.4 | 467.7 | 204.3 | (1 323.2) | 1 227.8 | 6 578.6 | 6 483.2 |
| Approved budget for 2025/26 |  |  |  |  |  |  | 69 576.4 |  |
| 2026/27 estimated efficiencies as a percentage of the approved budget for 2025/26 |  |  |  |  |  |  | 9.5 |  |

Abbreviation: MINUSMA, United Nations Multidimensional Integrated Stabilization Mission in Mali.

D.	Unencumbered balance

30.	The unencumbered balance for the periods from 2022/23 to 2024/25 as reported in the relevant performance reports, is as follows:

Trend of the unencumbered balance

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 706.3 | 1 378.0 | 558.7 |
| Civilian personnel | (226.7) | 1 265.5 | (976.0) |
| Operational costs | 111.2 | (239.8) | 1 288.9 |
| Total | 590.8 | 2 403.7 | 871.6 |

E.	Cancellation of prior-period obligations

31.	Prior-period obligations for the periods from 2022/23 to 2024/25 were cancelled as follows:

Trend of the cancellation of prior-period obligations

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 916.2 | 641.5 | 87.7 |
| Civilian personnel | 6.8 | 1.2 | 1.8 |
| Operational costs | 92.1 | 288.3 | 17.0 |
| Total | 1 015.1 | 931.0 | 106.5 |

Note: The amounts represent the total obligations that were cancelled at the end of the 12-month period following the end of the budget period in respect of goods supplied and services rendered in the budget period, and at the end of an additional period of four years in respect of obligations to troop- and police-contributing countries.

F.	Other revenue and adjustments, and borrowing

1.	Other revenue and adjustments

(Thousands of United States dollars)

| Category | Amount |
| --- | --- |
| Investment revenue | 1 497.0 |
| Other/miscellaneous revenue | 55.1 |
| Voluntary contributions in cash | – |
| Prior-period adjustments | – |
| Cancellation of prior-period obligations | 106.5 |
| Total | 1 658.6 |

32.	Credits comprising the unencumbered balances, other revenue and the cancellation of prior-period obligations reduce the assessed contributions owed by Member States in the following financial year. The credit for the 2024/25 period for the overall peacekeeping operations amounts to $335.5 million, including the support entities and the United Nations Multidimensional Integrated Stabilization Mission in Mali. In the current financial situation, offsetting this large amount of credit against a future assessment for the 2026/27 period will reduce the collection and undermine the ability of peacekeeping operations to fully implement their mandates. Accordingly, the Secretary-General proposes that the General Assembly approve that the credits in respect of the financial period 2024/25 be placed in a reserve that would be used in the event that collections are insufficient to enable the implementation of those mandates and allow Member States to apply their share towards current or future dues once the Assembly determines that the liquidity situation has sufficiently improved. This proposal is explained in more detail in the peacekeeping overview report.

2.	Borrowing

33.	Owing to cash liquidity situations in other active peacekeeping missions, UNDOF issued loans to missions, with the month-end loan balance as follows:

(Millions of United States dollars)

| As at | Borrowing mission | Amount |
| --- | --- | --- |
| 31 July 2024 | MINURSO (3.4), UNMIK (3.8), UNSOS (6.8) | (14.0) |
| 31 August 2024 | MINURSO (3.4), UNMIK (3.8), UNSOS (6.8) | (14.0) |
| 31 May 2025 | MINURSO (4.5), UNMIK (4.0) | (8.5) |
| 30 June 2025 | MINURSO (6.5), UNMIK (5.4) | (11.9) |

Abbreviations: MINURSO, United Nations Mission for the Referendum in Western Sahara; UNMIK, United Nations Interim Administration Mission in Kosovo.

G.	Vacancy factors

34.	The cost estimates for the period from 1 July 2026 to 30 June 2027 take into account the vacancy factors outlined in the table below. The table also summarizes, by category, the actual rates in the periods from 2022/23 to 2024/25, as well as the approved and current rates for the 2025/26 period:

(Percentage)

|  | Actual |  |  | 2025/26 approved | Actual as at 31 December 2025 | Actual average, January to December 2025 | 2026/27 proposed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Category | 2022/23 | 2023/24 | 2024/25 |  |  |  |  |
| Military and police personnel |  |  |  |  |  |  |  |
| Military contingents | 9.8 | 7.7 | 6.0 | 6.2 | 24.2 | 9.0 | 19.0 |
| Civilian personnel |  |  |  |  |  |  |  |
| International staff | 9.4 | 9.4 | 13.5 | 9.4 | 15.7 | 17.3 | 14.0 |
| National staff |  |  |  |  |  |  |  |
| National Professional Officer | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 | 0.0 |
| National General Service staff | 4.5 | 9.0 | 7.8 | 7.8 | 11.1 | 8.9 | 7.0 |
| Temporary positionsa |  |  |  |  |  |  |  |
| International staff | 50.0 | 50.0 | 0.0 | 0.0 | 100.0 | 50.0 | – |

a	Funded under general temporary assistance.

35.	The vacancy factors take into account the high number of abolishments included in the proposed budget for 2026/27. Accordingly, the proposed vacancy rates for civilian personnel categories with abolishments were estimated using the total number of vacant posts and positions as at 31 December 2025, net of the number of posts and positions proposed for abolishment. For categories without proposed abolishments, the standard policy guidance was applied, using either the 12-month average vacancy rate from January to December 2025 or the actual vacancy rate as at 31 December 2025. For military and police personnel, the vacancy factors reflect their planned deployment during the period. This approach ensures that vacancy rates are based on, to the extent possible, the actual data while maintaining consistency across the proposed budgets.

H.	Quick-impact projects

36.	The estimated resource requirements for quick-impact projects for the period from 1 July 2026 to 30 June 2027, compared with previous periods, are as follows:

(Thousands of United States dollars)

| Period | Amount | Number of projects |
| --- | --- | --- |
| 1 July 2024 to 30 June 2025 (actual) | 294.2 | 6 |
| 1 July 2025 to 30 June 2026 (approved) | 300.0 | 6 |
| 1 July 2026 to 30 June 2027 (proposed) | 300.0 | 6 |

37.	UNDOF will implement the quick-impact projects as a confidence-building measure in support of mandate implementation and will enhance their impact on the community, in line with the General Assembly resolution 76/274. As part of building trust between UNDOF and local communities, the Force is proposing projects that are focused mainly on the education sector in the most deprived rural areas and on supporting hospitals.

III.	Analysis of variances

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Military contingents | $558.7 | 1.3% | ($6 442.2) |  | (14.9%) |

38.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) less actual contingent-owned major equipment compared with the amount of equipment included in the approved budget; (b) the lower cost for the mission subsistence allowance due to the lower actual number of military staff officers compared with the number in the approved budget; and (c) the lower cost for rations due to the non-presence of government-provided liaison personnel.

39.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) the application of a higher vacancy rate of 19 per cent in the computation of the standard reimbursement and allowances, rations and contingent-owned equipment for military contingent personnel, and the mission subsistence allowance for military staff officers due to efficiency measures through organizational optimization, functional streamlining and allocative efficiencies, compared with 6.2 per cent applied in the approved budget; and (b) lower costs anticipated for travel on rotation (commercial) based on actual expenditure patterns compared with the estimated costs included in the approved budget for 2025/26.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| International staff | ($570.8) | (5.1%) | $156.1 |  | 1.4% |

40.	For the 2024/25 period, the increased requirements were attributable primarily to the termination indemnities paid to the three UNDOF staff members who were declared persona non grata by the host Government, offset in part by the higher actual average vacancy rate of 13.5 per cent compared with the rate of 9.4 per cent applied in the approved budget.

41.	For the 2026/27 period, the increased requirements are attributable primarily to the application of the higher common staff cost rate compared with the rate applied in the approved budget for 2025/26, offset in part by the application of the higher vacancy rate of 14 per cent, compared with 9.4 per cent applied in the approved budget, and the proposed abolishment of one post, due to efficiency measures.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| National General Service staff | ($230.2) | (5.7%) | ($181.6) |  | (4.5%) |

42.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) the actual incumbency at the higher average level/step of the salary scale versus the average level/step applied in the approved budget; and (b) the unbudgeted danger pay issued to a staff member from the Alpha side due to the security situation in the Force’s area of operations.

43.	For the 2026/27 period, the reduced requirements are attributable to (a) the non-requirement for overtime for driving services formerly provided by national General Service staff that will instead be provided by individual contractual personnel on an as-needed basis owing to logistical requirements and at a lower cost; and (b) the proposed abolishment of four posts due to efficiency measures.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| General temporary assistance | ($168.1) | (66.8%) | ($497.1) |  | (100.0%) |

44.	For the 2024/25 period, the increased requirements were attributable primarily to the full actual incumbency compared with the rate of 50.0 per cent applied in the approved budget.

45.	For the 2026/27 period, the reduced requirements are attributable to the proposed abolishment of two international temporary positions due to efficiency measures.

|  | 2024/25 variance |  |  |
| --- | --- | --- | --- |
| Consultants and consulting services | ($20.8) | (742.9%) |  |

46.	For the 2024/25 period, increased requirements were attributable primarily to the consultancy fee and other costs related to a non-United Nations staff member serving on the Board of Inquiry team.

|  | 2024/25 variance |  |  |
| --- | --- | --- | --- |
| Official travel | ($24.2) | (12.9%) |  |

47.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) the establishment of a new route, which was necessitated by the regional security situation, to supply petrol, oil and lubricants; (b) visit of the mission capability study team from Headquarters; and (c) travel expenses of United Nations staff members’ service on the Board of Inquiry.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Facilities and infrastructure | $859.8 | 14.1% | ($439.9) |  | (7.6%) |

48.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) the reprioritization of resources through the deferral of acquisitions of remote surveillance equipment, a diesel hybrid photovoltaic system and fuel tank maintenance due to liquidity challenges; and (b) the lower-than-budgeted consumption of 1.6 million litres of fuel for generators acquired at a lower actual average price of $0.9 per litre compared with the volume of 1.7 million litres at an average price of $1.06 per litre, offset in part primarily by: (a) the acquisition of security and accommodation equipment for essential improvements in the UNDOF area; (b) the acquisition for replacement of two containerized wastewater treatment plants that were beyond repair; and (c) the outsourcing of a building cleaning and maintenance service contract, which reduced the requirements for individual contractual services under the other supplies, services and equipment budget class.

49.	For the 2026/27 period, the reduced requirements are attributable primarily to the lower estimated average price of fuel for generators of $0.747 per litre for 1.4 million litres compared with $0.981 per litre for 1.6 million litres included in the approved budget.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Ground transportation | $265.1 | 16.9% | ($178.7) |  | (15.7%) |

50.	For the 2024/25 period, the reduced requirements were attributable primarily to the lower-than-budgeted actual consumption of 0.6 million litres of fuel for ground transport acquired at a lower actual average price of $0.9 per litre compared with the budgeted volume of 0.7 million litres at an average price of $1.06 per litre.

51.	For the 2026/27 period, the reduced requirements are attributable primarily to the lower estimated average price of fuel for vehicles of $0.747 per litre compared with an average price of $0.981 included in the approved budget.

|  | 2024/25 variance |  |  |
| --- | --- | --- | --- |
| Marine operations | ($22.3) | (89.2%) |  |

52.	For the 2024/25 period, the increased requirements were attributable primarily to the acquisition of four additional sea containers for the freight of engineering equipment, vehicles, spare parts and other related equipment from the United Nations Multidimensional Integrated Stabilization Mission in Mali.

|  |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- |
| Communications and information technology |  | ($419.4) |  | (23.8%) |

53.	For the 2026/27 period, the reduced requirements are attributable to: (a) the acquisition of less equipment as part of the regular asset replacement cycle, due to the extension of the duration of the useful life of such equipment, compared with the amount of equipment included in the approved budget for 2025/26; and (b) lower rates for centralized services provided by the Office of Information and Communications Technology compared with the rates applied in the approved budget.

IV.	Actions to be taken by the General Assembly

54.	The actions to be taken by the General Assembly in connection with the financing of the United Nations Disengagement Observer Force are:

(a)	To take note of the unencumbered balance of $871,600 with respect to the period from 1 July 2024 to 30 June 2025;

(b)	To take note of other revenue for the period ended 30 June 2025 amounting to $1,658,600 from investment revenue ($1,497,000), other/miscellaneous revenue ($55,100) and the cancellation of prior-period obligations ($106,500);

(c)	To approve the apportionment of the amount of $2,530,200 among Member States in accordance with the applicable scale of assessment for 2025 and to place such apportioned amount in a reserve that would be used in the event that collections are insufficient, to enable the full, efficient and effective implementation of mandates;

(d)	To allow Member States to apply their share of the amount apportioned in subparagraph (c) above towards current or future dues once the General Assembly determines that the liquidity situation has improved sufficiently to allow such application;

(e)	To appropriate the amount $61,615,100, for the maintenance of the Force for the 12-month period from 1 July 2026 to 30 June 2027;

(f)	To assess the amount in subparagraph (e) above at a monthly rate of $5,134,600 should the Security Council decide to continue the mandate of the Force.

V.	Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/307, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly

A.	General Assembly

Cross-cutting issues

(Resolution 76/274)

| Decision/request | Action taken to implement decision/request |
| --- | --- |
| Requests the Secretary-General to improve comprehensive oversight of the activities of peacekeeping missions and implement the recommendations of relevant oversight bodies in this regard to avoid deficiencies in management and related economic losses, with the aim of ensuring full compliance with the Financial Regulations and Rules of the United Nations (para. 17). | As at 31 December 2025, 1 of the 3 recommendations (33.3 per cent) issued by the Office of Internal Oversight Services and 11 of the 13 recommendations (84.6 per cent) issued by the Board of Auditors were implemented. Regular follow-up is undertaken to ensure the timely closure of the remaining recommendations. |
| Requests that future budget proposals demonstrate the scalability of mission support components, including their staffing and operational costs, be proportionate in relation to the changing level of other mission components and include standard indicators (para. 27). | The mission support ratio (total number of mission support and security personnel per 1,000 total mission personnel) in the 2025/26 period is 98.3, lower than 100 in the 2020/21 period. |
| Requests the Secretary-General to consider options for greater nationalization of functions when formulating budget submissions, commensurate with mission mandates and requirements where applicable (para. 34). | UNDOF will continue to review its staffing requirements in line with its priorities and the nationalization of functions. |
| Recalls the provisions of section XVIII of its resolution 61/276, recognizes the important role played by quick-impact projects in establishing and building confidence in missions, further recognizes the importance of conducting assessments of the quick-impact projects regularly, on their needs and impact as required in resolution 61/276, requests the Secretary-General to include the conducted assessments in his next reports, and also requests the Secretary-General to enhance their impact (para. 82). | UNDOF conducts regular internal assessments through reviews and direct meetings with Syrian caretaker authorities and beneficiaries from the local communities. The most recent assessment of the Force’s quick-impact projects covered the projects implemented between 2023 and 2024. Owing to the liquidity challenges and consequential recruitment freeze that resulted in reduced capacity, no assessment would be conducted for the 2024/25 or 2025/26 periods. Furthermore, all quick-impact projects were postponed for the 2025/26 period. |

B.	Advisory Committee on Administrative and Budgetary Questions

Financing of the United Nations peacekeeping forces in the Middle East: Financing of the United Nations Disengagement Observer Force

(A/79/724/Add.1 and General Assembly resolution 79/307)

| Request/recommendation | Action taken to implement request/recommendation |
| --- | --- |
| The Advisory Committee trusts that UNDOF will continue to engage the Force’s troops in the implementation of quick-impact projects, and ensure that projects benefit the local population, as intended, and that updated information, including on planning, implementation and assessment, will be provided in the context of the next proposed budget report (para. 28). | A total of six quick-impact projects were implemented during the 2024/25 period, all benefiting the local population directly and carried out with the engagement of the Force’s troops. However, owing to staffing shortages resulting from the recruitment freeze imposed in response to liquidity challenges, comprehensive end-of-period assessments could not be conducted. |

Annex

Organization chart

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; NGS, National General Service; NPO, National Professional Officer.

Map

__________________

__________________

Note: The following abbreviations are used in the tables: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer; UNV, United Nations Volunteers; USG, Under-Secretary-General.

The actual number of posts and positions is based on the rounded average.

The results-based budgeting outputs are available for consultation on the Umoja Analytics platform as part of efforts to streamline the volume of information presented in the new combined budget and performance report.

Resource variance amounts are expressed in thousands of United States dollars. Analysis is provided for variances of at least plus or minus 5 per cent or $100,000.