Eightieth session

Agenda item 150

Financing of the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic

Budget performance for the period from 1 July 2024 to 30 June 2025 and budget for the period from 1 July 2026 to 30 June 2027 for the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic

Report of the Secretary-General

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Mandate, results achieved and planned outcome |  |  | 7 |
| - Mandate |  |  | 7 |
| - Budget implementation for 2024/25 |  |  | 7 |
| - Planning assumptions and mission support initiatives for 2026/27 |  |  | 10 |
| - Regional mission cooperation |  |  | 14 |
| - Human resources |  |  | 15 |
| - Proposed staffing changes |  |  | 19 |
| - Results-based budgeting frameworks |  |  | 29 |
| - Financial resources |  |  | 40 |
| - Overall |  |  | 40 |
| - Non-budgeted contributions |  |  | 41 |
| - Efficiency gains |  |  | 41 |
| - Unencumbered balance |  |  | 45 |
| - Cancellation of prior-period obligations |  |  | 45 |
| - Other revenue and adjustments, and borrowing |  |  | 45 |
| - Vacancy factors |  |  | 46 |
| - Analysis of requirements for air operations |  |  | 47 |
| - Programmatic activities |  |  | 48 |
| - Quick-impact projects |  |  | 48 |
| - Analysis of variances |  |  | 49 |
| - Actions to be taken by the General Assembly |  |  | 56 |
| - Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/302, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly |  |  | 57 |
| - General Assembly |  |  | 57 |
| - Advisory Committee on Administrative and Budgetary Questions |  |  | 58 |
| Annex |  |  |  |
| Organization charts |  |  | 63 |
| Map |  |  | 65 |

Summary

The present report contains the budget performance and the budget for the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic (MINUSCA) for the periods from 1 July 2024 to 30 June 2025 and from 1 July 2026 to 30 June 2027, respectively.

During the 2024/25 period, MINUSCA advanced the implementation of its political strategy in close coordination with the Government of the Central African Republic. The Mission supported preparations for the electoral process and facilitated the implementation of an agreement signed on 19 April 2025 with two major armed groups, enabling progress in disarmament and demobilization and contributing to the revitalization of the Political Agreement for Peace and Reconciliation in the Central African Republic. In parallel, joint operations with national defence and security forces helped to reduce the presence of armed groups, reinforce border security and enhance the protection of civilians. Further progress was recorded in the development of early warning mechanisms and in the monitoring and reporting of human rights violations and abuses.

State authority and governance were reinforced through a decentralization approach, including the deployment of local officials, infrastructure rehabilitation, and capacity-building in the police, justice and penitentiary sectors, supported by partnerships with national and regional actors. Operational capacity was strengthened through enhanced airlift and mobility, an expanded field presence and increased local procurement. Environmental sustainability advanced through the installation of solar systems, generator upgrades and waste management initiatives. Despite persistent financial and political constraints, the Mission maintained progress towards improved security, governance and conditions conducive to credible and inclusive elections.

Looking ahead to the 2026/27 period, MINUSCA will focus on consolidating the considerable, though still fragile, gains and safeguarding these achievements to ensure sustainability, prevent a relapse into conflict and leave a positive legacy. The Mission will continue to implement its political strategy and integrated mission plan, with sustained efforts to advance the Political Agreement through political dialogue; reconciliation; disarmament, demobilization and reintegration; community violence reduction; and security sector reform, while continuing to protect civilians.

MINUSCA operations will remain shaped by regional dynamics, armed group activity, post-election tensions and economic challenges, requiring integrated political, security and programmatic responses. The Mission will maintain operational readiness and further strengthen State authority and local governance through decentralization, enhanced rule of law and human rights protection, while reinforcing coordination with national and international partners. MINUSCA will also continue to identify and implement efficiency measures, organizational optimization and functional streamlining, including through reconfiguration and consolidation.

Financial resources

MINUSCA incurred $1,146.3 million in expenditure for the budget performance period, representing a resource utilization rate of 97.8 per cent, compared with $1,143.0 million in expenditure and a resource utilization rate of 99.8 per cent in the 2023/24 period.

The unencumbered balance of $25.4 million reflects the net impact of the following: (a) reduced requirements for military and police personnel, attributable primarily to the repatriation and delayed rotation of units, the non-deployment or partial non-functionality of major equipment and lower ration costs; (b) increased requirements for civilian personnel, attributable primarily to lower actual average vacancy rates for international and national staff, higher actual common staff costs, and the revised higher national staff salary scale; and (c) reduced requirements for operational costs, primarily under air operations, attributable to the delayed or partial deployment of helicopters, lower utilization of air ambulance services, the unavailability of one fixed-wing aircraft and lower volumes and prices of aviation fuel.

The budget proposed for the 2026/27 period, in the amount of $1,021.6 million, reflects a decrease of $152.5 million, or 13.0 per cent, compared with the apportionment of $1,174.1 million approved for the 2025/26 period.

The estimates for the 2026/27 period are aligned with the Mission’s strategic priorities and operational needs and reflect a balance of efficiency-driven reductions and operationally necessary increases, as follows: (a) under military and police personnel, reductions result primarily from the application of higher vacancy rates; and (b) under civilian personnel, decreases stem from the proposed abolishment of 151 posts and positions, including election-related temporary positions following the scheduled completion of the Mission’s electoral mandate by 30 June 2026, alongside higher vacancy rates across most staff categories. Through the streamlining of functions and the optimization of resource allocation, the Mission will refine its footprint, strengthen the prioritization of critical mandated activities and ensure the continued effectiveness of Mission operations.

(Thousands of United States dollars; budget year is from 1 July to 30 June) Category; 2024/25 apportionment; 2024/25 expenditure; Variance; 2025/26 apportionment; 2026/27 cost estimates; Variance. Unencumbered balance; Percentage; Amount; Percentage. Military and police personnel; 642 877.4; 628 416.9; 14 460.5; 2.2; 635 236.3; 500 029.3; (135 207.0); (21.3). Civilian personnel; 235 925.4; 250 145.3; (14 219.9); (6.0); 256 506.0; 238 899.4; (17 606.6); (6.9). Operational costs; 292 816.9; 267 706.9; 25 110.0; 8.6; 282 389.7; 282 706.7; 317.0; 0.1. Gross requirements; 1 171 619.7; 1 146 269.1; 25 350.6; 2.2; 1 174 132 .0; 1 021 635.4; (152 496.6); (13.0). Staff assessment income; 18 237.5; 20 184.6; (1 947.1); (10.7); 21 144.2; 20 405.4; (738.8); (3.5). Net requirements; 1 153 382.2; 1 126 084.5; 27 297.7; 2.4; 1 152 987.8; 1 001 230.0; (151 757.8); (13.2). Voluntary contributions in kind (budgeted); –; –; –; –; –; –; –; –. Total requirements; 1 171 619.7; 1 146 269.1; 25 350.6; 2.2; 1 174 132 .0; 1 021 635.4; (152 496.6); (13.0).

Human resourcesa

The proposed budget provides for the deployment of uniformed personnel and civilian staff as follows:

Military observers; Military contingents; United Nations police; Formed police units; Inter-national staff; National Professional Officers; National General Service; Temporary positionsb; United Nations Volunteersc; Government-provided personnel; Total. Executive direction and management. Approved 2024/25; –; –; –; –; 128; 35; 57; 1; 51; –; 272. Actual 2024/25; –; –; –; –; 113; 33; 52; 1; 51; –; 250. Approved 2025/26; –; –; –; –; 127; 36; 56; 1; 51; –; 271. Proposed 2026/27; –; –; –; –; 112; 37; 57; 1; 46; –; 253. Components. Support for political, peace and reconciliation processes. Approved 2024/25; –; –; –; –; 56; 5; 5; 30; 61; –; 157. Actual 2024/25; –; –; –; –; 50; 5; 5; 23; 56; –; 139. Approved 2025/26; –; –; –; –; 56; 5; 5; 30; 61; –; 157. Proposed 2026/27; –; –; –; –; 45; 5; 5; –; 24; –; 79. Security, protection of civilians and human rights. Approved 2024/25; 155; 14 201; 600; 2 420; 56; 19; 11; –; 27; –; 17 489. Actual 2024/25; 152; 13 860; 591; 2 417; 52; 18; 11; –; 25; –; 17 126. Approved 2025/26; 155; 14 201; 600; 2 420; 56; 19; 11; –; 27; –; 17 489. Proposed 2026/27; 155; 13 847; 589; 2 410; 52; 19; 11; –; 25; –; 17 108. Fight against impunity and support for the extension of State authority and rule of law. Approved 2024/25; –; –; –; –; 49; 24; 86; –; 13; 108; 280. Actual 2024/25; –; –; –; –; 42; 23; 83; –; 13; 107; 268. Approved 2025/26; –; –; –; –; 49; 24; 86; –; 13; 108; 280. Proposed 2026/27; –; –; –; –; 40; 24; 86; –; 13; 108; 271. Support. Approved 2024/25; –; 44; –; –; 456; 32; 352; 10; 151; –; 1 045. Actual 2024/25; –; 44; –; –; 423; 30; 323; 9; 138; –; 967. Approved 2025/26; –; 44; –; –; 456; 32; 352; 10; 151; –; 1 045. Proposed 2026/27; –; 44; –; –; 421; 32; 351; 10; 148; –; 1 006. Total. Approved 2024/25; 155; 14 245; 600; 2 420; 745; 115; 511; 41; 303; 108; 19 243. Actual 2024/25; 152; 13 904; 591; 2 417; 680; 109; 474; 33; 283; 107; 18 750. Approved 2025/26; 155; 14 245; 600; 2 420; 744; 116; 510; 41; 303; 108; 19 242. Proposed 2026/27; 155; 13 891; 589; 2 410; 670; 117; 510; 11; 256; 108; 18 717. Net change; –; (354); (11); (10); (74); 1; –; (30); (47); –; (525).

a Represents the highest level of authorized/proposed strength. b Funded under general temporary assistance. c Includes international and national United Nations Volunteers.

Legislative history (Thousands of United States dollars) 2024/25; 2025/26. Report; Date; Amount; Report; Date; Amount. Proposed budget – Secretary-General; A/78/760; 7 February 2024; 1 197 538.3; A/79/765 and A/79/765/Corr.1; 6 February 2025 and 23 April 2025; 1 192 195.0. Recommendation – Advisory Committee on Administrative and Budgetary Questions; A/78/744/Add.10; 5 April 2024; 1 196 319.7; A/79/724/Add.13; 16 April 2025; 1 186 632.0. Appropriationa – General Assembly; A/RES/78/298; 28 June 2024; 1 171 619.7; A/RES/79/302; 30 June 2025; 1 174 132.0. Appropriation (net); 1 153 382.2; 1 152 987.8.

a The total amount has been assessed on Member States.

The actions to be taken by the General Assembly are set out in section IV of the present report.

I.	Mandate, results achieved and planned outcome

A.	Mandate

1.	The mandate of the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic (MINUSCA) was established by the Security Council in its resolution 2149 (2014). The mandate for the performance period was provided in its resolutions 2709 (2023) and 2759 (2024). The most recent extension of the mandate was authorized by the Council in its resolution 2800 (2025), by which the Council extended the mandate until 15 November 2026.

2.	In its resolution 2800 (2025), the Security Council reduced the authorized strength of the uniformed component of the Mission by deciding that MINUSCA shall comprise up to 14,046 military personnel, including 580 military observers and military staff officers, and 2,999 police personnel, including 589 individual police officers and 2,410 formed police unit personnel, as well as 108 corrections officers, recalled its intention to keep that number under continuous review, taking into account progress on the security situation and the objective of transition and eventual drawdown of MINUSCA when conditions were met, and further expressed its firm intention to review the number of personnel following the successful completion of the electoral process scheduled in 2025 and 2026.

3.	The Mission is mandated to help the Security Council achieve the overall objective of advancing peace and security in the Central African Republic.

B.	Budget implementation for 2024/25

4.	During the reporting period, MINUSCA advanced the implementation of its mission plan through strengthened coordination with the Government of the Central African Republic, fostering inclusive dialogue, supporting stabilization efforts and assisting with electoral preparations, despite the postponement of local elections. The Mission contributed to the revision of the voter list and supported the implementation of a landmark agreement signed on 19 April 2025 between the Government and two major armed groups, Union pour la paix en Centrafrique (UPC) and Retour, réclamation et réhabilitation (3R). This agreement enabled renewed engagement with the Political Agreement for Peace and Reconciliation in the Central African Republic and facilitated the disarmament and demobilization of combatants. In volatile areas, MINUSCA joint operations with national forces curtailed armed group influence, expanded protection measures and strengthened border security. These operations, complemented by explosive ordnance risk education, human rights monitoring and support for local peace and mediation mechanisms, helped to create conditions conducive to the extension of State authority and contributed to improved security.

5.	State authority and governance were reinforced through decentralization initiatives, the deployment of local officials, capacity-building in the justice sector and infrastructure rehabilitation. Justice institutions, including the Special Criminal Court, progressively expanded their operations nationwide, although progress in transitional justice remained constrained. The Mission advanced security sector reform and the protection of civilians through a whole-of-mission approach. Operational capacity was strengthened through enhanced mobility, information and communications technology upgrades, environmental measures and targeted support for defence, security and justice institutions. Partnerships with the United Nations country team and regional organizations underpinned efforts to extend State authority and sustain peace. Persistent violations, weak institutions, limited fiscal capacity and uneven political will to pursue reforms continued to constrain progress. While the N’Djamena Agreement offered new prospects for revitalizing the peace process, the approach of national elections amid political divisions underscored the need for intensified good offices and an adjusted Mission posture to foster conditions conducive to credible, inclusive and peaceful elections.

6.	The implementation of the Mission’s mandate was constrained by financial, operational, infrastructure-related and political challenges. Liquidity constraints required cost-containment measures, including the suspension of some travel, procurement delays and strict prioritization of mandated tasks. Critical fuel shortages necessitated mobility restrictions, which adversely affected operational capacity and activities related to the protection of civilians. The liquidity constraints limited the decentralization of operations and the expansion of field presence, while prolonged liquidity pressures negatively affected staff well-being, particularly in remote field offices. Weak national infrastructure, inadequate service delivery and restricted accessibility further hindered both Mission activities and public access to essential services. Fiscal limitations and competing national priorities slowed the pace of mandate implementation and required the Mission to adapt its approach while maintaining progress toward strategic objectives. In response, MINUSCA pursued more cost-efficient means of mandate delivery while encouraging greater national ownership by the Government.

7.	MINUSCA supported conditions conducive to the holding of local elections through good offices, as well as technical, logistical, operational and security assistance, with a focus on the revision of the voter list. Despite the postponement of local elections, the Mission provided nationwide planning, technical, training, transport and security support for voter registration, including in remote areas, and conducted civic education and outreach activities. These efforts contributed to the completion of the voter list revision in August 2025 and laid the groundwork for subsequent electoral processes.

8.	The Mission enhanced mobility, flexibility and operational posture through the deployment of targeted enabling capabilities. Uniformed components benefited from air assets, the concentration of forces, the rationalization of operating bases and the construction or rehabilitation of critical infrastructure. These measures enabled proactive operations, strengthened the protection of civilians and improved humanitarian access. MINUSCA enhanced situational awareness and early warning capacity through the implementation of the peacekeeping intelligence action plan and early warning systems. Progress across the six pillars of the mission plan included rolling out integrated peacekeeping intelligence coordination mechanisms to harmonize the analysis of threats, link assessments to strategic decision-making through monthly forecasts, and conduct peacekeeping intelligence training jointly with the Peacekeeping-Intelligence Academy. A pilot project introducing artificial intelligence to analytical capabilities was also initiated, along with enhanced exchanges with neighbouring peacekeeping missions.

9.	The Mission continued to implement infrastructure projects facilitating access, including the construction and rehabilitation of roads, bridges and ferries. These initiatives, coordinated with humanitarian actors and the United Nations country team, improved mobility, access to essential services and the safe return, integration or resettlement of internally displaced persons and refugees. It also strengthened early warning and response capacities, coordination between security and humanitarian actors, and State presence in previously isolated areas, thereby enhancing the protection of civilians and community resilience.

10.	MINUSCA supported the drafting and adoption of the national defence policy and strategy and the border management policy, and the development of the 2026–2030 military programming law, strengthening long-term defence planning and nationwide force deployment. The Mission maintained its support for internal oversight and military justice, contributing to accountability and efforts to combat impunity. Parallel support for national judicial and corrections institutions enabled an increase in the number of cases brought to a conclusion, while the Special Criminal Court pursued its mandate across multiple locations.

11.	The Mission assisted national authorities in improving weapons and ammunition management through infrastructure upgrades, training and technical assistance. These activities enhanced safe storage, built national capacity, including for women personnel, and reinforced compliance through joint quality-assurance visits. MINUSCA also supported the implementation of the national action plan on small arms and light weapons, including marking, registration and the establishment of regional offices of the national commission, contributing to decentralization objectives and extending State authority in the regions.

12.	MINUSCA prioritized mobility, performance optimization and accountability, with particular emphasis on enforcing the United Nations zero-tolerance policy on sexual exploitation and abuse. Key actions included timely training for personnel, targeted support to high-risk contingents, integrated risk assessments of base camps, expanded awareness campaigns, community engagement initiatives and joint military-police deterrent patrols. Co-location of police and civilian staff with military personnel promoted integrated field presence and helped mitigate risks. Victims received comprehensive support, including counselling, mental health services and access to vocational training through established programmes.

13.	During the reporting period, the Mission further consolidated its digital management environment by aligning planning, budgeting and performance platforms within a single framework. This enabled synchronization between the mission plan results framework and budget reporting. Analytical dashboards tracked financial allocations against projects by section and location, thereby enhancing transparency and the visibility of data to senior leadership. Leveraging Comprehensive Planning and Performance Assessment System tools, the Mission produced visual products, including infographics, to clearly illustrate progress, trends and challenges.

14.	MINUSCA implemented an integrated, multi-platform communications and outreach strategy to support mandate delivery and strengthen public understanding of priorities, including the protection of civilians, peace process support, extension of State authority and humanitarian facilitation. Coordinated with the Government and national and local media, these efforts enhanced visibility, reinforced impartiality, countered misinformation and built community trust, including through targeted radio campaigns in high-risk areas.

15.	The Mission progressively adjusted its field presence to align with new administrative boundaries, enabling co-location of uniformed and civilian personnel and strengthening regional coordination. This decentralized posture was complemented by the phased reconfiguration of force and police components, taking into account evolving security conditions, national force capacities and logistical constraints. Rationalization of the footprint preserved the Mission’s ability to protect civilians, maintain operational agility and support priority mandate tasks.

16.	MINUSCA strengthened the collection, analysis and sharing of information through improved coordination between Mission headquarters and field offices, enabling timely and actionable early warning. Information management and analysis were aligned with the Mission’s four-sector force structure, allowing for a stronger sector-level focus while maintaining Mission headquarters-level coordination and leadership support. Key functional areas continued to provide intelligence-informed support to operations and protection activities, improving situational awareness and enabling proactive responses to emerging threats.

17.	MINUSCA implemented infrastructure projects to improve living and working conditions and sustain operational readiness. Construction and extension works at Bangassou Sector headquarters reached approximately 14 per cent completion before they were suspended due to liquidity constraints. Essential maintenance at airfields in Obo, Kaga Bandoro and Bossangoa preserved air mobility. The Mission supported the redeployment and operational readiness of vetted internal security forces, including transportation and the construction and rehabilitation of facilities, enabling the deployment of over 300 personnel and the construction or rehabilitation of more than 60 police and gendarmerie offices. Support was provided to the Central African Armed Forces where feasible, with funds prioritized to achieve immediate operational impact.

18.	Local procurement increased significantly to $16.5 million, engaging the services of over 100 vendors, including 20 under long-term agreements. Air operations were enhanced through the deployment of Mi-8 and UH-60 helicopters and a C-130 aircraft, which delivered 9,462 tons of cargo across 12 sites, improving operational reach and responsiveness. Multi-vendor inland transport contracts cleared cargo backlogs and improved delivery timelines.

19.	Despite challenges from a six-month rainy season, MINUSCA enhanced mobility through infrastructure upgrades, bridge works and the maintenance of key supply routes and ferries. Decentralization was supported through the construction of facilities in Bangassou, Ndélé, Birao and Obo, and the completion of camps in Sam Ouandja and Ippy. Environmental sustainability advanced through the installation of seven solar photovoltaic systems (993 kilowatt-peak (kWp)), projected to save approximately 486,000 litres of fuel annually, the replacement of eight generators with more efficient models, and waste-management initiatives, including completion of the Bimbo waste yard phase one, ongoing maintenance of the Kolongo landfill and subsequent phases of those projects.

C.	Planning assumptions and mission support initiatives for 2026/27

20.	The successful conduct of the combined presidential, legislative, regional and municipal elections on 28 December 2025 marked a significant milestone for the Central African Republic and provides an opportunity for MINUSCA to adjust its footprint and posture in line with its mandate under Security Council resolution 2800 (2025). During the 2026/27 period, the Mission will advance internal planning and analysis processes to guide adaptation to the post-election environment, aligning its configuration with strategic priorities while identifying organizational, functional and process efficiencies to support sustainable mandate delivery. MINUSCA will focus on consolidating the considerable, though still fragile, gains and safeguarding these achievements to ensure sustainability, prevent a relapse into conflict and leave a positive legacy.

21.	The Mission will continue to implement its political strategy and integrated mission plan for 2023–2028, with a sustained focus on finalizing the implementation of the peace agreement, strengthening conflict-management mechanisms and supporting the extension of State presence and authority. Building on progress in strengthening national and local political processes, coordination frameworks and decentralized engagement, MINUSCA will prioritize coherence, field-level implementation and national ownership to support stabilization and the extension of State authority, gradually shifting from facilitation to the consolidation of political outcomes.

22.	In the light of the post-election context, and in preparation for implementation of the MINUSCA mandate during the 2026/27 period, the Mission is initiating a phase of consolidation, reconfiguration and internal strategic review, in line with paragraph 48 of Security Council resolution 2800 (2025). Following the successful conduct of national elections, and consistent with the Mission’s plans to expeditiously sunset the electoral division, the Mission has completed the withdrawal of all elections-related resources. The Mission has also begun assessing the evolving political and security environment to identify opportunities to adjust its footprint, refine its posture and seek efficiencies in the delivery of mandated activities. These efforts, however, are being undertaken against the backdrop of persistent liquidity constraints, which are delaying the initiation of planned activities and potentially constraining the Mission’s flexibility in implementing reconfiguration measures. As a result, consolidation and restructuring efforts will require strengthened prioritization and tighter controls to ensure that scarce resources are directed to the most critical mandate priorities, while positioning the Mission to sustain impact and effectiveness in the post-election environment.

23.	The Mission will continue to build on recent political and peace process gains, including renewed engagement by armed groups in the Political Agreement and strengthened regional and international cooperation. Efforts will focus on supporting inclusive dialogue, safeguarding civic and political space and upholding and promoting respect for human rights. MINUSCA will strengthen its integrated, multi-platform communications and outreach strategy to support mandate delivery, with a focus on coordinated messaging with the Government and national and local media, targeted radio campaigns in high-risk areas, and cost-effective dissemination to enhance public understanding, counter misinformation and reinforce community trust in mandate priorities.

24.	MINUSCA will continue to prioritize implementation of the Political Agreement, maintaining engagement with Union pour la paix en Centrafrique (UPC), Retour, réclamation et réhabilitation (3R) and other armed actors. The Mission will facilitate dialogue, monitor compliance and implement reconciliation initiatives to consolidate peace gains.

25.	Disarmament, demobilization and reintegration and community violence reduction programmes will be sustained and adapted to address remaining caseloads of former combatants and at-risk youth. Despite progress, incomplete reintegration and persistent socioeconomic vulnerabilities pose risks of renewed recruitment and localized violence, particularly in the post-election context. MINUSCA will work closely with newly elected authorities to ensure alignment with national priorities, including decentralization, strengthening local governance, and promoting human rights and the rule of law. The Mission will continue to empower local communities to take ownership of the peace process, enhance information-sharing and increase public awareness.

26.	Mission operations will be shaped by regional security dynamics, fluctuating armed group activity, post-election tensions and persistent logistical, economic and fiscal constraints, alongside socioeconomic vulnerabilities among at-risk populations, particularly young people. These conditions necessitate an integrated political, security and programmatic approach to preserve and consolidate stabilization gains and support reconciliation efforts. Maintaining a footprint that ensures operational readiness, sustained field presence and rapid response capacity is essential, while deployments will remain flexible and adaptive to evolving risks and constraints.

27.	Force and police components will continue implementing operations under the mission plan while optimizing the post-election footprint, accounting for evolving risks from armed group activity, residual post-election tensions, explosive ordnance threats and spoiler actions. Key uniformed capabilities, including quick reaction forces, aviation, engineering, intelligence, and agile light infantry remain essential to address operational gaps created by base closures, sustain deterrence, ensure mobility and maintain the protection of civilians and United Nations and humanitarian personnel. Quick reaction force units will establish short-term temporary operating bases and deploy within 24 to 48 hours to remote locations requiring air insertion. Aviation remains the primary mode of transportation to reach remote locations in all weather conditions. Combined aviation and quick reaction force capabilities have mitigated logistical gaps, enhanced casualty evacuation capacity and reinforced the Mission’s presence in higher-threat areas. MINUSCA will continue to support the Armed Forces of the Central African Republic and internal security forces through joint operations, mentoring, training and weapons and ammunition management, contributing to the progressive extension of State security presence and rule of law institutions, in compliance with the United Nations human rights due diligence policy. Complementary disarmament, demobilization and reintegration, community violence reduction and small arms control initiatives will continue to address the root causes of insecurity and support community stabilization.

28.	The continued presence of explosive ordnance threats remains a significant risk to civilian safety and freedom of movement, requiring sustained mitigation and prevention efforts. The Mission will support national forces and assist in operationalizing the national mine action authority to strengthen institutional frameworks and operational capacity for explosive ordnance management, complemented by ongoing risk education for affected communities. Systematic monitoring and reporting of human rights violations will remain central to the Mission’s protection-of-civilians approach, informing operational decision-making and guiding engagement and capacity-building with national authorities.

29.	The Mission will continue to prioritize high-risk areas and border regions through targeted deployments, security patrols, and operational support to the Armed Forces of the Central African Republic and internal security forces to safeguard civilians and personnel. Continuous threat assessments and reconnaissance tools will guide evidence-based operational adjustments and security planning. Cross-cutting operational assumptions, including logistical and security constraints such as fuel shortages, mobility limitations and liquidity pressures, will influence deployment flexibility. Conduct- and discipline-related risks, including sexual exploitation and abuse, misconduct and reputational challenges, will remain actively managed to preserve operational effectiveness and maintain trust with local communities and partners.

30.	MINUSCA will continue to work closely with the United Nations country team and international financial institutions to support decentralization and local governance initiatives through sustained guidance and capacity-building for local authorities, particularly in the context of electoral transitions. This support strengthens State presence and institutional capacity, mitigates risks of uneven decentralization and promotes good governance, democratic processes, human rights and effective service delivery, ensuring that post-election transitions translate into tangible stabilization and development outcomes.

31.	The consolidation of the rule of law and State authority will require integrated political, security and programmatic interventions, particularly in the context of reduced international support, economic pressures and persistent local vulnerabilities. Targeted support for the judiciary, including the Special Criminal Court and penitentiary institutions, will promote transparency, efficiency and accountability, while community engagement initiatives will strengthen trust between citizens and local authorities. Complementing these efforts, the Mission will maintain support for critical infrastructure, including administrative buildings, to facilitate personnel deployment, service delivery and the extension of State presence in underserved areas. Coordination with the United Nations country team, strategic partners and donors will remain essential to ensure coherent, mutually reinforcing interventions aligned with national priorities.

Mission support initiatives

32.	MINUSCA will continue to decentralize its operations and execute targeted construction projects aimed at improving the safety and living and working conditions of Mission personnel in the field. These efforts will be carefully managed in the context of ongoing liquidity constraints, with a focus on maximizing operational impact.

33.	The Mission will implement the priority infrastructure projects, including: (a) the installation of a hybrid solar photovoltaic system at Kaga Bandoro to increase the renewable energy share and reduce fuel utilization; (b) the continuation of bridge abutment construction; (c) the design and construction of a stormwater canal network; (d) the construction of concrete helipads in Zemio, Mboki and Bocaranga, which are essential for protection-of-civilian operations and casualty evacuation in volatile regions; and (e) the second phase of borehole drilling works.

34.	MINUSCA will continue to reduce its environmental footprint and align its operations with a long-term vision for a positive environmental legacy. The Mission will strengthen solid waste and wastewater management through ongoing monitoring and infrastructure development, including by acquiring solid waste equipment such as incinerators and glass crushers, installing wastewater treatment plants and upgrading existing facilities. In addition, Unite field remote infrastructure monitoring systems will continue to be deployed, enabling real-time data collection and proactive maintenance to support data-driven improvements in environmental performance.

35.	To enhance logistical efficiency and ensure reliable operational support, MINUSCA will maintain decentralized warehousing in high-demand regions, digitize supply chain processes with improved forecasting and risk monitoring and optimize the use of the C-130 Hercules aircraft for air cargo. Inventory and warehouse management will be strengthened through targeted training, emphasizing national capacity development. Enhanced monitoring systems will ensure that logistics operations remain agile, resilient and responsive to rapid decision-making.

36.	MINUSCA will continue to leverage technology and advance the digitalization of its operations through the systematic use of integrated platforms such as the Comprehensive Planning and Performance Assessment System, Unite Aware, Situational Awareness Geospatial Enterprise (SAGE) and Umoja to support planning, monitoring, reporting and analysis. These tools have streamlined and standardized internal processes, reduced reliance on paper and other consumables and improved the availability of information for management and decision-making. At the same time, the Mission has expanded virtual and hybrid meetings, minimizing travel and in-person engagements while maintaining effective coordination across components and with partners.

37.	In line with the Secretary-General’s UN80 Initiative, the proposed 2026/27 budget reflects a set of efficiency measures designed to enhance effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures are informed by a review of operational requirements and workload distribution, and are implemented primarily through adjustments to force posture and a reduction in personnel, while maintaining the delivery of core mandated activities. Mitigating measures are being put in place to minimize adverse effects. Resources have been realigned to reflect evolving operational priorities, supported by optimized deployment, strengthened coordination, and adjustments to the sequencing and modalities of activities, enabling the Mission to sustain essential outcomes with a reduced footprint.

38.	Civilian staffing adjustments have been implemented through functional streamlining and organizational optimization, including the redistribution of responsibilities, the merging of functions and the refinement of internal workflows, with some functions absorbed by remaining posts. The proposed merger of the Joint Operations Centre and the Joint Mission Analysis Centre, alongside structural adjustments, will boost efficiency and performance. Needs for goods and services have been aligned with the reduced operational footprint while maintaining essential capabilities. While these measures require tighter prioritization and may reduce flexibility to respond to workload surges, the Mission has strengthened internal coordination, joint integrated planning, management oversight and prioritization mechanisms to mitigate risks and ensure effective mandate delivery.

39.	The Mission will continue to adjust its organizational structure to emphasize the centrality of security, the protection of civilians and the extension of State presence and authority across all components. Structural realignments, including the consolidation of coordination and analytical functions and the redeployment of resources under executive direction and management, aim to enhance field-level responsiveness, strengthen decentralized protection delivery and improve operational coherence under constrained resource conditions. These adjustments will support more efficient decision-making, clearer accountability and optimized use of existing capacities to deliver protection outcomes where they are most needed.

40.	In pursuit of allocative efficiencies, the Mission continues to realign resources with evolving operational and programmatic requirements, prioritizing substantive activities over administrative functions and evaluating deliverables against production costs to optimize the impact of planned outcomes. A structured resource allocation process, supported by high-level coordination meetings, ensures that resources are directed to priority activities in alignment with the mission plan and annual workplans. The Mission will continue to apply risk-based prioritization and adaptive planning and to strengthen management oversight to mitigate any potential risks. The impact of these measures will be closely monitored and adjusted as necessary to sustain effective mandate implementation.

D.	Regional mission cooperation

41.	During the 2024/25 period, MINUSCA strengthened regional cooperation by leveraging support services from various United Nations entities. The Mission engaged the services of the Entebbe Support Base of the United Nations Organization Stabilization Mission in the Democratic Republic of the Congo (MONUSCO), the Global Procurement Support Section and the Regional Service Centre in Entebbe, Uganda, to enhance operational efficiency. These entities provided critical support in areas that included onboarding and separation, payroll and benefits, vendor payments, entitlements, official travel, claims processing, cashier services, training and movement control.

42.	MINUSCA utilized the United Nations Logistics Base at Brindisi, Italy, for stock deployment services, streamlining procurement and ensuring timely delivery of mission supplies. In addition, MONUSCO provided two air assets on a cost-recovery basis to support MINUSCA flights, thereby contributing to improved staff well-being.

43.	The Mission continued to collaborate with the United Nations Regional Office for Central Africa, particularly on political engagement and regional initiatives addressing the situation in the Central African Republic. As part of this partnership, MINUSCA supported the preparation of the 58th meeting of the United Nations Standing Advisory Committee on Security Questions in Central Africa, held in Bangui in November 2024, by facilitating logistical arrangements and processing participant payments.

44.	During the 2026/27 period, MINUSCA will facilitate and support mediation and coordination initiatives in priority border areas, particularly with the Sudan, through engagement with local representatives and community leaders to foster trust and mitigate risks in the absence of formal government counterparts. The Mission will work closely with the United Nations country team and United Nations agencies in neighbouring countries to ensure a coherent, strategic approach to the Sudan context through strengthened information-sharing, joint situational analyses and coordinated planning.

45.	MINUSCA will maintain close collaboration with regional and subregional organizations to advance political dialogue, preventive diplomacy and early warning initiatives. Partnerships with regional and subregional organizations, including the African Union and the Economic Community of Central African States, will continue to reinforce joint efforts to promote peace, security and good governance in the Central African Republic and the wider subregion. These partnerships are essential to ensuring that regional dynamics are integrated into the Mission’s strategic planning and that political, security and programmatic interventions remain coherent and mutually reinforcing.

E.	Human resources

Executive direction and management

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Civilian staff | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | 3 | 7 | 46 | 45 | 27 | 128 | 35 |  | 57 | 92 | 50 |  | 1 | 51 | 271 |
| Actual posts 2024/25 | 2 | 4 | 40 | 42 | 24 | 112 | 33 |  | 52 | 85 | 50 |  | 1 | 51 | 248 |
| Approved posts 2025/26 | 3 | 7 | 46 | 44 | 27 | 127 | 36 |  | 56 | 92 | 50 |  | 1 | 51 | 270 |
| Proposed posts 2026/27 | 3 | 6 | 37 | 40 | 26 | 112 | 37 |  | 57 | 94 | 45 |  | 1 | 46 | 252 |
| Net change | – | (1) | (9) | (4) | (1) | (15) | 1 |  | 1 | 2 | (5) |  | – | (5) | (18) |
| Approved temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Actual temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Approved temporary positionsa 2025/26 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Proposed temporary positionsa 2026/27 | – | – | 1 | – | – | 1 | – |  | – | – | – |  | – | – | 1 |
| Net change | – | – | – | – | – | – | – |  | – | – | – |  | – | – | – |
| Total, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | 3 | 7 | 47 | 45 | 27 | 129 | 35 |  | 57 | 92 | 50 |  | 1 | 51 | 272 |
| Actual 2024/25 | 2 | 4 | 41 | 42 | 24 | 113 | 33 |  | 52 | 85 | 50 |  | 1 | 51 | 249 |
| Approved 2025/26 | 3 | 7 | 47 | 44 | 27 | 128 | 36 |  | 56 | 92 | 50 |  | 1 | 51 | 271 |
| Proposed 2026/27 | 3 | 6 | 38 | 40 | 26 | 113 | 37 |  | 57 | 94 | 45 |  | 1 | 46 | 253 |
| Net change | – | (1) | (9) | (4) | (1) | (15) | 1 |  | 1 | 2 | (5) |  | – | (5) | (18) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 | 46 129.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed 2026/27 | 44 034.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

a	Funded under general temporary assistance.

Component 1: support for political, peace and reconciliation processes

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Civilian staff | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | – | 4 | 20 | 27 | 5 | 56 | 5 |  | 5 | 10 | 61 |  | – | 61 | 127 |
| Actual posts 2024/25 | – | 4 | 17 | 24 | 5 | 50 | 5 |  | 5 | 10 | 56 |  | – | 56 | 116 |
| Approved posts 2025/26 | – | 4 | 20 | 27 | 5 | 56 | 5 |  | 5 | 10 | 61 |  | – | 61 | 127 |
| Proposed posts 2026/27 | – | 4 | 13 | 25 | 3 | 45 | 5 |  | 5 | 10 | 24 |  | – | 24 | 79 |
| Net change | – | – | (7) | (2) | (2) | (11) | – |  | – | – | (37) |  | – | (37) | (48) |
| Approved temporary positionsa 2024/25 | – | 1 | 5 | 22 | 1 | 29 | – |  | 1 | 1 | – |  | – | – | 30 |
| Actual temporary positionsa 2024/25 | – | 1 | 4 | 16 | 1 | 22 | – |  | 1 | 1 | – |  | – | – | 23 |
| Approved temporary positionsa 2025/26 | – | 1 | 5 | 22 | 1 | 29 | – |  | 1 | 1 | – |  | – | – | 30 |
| Proposed temporary positionsa 2026/27 | – | – | – | – | – | – | – |  | – | – | – |  | – | – | – |
| Net change | – | (1) | (5) | (22) | (1) | (29) | – |  | (1) | (1) | – |  | – | – | (30) |
| Total, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | – | 5 | 25 | 49 | 6 | 85 | 5 |  | 6 | 11 | 61 |  | – | 61 | 157 |
| Actual 2024/25 | – | 5 | 21 | 41 | 6 | 72 | 5 |  | 6 | 11 | 56 |  | – | 56 | 139 |
| Approved 2025/26 | – | 5 | 25 | 49 | 6 | 85 | 5 |  | 6 | 11 | 61 |  | – | 61 | 157 |
| Proposed 2026/27 | – | 4 | 13 | 25 | 3 | 45 | 5 |  | 5 | 10 | 24 |  | – | 24 | 79 |
| Net change | – | (1) | (12) | (24) | (3) | (40) | – |  | (1) | (1) | (37) |  | – | (37) | (78) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 | 29 215.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed 2026/27 | 16 448.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

a	Funded under general temporary assistance.

Component 2: security, protection of civilians and human rights

| Category |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. Military observers |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 155 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 152 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 155 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 155 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | – |
| II. Military contingents |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 14 201 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 13 860 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 14 201 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 13 847 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | (354) |
| III. United Nations police |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 600 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 591 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 600 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 589 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | (11) |
| IV. Formed police units |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 2 420 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 2 417 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 2 420 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 2 410 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | (10) |

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| V. Civilian staff | USG–ASG | D-2– D-1 | P-5– P-4 | P-3– P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | 1 | 4 | 22 | 25 | 4 | 56 | 19 |  | 11 | 30 | 27 |  | – | 27 | 113 |
| Actual posts 2024/25 | 1 | 4 | 20 | 23 | 4 | 52 | 18 |  | 11 | 29 | 25 |  | – | 25 | 106 |
| Approved posts 2025/26 | 1 | 4 | 22 | 25 | 4 | 56 | 19 |  | 11 | 30 | 27 |  | – | 27 | 113 |
| Proposed posts 2026/27 | 1 | 4 | 19 | 25 | 3 | 52 | 19 |  | 11 | 30 | 25 |  | – | 25 | 107 |
| Net change | – | – | (3) | – | (1) | (4) | – |  | – | – | (2) |  | – | (2) | (6) |
| Total (I–V) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17 489 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17 126 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17 489 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17 108 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (381) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 | 20 359.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed 2026/27 | 20 495.8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Component 3: fight against impunity and support for the extension of State authority and rule of law

| Category |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. Government-provided personnel |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 108 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 107 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 108 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 108 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | – |

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| II. Civilian staff | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal |  |
| Approved posts 2024/25 | – | 2 | 22 | 22 | 3 | 49 | 24 |  | 86 | 110 | 13 |  | – | 13 | 172 |
| Actual posts 2024/25 | – | 1 | 18 | 20 | 3 | 42 | 23 |  | 83 | 106 | 13 |  | – | 13 | 161 |
| Approved posts 2025/26 | – | 2 | 22 | 22 | 3 | 49 | 24 |  | 86 | 110 | 13 |  | – | 13 | 172 |
| Proposed posts 2026/27 | – | 2 | 16 | 19 | 3 | 40 | 24 |  | 86 | 110 | 13 |  | – | 13 | 163 |
| Net change | – | – | (6) | (3) | – | (9) | – |  | – | – | – |  | – | – | (9) |
| Total (I–II) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 280 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 268 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 280 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 271 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (9) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 | 20 642.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed 2026/27 | 19 099.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Component 4: support

| Category |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. Military contingents |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 44 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  | 44 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  | 44 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  | 44 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  | – |

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| II. Civilian staff | USG–ASG | D-2– D-1 | P-5– P-4 | P-3– P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | – | 4 | 41 | 57 | 354 | 456 | 32 |  | 352 | 384 | 97 |  | 54 | 151 | 991 |
| Actual posts 2024/25 | – | 4 | 39 | 46 | 333 | 422 | 30 |  | 323 | 353 | 91 |  | 47 | 138 | 913 |
| Approved posts 2025/26 | – | 4 | 41 | 57 | 354 | 456 | 32 |  | 352 | 384 | 97 |  | 54 | 151 | 991 |
| Proposed posts 2026/27 | – | 4 | 41 | 47 | 329 | 421 | 32 |  | 351 | 383 | 94 |  | 54 | 148 | 952 |
| Net change | – | – | – | (10) | (25) | (35) | – |  | (1) | (1) | (3) |  | – | (3) | (39) |
| Approved temporary positionsa 2024/25 | – | – | – | – | – | – | – |  | 10 | 10 | – |  | – | – | 10 |
| Actual temporary positionsa 2024/25 | – | – | – | – | – | – | – |  | 9 | 9 | – |  | – | – | 9 |
| Approved temporary positionsa 2025/26 | – | – | – | – | – | – | – |  | 10 | 10 | – |  | – | – | 10 |
| Proposed temporary positionsa 2026/27 | – | – | – | – | – | – | – |  | 10 | 10 | – |  | – | – | 10 |
| Net change | – | – | – | – | – | – | – |  | – | – | – |  | – | – | – |
| Subtotal, civilian staff, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | – | 4 | 41 | 57 | 354 | 456 | 32 |  | 362 | 394 | 97 |  | 54 | 151 | 1 001 |
| Actual 2024/25 | – | 4 | 39 | 46 | 333 | 422 | 30 |  | 332 | 362 | 91 |  | 47 | 138 | 922 |
| Approved 2025/26 | – | 4 | 41 | 57 | 354 | 456 | 32 |  | 362 | 394 | 97 |  | 54 | 151 | 1 001 |
| Proposed 2026/27 | – | 4 | 41 | 47 | 329 | 421 | 32 |  | 361 | 393 | 94 |  | 54 | 148 | 962 |
| Net change | – | – | – | (10) | (25) | (35) | – |  | (1) | (1) | (3) |  | – | (3) | (39) |
| Total (I–II) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 045 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 966 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 045 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 066 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (39) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 | 134 433.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed 2026/27 | 135 918.9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

a	Funded under general temporary assistance.

F.	Proposed staffing changes

Abolishment

46.	In line with ongoing efficiency efforts, which will continue to be implemented in the 2026/27 period, the proposed abolishments detailed in the table below reflect the Mission’s approach to organizational optimization and functional streamlining. Following a review of operational requirements and workload distribution, functions will be consolidated and responsibilities redistributed; these reconfigurations will support a more integrated and agile operating model aligned with evolving Mission priorities. Accordingly, it is proposed that 81 posts and positions, as detailed in the table below, be abolished.

47.	In accordance with the mandate framework governing MINUSCA electoral support, the Mission’s electoral assistance was time bound and limited to specific phases of the electoral process. As the Mission’s operational focus shifts following the successful completion of the electoral cycle and the conclusion of its electoral support mandate by 30 June 2026, the Mission’s priorities have shifted towards stabilization, the protection of civilians and governance. The functions formerly performed by the Electoral Affairs Service are no longer required beyond the current electoral support phase. No residual technical, advisory or operational responsibilities related to electoral support are foreseen within the Mission’s mandate. Accordingly, it is proposed that 67 temporary positions within the Service, and 3 posts in the Political Affairs Division, as detailed in the table below, be abolished.

Redeployment

Office of the Deputy Special Representative of the Secretary-General (Resident Coordinator/Humanitarian Coordinator)

48.	It is proposed that one position of Victims’ Rights Officer (United Nations Volunteer) be redeployed from the Office of the Special Representative of the Secretary-General to strengthen the Mission’s capacity to support victims’ rights in a more operationally focused manner. As the Mission adapts its structure to evolving mandate priorities, the proposed redeployment will ensure more effective coordination within the Mission, enhance service delivery to victims and optimize the use of existing human resources without additional financial implications.

Office of the Deputy Special Representative of the Secretary-General (Protection and Operations)

49.	It is proposed that one post of Gender Affairs Officer (P-3), three posts of Gender Affairs Officer (National Professional Officer), one post of Associate Gender Affairs Officer (National Professional Officer) and one post of Administrative Assistant (national General Service) be redeployed from the Office of the Special Representative of the Secretary-General. These posts support the integration of gender equality and women’s empowerment across all aspects of mandate implementation by advising senior leadership, providing technical guidance and ensuring that Mission policies and operations reflect the distinct needs of women, men, girls and boys.

50.	The proposed redeployment of these positions is intended to strengthen coherence across protection functions and improve alignment among components responsible for the protection of civilians, human rights, child protection, conflict-related sexual violence and gender mainstreaming. It will facilitate joint analysis and programming, as well as the systematic integration of gender perspectives into protection priorities. It will also streamline reporting and advisory channels, reinforce delivery of the Mission’s women and peace and security commitments, and enhance the effectiveness, efficiency and overall impact of the Mission’s protection architecture.

Office of the Chief of Staff

51.	It is proposed that one post of Political Affairs Officer (P-4) be redeployed from the Office of the Special Representative of the Secretary-General. The Office of the Chief of Staff provides central coordination across all Mission components, ensuring coherence, effective management and unified mandate implementation. It oversees a front office, chairs key coordination mechanisms and supports integrated planning and information flow among civilian, military and police elements. The proposed redeployment is intended to strengthen the Mission’s capacity for cross-cutting coordination, mission planning, strategic reporting, decision-tracking and liaison with senior leadership and field elements, thereby enhancing overall coherence and follow-up on strategic priorities.

52.	It is proposed that one post of Administrative Officer (Field Service) be redeployed from the Conduct and Discipline Service to strengthen the administrative and operational support capacity of the Office of the Chief of Staff, by providing direct support to the Chief of Staff and Field Office Coordination, as well as cross-functional support to all sections under the Office of the Chief of Staff. The post will ensure a permanent administrative presence responsible for key functions, including recruitment and human resources advisory support, budget and financial oversight, interdepartmental coordination and supervision of a support unit, providing additional support to the Special Representative of the Secretary-General’s front office as required. It will also enhance the efficiency and responsiveness of the Office of the Chief of Staff in delivering its mandate.

53.	It is proposed that one post of Light Vehicle Driver (national General Service) be redeployed from the Strategic Communications and Public Information Service to strengthen the logistical and operational efficiency of the Office of the Chief of Staff by providing dedicated driver support to the Chief of Staff and his/her front office. The post will ensure reliable and secure transportation for mission-wide activities, high-level engagements and field visits, while supporting administrative movements, document delivery and other logistical tasks. This redeployment will enhance scheduling flexibility, facilitate coordination with field offices and external stakeholders and improve confidentiality and security for sensitive movements.

Joint Coordination and Analysis Centre

54.	In response to the complex and dynamic operational environment in the Central African Republic, MINUSCA must adopt a more integrated, agile and data-driven approach to peacekeeping. The current separation between the Joint Operations Centre and the Joint Mission Analysis Centre has resulted in fragmented workflows and duplication of effort. Although both units draw on similar data sources, field inputs and digital platforms, they operate in parallel structures that limit mission-wide situational awareness and operational coherence.

55.	It is therefore proposed that the Joint Operations Centre and the Joint Mission Analysis Centre be consolidated into a single organizational unit, to be renamed the Joint Coordination and Analysis Centre. The merged unit will streamline operational and analytical functions, strengthen coordination across Mission components and improve the timeliness and quality of decision-making. The Joint Coordination and Analysis Centre will leverage digital transformation, including artificial intelligence-enabled analytics, automated incident monitoring and real-time dashboards, to provide timely, actionable insights to both Mission headquarters and field offices. This restructuring is aligned with the MINUSCA decentralization strategy by equipping field teams with enhanced tools, autonomy and analytical capacity to respond more effectively to evolving local dynamics.

56.	The Joint Coordination and Analysis Centre will function as the central hub for multi-source information management, integrating operational reporting with strategic assessments to support proactive planning and rapid crisis response. The consolidation will also reinforce collaboration with the Military U2 cell, the Police Operations Centre and the Security Operations Centre, ensuring that military intelligence, public safety functions and security operations are fully aligned within a unified framework. By optimizing resources, harmonizing reporting and fostering cross-functional collaboration, the Joint Coordination and Analysis Centre will enhance mission effectiveness, reduce operational redundancies and build a more resilient and adaptive mission-wide information architecture. This transformation reflects best practices in contemporary peacekeeping and positions MINUSCA to implement its mandate with greater precision, agility and impact.

57.	Accordingly, it is proposed that the posts and positions of the Joint Operations Centre and the Joint Mission Analysis Centre, detailed in the table below, be redeployed to the Joint Coordination and Analysis Centre.

Reassignment

Mission Planning Unit

58.	It is proposed that one post of Telecommunications Assistant (national General Service) in the Field Technology Section be reassigned as an Information Management Assistant to strengthen the Unit’s capacity to support data collection, analysis and visualization for strategic decision-making. The post will enhance the systematic tracking and presentation of Mission activities and financial performance, including through interactive dashboards such as the programmatic funds and strategic communications and public information dashboards, enabling real-time monitoring of project implementation and expenditure trends. By improving the consistency and accessibility of information, the role would reinforce accountability and support leadership decision-making through accurate and comprehensive data, while integrating planning, budgeting and performance monitoring within a unified, results-oriented framework.

Establishment

Office of the Deputy Special Representative of the Secretary-General (Resident Coordinator/Humanitarian Coordinator)

59.	In line with the request from the General Assembly in its resolution 76/274 for further nationalization and taking into account the proposed abolishment of one post of Senior Victims’ Rights Officer (P-5) in the Office of the Special Representative of the Secretary-General, the capacity of national staff and the potential for increased efficiencies, it is proposed that one post of Victims’ Rights Officer (National Professional Officer) be established. The proposed national post will ensure the continued delivery of victims’ rights functions in a more cost-effective and operationally focused manner. Leveraging national expertise, language proficiency and knowledge of the local context is expected to enhance direct engagement with affected communities and facilitate the timely implementation of activities, while contributing to overall budgetary efficiencies and the Mission’s nationalization objectives.

Continuation of general temporary assistance positions

Office of the Deputy Special Representative of the Secretary-General (Protection and Operations)

60.	One position of Programme Management Officer (P-4), funded under general temporary assistance, was established on 1 July 2022 and is embedded in the staffing of the Office of the Deputy Special Representative of the Secretary-General (Protection and Operations) to direct implementation of the mine action programme in MINUSCA. In view of the continuation of the programme in the 2026/27 period, it is proposed that this position be retained. The incumbent develops the Mission’s mine action programme strategy; leads operational planning, programme design and responses to threats; supports advocacy efforts; and oversees the delivery and performance of implementing partners.

Aviation Section

61.	It is proposed that 10 positions of Air Operations Assistant (national General Service), funded under general temporary assistance, be retained to operate the specialized firefighting vehicles during aircraft refuelling and engine start-up, take-off and landing.

Change of organizational unit title

Office of the Deputy Special Representative of the Secretary-General (Protection and Operations)

62.	It is proposed that the name of the Office be changed from the Office of the Deputy Special Representative of the Secretary-General (Political) to the Office of the Deputy Special Representative of the Secretary-General (Protection and Operations). The proposed change reflects an evolution in the focus of the Office, aligning it more closely with the Mission’s current priorities and operational realities. It also underscores the centrality of protection-related responsibilities within the Mission’s mandate, while clarifying leadership and accountability for protection outcomes.

Mission Planning Unit

63.	It is proposed that the name of the Unit be changed from Strategic Planning Unit to Mission Planning Unit. The proposed change better reflects contemporary United Nations policy and planning practices, as well as the Mission’s evolving operational realities. As the Mission continues to adapt its structures to shifting mandate priorities, this change will align the function more closely with integrated, forward-looking and results-oriented planning processes. It will also enhance clarity of purpose across Mission components, strengthen coordination and ensure that planning frameworks remain responsive, practical and operationally relevant, without entailing additional resource implications.

Proposed staffing changes

| Component/office/section/unit | Type | Number | Level | Functional title | Action | From/to |
| --- | --- | --- | --- | --- | --- | --- |
| Executive direction and management |  |  |  |  |  |  |
| Office of the Special Representative of the Secretary-General |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Gender Affairs Officer | Redeployment | To Office of the Deputy Special Representative of the Secretary-General (Protection and Operations) |
|  | National | (3) | NPO | Gender Affairs Officer |  |  |
|  |  | (1) | NPO | Associate Gender Affairs Officer |  |  |
|  |  | (1) | NGS | Administrative Assistant |  |  |
| Position |  | (1) | UNV | Victims’ Rights Officer |  |  |
| Post | International | (1) | P-4 | Political Affairs Officer | Redeployment | To Office of the Chief of Staff |
|  |  | (1) | P-5 | Senior Gender Affairs Officer | Abolishment |  |
|  |  | (1) | P-5 | Senior Victims’ Rights Officer |  |  |
| Net change |  | (10) |  |  |  |  |
| Office of the Deputy Special Representative of the Secretary-General (Resident Coordinator/Humanitarian Coordinator) |  |  |  |  |  |  |
| Position | National | 1 | UNV | Victims’ Rights Officer | Redeployment | From Office of the Special Representative of the Secretary-General |
| Post |  | 1 | NPO | Victims’ Rights Officer | Establishment |  |
|  | International | (1) | P-4 | Programme Management Officer | Abolishment |  |
| Net change |  | 1 |  |  |  |  |
| Office of the Deputy Special Representative of the Secretary-General (Protection and Operations) |  |  |  |  |  |  |
| Post | International | 1 | P-3 | Gender Affairs Officer | Redeployment | From Office of the Special Representative of the Secretary-General |
|  | National | 3 | NPO | Gender Affairs Officer |  |  |
|  |  | 1 | NPO | Associate Gender Affairs Officer |  |  |
|  |  | 1 | NGS | Administrative Assistant |  |  |
| Position | International | 1 | P-4 | Programme Management Officer | Continuation |  |
| Net change |  | 6 |  |  |  |  |
| Office of the Chief of Staff |  |  |  |  |  |  |
| Post | International | 1 | P-4 | Political Affairs Officer | Redeployment | From Office of the Special Representative of the Secretary-General |
|  |  | 1 | FS | Administrative Officer |  | From Conduct and Discipline Service |
|  | National | 1 | NGS | Light Vehicle Driver |  | Strategic Communications and Public Information Service |
|  | International | (2) | P-5 | Head of Office, Political Affairs | Abolishment |  |
|  |  | (2) | P-4 | Political Affairs Officer |  |  |
|  |  | (1) | P-3 | Protocol Officer |  |  |
|  |  | (1) | FS | Administrative Assistant |  |  |
| Position |  | (1) | UNV | Special Assistant |  |  |
| Net change |  | (4) |  |  |  |  |
| Joint Operations Centre |  |  |  |  |  |  |
| Post | International | (1) | P-5 | Senior Joint Operations Officer | Redeployment | To Joint Coordination and Analysis Centre |
|  |  | (5) | P-3 | Joint Operations Officer |  |  |
|  |  | (1) | P-2 | Associate Administrative Officer |  |  |
|  |  | (1) | P-2 | Associate Information Systems Officer |  |  |
|  | National | (2) | NPO | Associate Information Analyst |  |  |
| Position | International | (13) | UNV | Joint Operations Officer |  |  |
| Post |  | (1) | P-3 | Joint Operations Officer | Abolishment |  |
| Net change |  | (24) |  |  |  |  |
| Joint Mission Analysis Centre |  |  |  |  |  |  |
| Post | International | (1) | P-5 | Senior Information Analyst, Political Affairs | Redeployment | To Joint Coordination and Analysis Centre |
|  |  | (3) | P-3 | Information Analyst, Political Affairs |  |  |
|  |  | (2) | P-2 | Associate Information Analyst, Political Affairs |  |  |
|  | National | (2) | NPO | Associate Information Analyst |  |  |
|  |  | (2) | NPO | Assistant Information Analyst |  |  |
|  |  | (1) | NGS | Administrative Assistant |  |  |
| Position | International | (1) | UNV | Associate Database Analyst |  |  |
|  |  | (9) | UNV | Associate Information Analyst |  |  |
| Post |  | (1) | P-4 | Information Analyst | Abolishment |  |
| Net change |  | (22) |  |  |  |  |
| Joint Coordination and Analysis Centre |  |  |  |  |  |  |
| Post | International | 1 | P-5 | Senior Joint Operations Officer | Redeployment | From Joint Operations Centre |
|  |  | 5 | P-3 | Joint Operations Officer |  |  |
|  |  | 1 | P-2 | Associate Administrative Officer |  |  |
|  |  | 1 | P-2 | Associate Information Systems Officer |  |  |
|  | National | 2 | NPO | Associate Information Analyst |  |  |
| Position | International | 13 | UNV | Joint Operations Officer |  |  |
| Post |  | 1 | P-5 | Senior Information Analyst, Political Affairs | Redeployment | From Joint Mission Analysis Centre |
|  |  | 3 | P-3 | Information Analyst, Political Affairs |  |  |
|  |  | 2 | P-2 | Associate Information Analyst, Political Affairs |  |  |
|  | National | 2 | NPO | Associate Information Analyst |  |  |
|  |  | 2 | NPO | Assistant Information Analyst |  |  |
|  |  | 1 | NGS | Administrative Assistant |  |  |
| Position | International | 1 | UNV | Associate Database Analyst |  |  |
|  |  | 9 | UNV | Associate Information Analyst |  |  |
| Net change |  | 44 |  |  |  |  |
| Conduct and Discipline Service |  |  |  |  |  |  |
| Post | International | (1) | FS | Administrative Officer | Redeployment | To Office of the Chief of Staff |
|  |  | (1) | P-3 | Conduct and Discipline Officer | Abolishment |  |
|  |  | (1) | UNV | Conduct and Discipline Officer |  |  |
| Net change |  | (3) |  |  |  |  |
| Mission Planning Unit |  |  |  |  |  |  |
| Post | National | 1 | NGS | Information Management Assistant | Reassignment | From Field Technology Section |
| Net change |  | 1 |  |  |  |  |
| Strategic Communications and Public Information Service |  |  |  |  |  |  |
| Post | National | (1) | NGS | Light Vehicle Driver | Redeployment | To Office of the Chief of Staff |
|  | International | (1) | D-1 | Chief of Service, Communications | Abolishment |  |
|  |  | (1) | P-4 | Radio Producer |  |  |
|  |  | (1) | P-3 | Public Information Officer |  |  |
| Position |  | (2) | UNV | Radio Producer and Outreach Officer |  |  |
|  |  | (1) | UNV | Radio Producer |  |  |
| Net change |  | (7) |  |  |  |  |
| Subtotal, executive direction and management |  | (18) |  |  |  |  |
| Component 1: support for political, peace and reconciliation processes |  |  |  |  |  |  |
| Political Affairs Division |  |  |  |  |  |  |
| Post | International | (1) | P-5 | Senior Electoral Officer | Abolishment |  |
|  |  | (2) | P-4 | Electoral Officer |  |  |
|  |  | (2) | P-4 | Political Affairs Officer |  |  |
|  |  | (1) | FS | Administrative Assistant |  |  |
| Net change |  | (6) |  |  |  |  |
| Disarmament, Demobilization and Reintegration Section |  |  |  |  |  |  |
| Post | International | (2) | P-4 | Disarmament, Demobilization and Reintegration Officer | Abolishment |  |
|  |  | (2) | P-3 |  |  |  |
| Net change |  | (4) |  |  |  |  |
| Security Sector Reform Service |  |  |  |  |  |  |
| Post | International | (1) | FS | Administrative Assistant | Abolishment |  |
| Net change |  | (1) |  |  |  |  |
| Electoral Affairs Service |  |  |  |  |  |  |
| Position | International | (1) | D-1 | Principal Electoral Affairs Officer | Abolishment |  |
|  |  | (5) | P-4 | Electoral Officer |  |  |
|  |  | (22) | P-3 | Electoral Officer |  |  |
|  |  | (1) | FS | Administrative Assistant |  |  |
|  | National | (1) | NGS | Driver |  |  |
|  | International | (37) | UNV | Electoral Officer |  |  |
| Net change |  | (67) |  |  |  |  |
| Subtotal, component 1 |  | (78) |  |  |  |  |
| Component 2: security, protection of civilians and human rights |  |  |  |  |  |  |
| Human Rights Division |  |  |  |  |  |  |
| Post | International | (2) | P-4 | Human Rights Officer | Abolishment |  |
|  |  | (1) | FS | Administrative Assistant |  |  |
| Position |  | (2) | UNV | Human Rights Officer |  |  |
| Net change |  | (5) |  |  |  |  |
| Child Protection Unit |  |  |  |  |  |  |
| Post | International | (1) | P-4 | Child Protection Officer | Abolishment |  |
| Net change |  | (1) |  |  |  |  |
| Subtotal, component 2 |  | (6) |  |  |  |  |
| Component 3: fight against impunity and support for the extension of State authority and rule of law |  |  |  |  |  |  |
| Justice and Corrections Section |  |  |  |  |  |  |
| Post | International | (2) | P-5 | Senior Judicial Affairs Officer | Abolishment |  |
|  |  | (4) | P-4 | Judicial Affairs Officer |  |  |
|  |  | (2) | P-3 | Judicial Affairs Officer |  |  |
|  |  | (1) | P-3 | Corrections Officer |  |  |
| Net change |  | (9) |  |  |  |  |
| Subtotal, component 3 |  | (9) |  |  |  |  |
| Component 4: support |  |  |  |  |  |  |
| Aviation Section |  |  |  |  |  |  |
| Position | National | 10 | NGS | Air Operations Assistant | Continuation |  |
| Post | International | (1) | P-3 | Air Operations Officer | Abolishment |  |
| Net change |  | (1) |  |  |  |  |
| Medical Services Section |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Medical Officer | Abolishment |  |
| Position |  | (1) | UNV | Laboratory Technician |  |  |
| Net change |  | (2) |  |  |  |  |
| Life Support Section |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Fuel Officer | Abolishment |  |
|  |  | (1) | FS | Logistics Assistant |  |  |
|  |  | (1) | FS | Supply Assistant |  |  |
| Net change |  | (3) |  |  |  |  |
| Supply Chain Management Service (Office of the Chief) |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Acquisition Planning Officer | Abolishment |  |
|  |  | (2) | FS | Acquisition Planning Assistant |  |  |
|  |  | (1) | FS | Property Management Assistant |  |  |
|  |  | (1) | FS | Procurement Assistant |  |  |
|  |  | (1) | FS | Logistics Assistant |  |  |
| Net change |  | (6) |  |  |  |  |
| Centralized Warehouse Section |  |  |  |  |  |  |
| Position | International | (2) | UNV | Warehouse Assistant | Abolishment |  |
| Net change |  | (2) |  |  |  |  |
| Movement Control Section |  |  |  |  |  |  |
| Post | International | (1) | FS | Movement Control Assistant | Abolishment |  |
| Net change |  | (1) |  |  |  |  |
| Field Technology Section |  |  |  |  |  |  |
| Post | National | (1) | NGS | Telecommunications Assistant | Reassignment | To Mission Planning Unit |
|  | International | (2) | FS | Telecommunications Technician | Abolishment |  |
|  |  | (1) | FS | Information Management Assistant |  |  |
| Net change |  | (4) |  |  |  |  |
| Integrated Mission Training Cell |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Training Officer | Abolishment |  |
| Net change |  | (1) |  |  |  |  |
| Security Section |  |  |  |  |  |  |
| Post | International | (1) | P-3 | Close Protection Coordination Officer | Abolishment |  |
|  |  | (4) | P-3 | Security Coordination Officer |  |  |
|  |  | (7) | FS | Close Protection Officer |  |  |
|  |  | (4) | FS | Security Officer |  |  |
|  |  | (2) | FS | Investigations Assistant |  |  |
|  |  | (1) | FS | Information Systems Officer |  |  |
| Net change |  | (19) |  |  |  |  |
| Subtotal, component 4 |  | (39) |  |  |  |  |
| Total |  | (150) |  |  |  |  |

G.	Results-based budgeting frameworks

Component 1: support for political, peace and reconciliation processes

| Expected accomplishment | Indicators of achievement |
| --- | --- |
| 1.1 Operationalization of all components of the joint road map in harmony with the Political Agreement | 1.1.1 Number of new members of armed groups sustainably disarmed and demobilized who have received reinsertion support (2022/23: 351; 2023/24: 226; 2024/25: 593; 2025/26: 1,000; 2026/27: not applicable) |
|  | 1.1.2 Number of armed group members disarmed and demobilized (2022/23: 388; 2023/24: 174; 2024/25: 592; 2025/26: 700; 2026/27: 800) |
|  | 1.1.3 The Truth, Justice, Reparation and Reconciliation Commission, as a transitional justice mechanism recommended in the Political Agreement, is operational (2022/23: not applicable; 2023/24: not applicable; 2024/25: no; 2025/26: yes; 2026/27: not applicable) |
|  | 1.1.4 Number of hearings by the Truth, Justice, Reparation and Reconciliation Commission (2022/23: 0; 2023/24: 0; 2024/25: 0; 2025/26: 1; 2026/27: 4) |
|  | 1.1.5 Progress in the implementation of key strategies and policies on security sector reform (2022/23: 1 strategy and 3 sectoral plans; 2023/24: not applicable; 2024/25: 1 national security sector reform strategy, 4 national policies and 1 sectoral plan; 2025/26: 1 national security sector reform strategy, 1 national defence strategy, 3 national policies and 2 sectoral plans; 2026/27: not applicable) |
|  | 1.1.6 Number of advisory meetings with the diplomatic community and regional, national and local stakeholders to support coordination of the implementation of the pooled peace process, and measure the implementation of the pooled peace process in line with the joint road map and the Political Agreement (2022/2023: not applicable; 2023/24: not applicable; 2024/25: 2; 2025/26: 2; 2026/27: 5) |
|  | 1.1.7 Number of decentralized Government dashboards finalized and approved (2022/23: 1; 2023/24: 3; 2024/25: 0; 2025/26: 7; 2026/27: 20) |
|  | 1.1.8 Number of armed groups present in the Central African Republic (2022/23: 28; 2023/24: 5; 2024/25: 4; 2025/26: 3; 2026/27: 2) |
|  | 1.1.9 Progress in the implementation of the security sector reform sectoral policies/strategies/plans with subsequent regulatory framework in effect (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 2 national strategies, 3 national policies and 1 sectoral plan; 2026/27: 2 national strategies, 3 national policies and 1 sectoral plan) |
|  | 1.1.10 Percentage of independent and democratic oversight bodies and mechanisms for national defence and security forces fully operational (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 100) |
|  | 1.1.11 Number of activities outlined in the national action plan to combat the proliferation of small arms and light weapons where progress has been achieved (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 8) |
|  | 1.1.12 Number of cross-border incidents (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 5) |
|  | 1.1.13 Progress in the implementation of a national border management policy and the action plans (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 1 action plan and 1 policy) |
|  | 1.1.14 Number of violations of the Political Agreement by signatory parties (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 600) |
|  | 1.1.15 Number of mediation efforts conducted towards armed groups’ leaders (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 20) |
| 1.2 Decentralized peace process through targeted MINUSCA interventions in geographically strategic and priority areas | 1.2.1 Number of advisory meetings with the Prime Minister’s Office, line ministries and the prefectural committees for the implementation of the Political Agreement to facilitate the development and appropriate use of the national and prefectural dashboards and ownership of the pooled peace process at the prefectural and local levels (2022/23: not applicable; 2023/24: not applicable; 2024/25: 4; 2025/26: 4; 2026/27: 5) |
|  | 1.2.2 Number of political engagements at the local level to increase the participation of communities in local governance and in the pooled political process, as well as in its ownership (2022/23: not applicable; 2023/24: not applicable; 2024/25: 5; 2025/26: 5; 2026/27: 7) |
|  | 1.2.3 Number of security incidents in communities where community violence reduction programmes are implemented (2022/23: 123; 2023/24: 3,778; 2024/25: 300; 2025/26: 250; 2026/27: 200) |
|  | 1.2.4 Number of inclusive community reconciliation programmes that contribute to peace and stability with the participation of youth and women (2022/23: 18; 2023/24: not applicable; 2024/25: 20; 2025/26: 16; 2026/27: 30) |
|  | 1.2.5 Number of local initiatives undertaken by civil society organizations, including youth, religious leaders and women’s organizations, to promote local peace following outreach and awareness-raising activities (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 350) |
|  | 1.2.6 Number of joint projects between the Mission and the United Nations country team (2022/23: not applicable; 2023/24: 10; 2024/25: 10; 2025/26: 15; 2026/27: 17) |
|  | 1.2.7 Number of actions taken to support the United Nations Population Fund in assisting victims of sexual violence (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 20) |
|  | 1.2.8 Number of community members who have been trained in and started income-generating activities through quick-impact projects, programmatic funds and community violence reduction projects (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 3,000) |
|  | 1.2.9 Total number of beneficiaries of community violence reduction projects (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 6,300) |
|  | 1.2.10 Number of transhumance-related incidents 2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 30) |
|  | 1.2.11 Number of prefectural implementation committees operational in priority areas (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 20) |
| 1.3 Inclusive and credible elections | 1.3.1 Percentage of polling stations where elections are held in accordance with the mapping conducted by the National Electoral Authority (2022/23: not applicable; 2023/24: not applicable; 2024/25: 0 per cent; 2025/26: 100 per cent; 2026/27: not applicable) |
|  | 1.3.2 Percentage of electoral disputes addressed by the competent judicial bodies while respecting legal time frames (2022/23: not applicable; 2023/24: not applicable; 2024/25: 100 per cent; 2025/26: 100 per cent; 2026/27: not applicable) |
|  | 1.3.3 Percentage of female candidates for elections and officials elected to local governing bodies (2022/23: 0 per cent; 2023/24: not applicable; 2024/25: 0 per cent; 2025/26: 35 per cent; 2026/27: not applicable) |
|  | 1.3.4 Level of technical, operational, logistical and security preparedness for the timely holding of elections (2022/23: not applicable; 2023/24: moderate/ mediocre; 2024/25: moderate/mediocre; 2025/26: very high; 2026/27: not applicable) |
|  | 1.3.5 Percentage of women elected in municipal and regional councils (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 30 per cent; 2026/27: not applicable) |
|  | 1.3.6 Number of electoral polling stations secured by election day, meeting defined criteria (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 20; 2026/27: not applicable) |
|  | 1.3.7 Number of registered voters of between 18–35 years of age (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 4,000; 2026/27: not applicable) |
| 1.4 Strengthened democratic institutions, trust and political dialogue | 1.4.1 Number of activities in support of civil society organizations and national human rights institutions to foster civic space and community engagement (2022/23: not applicable; 2023/24: not applicable; 2024/25: 214; 2025/26: not applicable; 2026/27: not applicable) |
|  | 1.4.2 Number of political opposition parties taking part in consultations and dialogue processes with the Government (2022/23: not applicable; 2023/24: not applicable; 2024/25: 10; 2025/26: 10; 2026/27: 10) |
|  | 1.4.3 Number of civil society organizations taking part in consultations and dialogue processes with the Government to foster consensus and trust in the electoral process (2022/23: not applicable; 2023/24: not applicable; 2024/25: 50; 2025/26: 50; 2026/27: 50) |
|  | 1.4.4 Number of actionable agreements, resolutions or mediations actions addressing disagreements and tensions that are implemented (2022/23: 10; 2023/24: 3; 2024/25: 0; 2025/26: 10; 2026/27: 15) |
|  | 1.4.5 Number of field visits and joint missions facilitated for members of Parliament to their constituencies (2022/23: not applicable; 2023/24: 24; 2024/25: 15; 2025/26: 25; 2026/27: 30) |
| External factors |  |
| The willingness of armed groups, including those that have renounced the Political Agreement, to engage in the national disarmament, demobilization and reintegration process, comply with the eligibility criteria of the national programme and respect the commitments made by signing the Political Agreement; and political will and trust among national and regional stakeholders to continue to implement the Agreement, including through the joint road map adopted under the International Conference on the Great Lakes Region |  |

Component 2: security, protection of civilians and human rights

| Expected accomplishment | Indicators of achievement |
| --- | --- |
| 2.1 Enhanced explosive threat mitigation and protection of civilians and human rights | 2.1.1 Number of violations of the Political Agreement (2022/23: 1,117; 2023/24: 1,037; 2024/25: 284; 2025/26: 1,500; 2026/27: not applicable) |
|  | 2.1.2 Number of attacks and armed clashes between parties to the conflict (2022/23: 224; 2023/24: 258; 2024/25: 180; 2025/26: 150; 2026/27: 100) |
|  | 2.1.3 Number of cases of violations of human rights and international humanitarian law, including grave violations of the rights of children and conflict-related sexual violence, brought to the attention of national authorities and armed groups (2022/23: 1,179; 2023/24: 877, 2024/25: 3,185; 2025/26: 1,000; 2026/27: not applicable) |
|  | 2.1.4 Percentage of the total number of identified explosive ordnance safely destroyed (2022/23: 83 per cent; 2023/24: 91 per cent; 2024/25: 96 per cent; 2025/26: not applicable; 2026/27: not applicable) |
|  | 2.1.5 Number of members of most at-risk local communities who demonstrate increased knowledge of safe and unsafe practices as a result of explosive ordnance risk education (2022/23: 21,693; 2023/24: 27,397; 2024/25: 26,141; 2025/26: 20,000; 2026/27: not applicable) |
|  | 2.1.6 Total number of national stakeholders (including national defence and internal security forces) trained on human rights, protection of civilians, protection of children and prevention of conflict-related sexual violence and gender-based violence (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 1,500; 2026/27: 2,000) |
|  | 2.1.7 Number of joint protection team missions deployed to prevent escalations of protection of civilians concerns (2022/23: not applicable; 2023/24: 6; 2024/25: 148; 2025/26: 150; 2026/27: 150) |
|  | 2.1.8 Number of incidents of extortion and illegal taxation committed by armed groups (2022/23: 38; 2023/24: 51; 2024/25: 40; 2025/26: 30; 2026/27: 20) |
|  | 2.1.9 Number of conflict-related human rights violations and international humanitarian law breaches (2022/23: not applicable; 2023/24: 92; 2024/25: 234; 2025/26: 200; 2026/27: 150) |
|  | 2.1.10 Number of civilian victims of conflict-related incidents (2022/23: not applicable; 2023/24: 210; 2024/25: 327; 2025/26: 250; 2026/27: 200) |
|  | 2.1.11 Number of documented grave violations committed against children in armed conflict (2022/23: 322; 2023/24: 662; 2024/25: 979; 2025/26: 600; 2026/27: 400) |
|  | 2.1.12 Number of engagements with parties to the conflict to better prevent and end conflict-related sexual violence (2022/23: 0; 2023/24: not applicable; 2024/25: 12; 2025/26: 20; 2026/27: 24) |
|  | 2.1.13 Percentage of reported explosive ordnance incidents responded to by MINUSCA and national authorities with Mine Action Service support (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 50 per cent; 2026/27: 50 per cent) |
|  | 2.1.14 Number of mine action activities conducted by the national mine action authority (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: 12) |
|  | 2.1.15 Number of children released by parties to the conflict following dialogue (2022/23: 222; 2023/24: 118; 2024/25: 415; 2025/26: 450; 2026/27: 200) |
|  | 2.1.16 Number of refugees and internally displaced persons in the Central African Republic (2022/23: not applicable; 2023/24: not applicable; 2024/25: 4,037; 2025/26: 3,500; 2026/27: 2,500) |
| 2.2 Optimized protection resources of the Mission | 2.2.1 Weekly average of the force total strength on patrol (2022/23: not applicable; 2023/24: not applicable; 2024/25: 25 per cent; 2025/26: 30 per cent; 2026/27: 30 per cent) |
|  | 2.2.2 Weekly average of the police total strength on patrol (2022/23: not applicable; 2023/24: not applicable; 2024/25: 70 per cent; 2025/26: 70 per cent; 2026/27: 70 per cent) |
|  | 2.2.3 Number of missions of the Mission’s joint protection team to assess and analyse security and protection needs, enhance early warning and recommend preventive and responsive interventions (2022/23: not applicable; 2023/24: not applicable; 2024/25: 133; 2025/26: 25; 2026/27: not applicable) |
|  | 2.2.4 Percentage of active community alert networks managed by community liaison assistants that generate proactive threat mitigations to protect civilians (2022/23: not applicable; 2023/24: not applicable; 2024/25: 100 per cent; 2025/26: 80 per cent; 2026/27: not applicable) |
|  | 2.2.5 Number of operational community alert networks (2022/23: 1,434; 2023/24: 1,839; 2024/25: 2,208; 2025/26: 2,300; 2026/27: 2,400) |
|  | 2.2.6 Percentage of community alert networks responded to by the Mission (2022/23: not applicable; 2023/24: 100 per cent; 2024/25: 100 per cent; 2025/26: 80 per cent; 2026/27: 90 per cent) |
| External factors |  |
| The continued deployment and modalities of deployment of bilaterally deployed forces and other security personnel to the security environment; the conduct of armed groups; the timely deployment and remuneration of national security personnel and the technical capacity of national authorities to assume increasing and sustainable responsibility for the provision of security and the protection of civilians; and increased violence and protection concerns during the local electoral process and attempts to destabilize the implementation of the Political Agreement |  |

Component 3: fight against impunity and support for the extension of State authority and rule of law

| Expected accomplishment | Indicators of achievement |
| --- | --- |
| 3.1 Enhanced State authority through the provision of support in the areas of security, rule of law, the fight against impunity, and local administration throughout the country | 3.1.1 Number of State representatives present in their posts at the local level (2022/23: not applicable; 2023/24: not applicable; 2024/25: 2,394; 2025/26: 5,180; 2026/27: 2,750) |
|  | 3.1.2 Number of local authorities and civil servants deployed to their duty stations by MINUSCA (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 800; 2026/27: 900) |
|  | 3.1.3 Number of internal security forces personnel deployed (2022/23: 1,144; 2023/24: 1,700; 2024/25: 1,854; 2025/26: 2,000; 2026/27: 2,500) |
|  | 3.1.4 Number of operational internal security forces buildings (2022/23: 150; 2023/24: 436; 2024/25: 670; 2025/26: 750; 2026/27: 850) |
|  | 3.1.5 Total number of cases closed by the Special Criminal Court’s Investigating Chamber since inception of the Court (2022/23: not applicable; 2023/24: 10; 2024/25: 6; 2025/26: 11; 2026/27: not applicable) |
|  | 3.1.6 Total number of judgments delivered by the Special Criminal Court’s Trial and Appeals Chambers since inception of the Court (2022/23: not applicable; 2023/24: 6; 2024/25: 6; 2025/26: 8; 2026/27: 12) |
|  | 3.1.7 Average number of serious prison incidents (escapes, riots, attacks on prisons) per 100 detainees (2022/23: 0.77; 2023/24: 2; 2024/25: 7; 2025/26: 2; 2026/27: not applicable) |
|  | 3.1.8 Percentage of prisoners in unlawful or pretrial detention (2022/23: not applicable; 2023/24: not applicable; 2024/25: 69 per cent; 2025/26: 65 per cent) |
|  | 3.1.9 Transformation of the national defence and internal security forces into a garrison army (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: not applicable; 2026/27: tangible and measurable garrisoning of national forces) |
|  | 3.1.10 Number of judicial personnel present and active throughout the country (2022/23: 125; 2023/24: 155; 2024/25: 148; 2025/26: 200; 2026/27: 213) |
|  | 3.1.11 Number of penitentiary personnel present and active throughout the country (2022/23: 109; 2023/24: 380; 2024/25: 396; 2025/26: 401; 2026/27: 401) |
|  | 3.1.12 Number of prefectures that have buildings of local administration that were operationalized through quick-impact projects and programmatic funds (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 50; 2026/27: 60) |
|  | 3.1.13 Number of courts functioning in the Central African Republic (2022/23: 23; 2023/24: 23; 2024/25: 26; 2025/26: 30; 2026/27: 34) |
|  | 3.1.14 Number of prisons effectively operational throughout the country (2022/23: 15; 2023/24: 16; 2024/25: 16; 2025/26: 16; 2026/27: 17) |
|  | 3.1.15 Number of judicial oversight and accountability mechanisms established and operationalized (2022/23: not applicable; 2023/24: not applicable; 2024/25: not applicable; 2025/26: 10; 2026/27: 20) |
|  | 3.1.16 Annual number of criminal sessions held (2021/22: 2; 2022/23: 6; 2023/24: 6; 2024/25: 6; 2025/26: 6; 2026/27: 6) |
|  | 3.1.17 Number of mobile hearings held by courts of first instance (2021/22: not applicable; 2022/23: not applicable; 2023/24: 40; 2024/25: 45; 2025/26: 45; 2026/27: 45) |
| External factors |  |
| Armed group violence and host country fiscal constraints, as well as limited economic infrastructure throughout the country, may impede progress and the efforts of the Government to improve infrastructure across the country and strengthen the rule of law. Further, they may have an impact on the sustainable extension of State authority, delaying the timely deployment of necessary staff and hindering the ability of judicial personnel and civil servants to remain in their posts owing to the security situation and the ability of judicial actors to conduct investigations and proceedings. The willingness of the Ministry of Justice to implement disciplinary measures against unjustifiably absent personnel may also have an impact on progress, as well as on the inclination of strategic partners to provide timely and sufficient investments in strengthening basic services |  |

Component 4: support

| Expected accomplishment | Mission support indicators |
| --- | --- |
| 4.1 Rapid, effective, efficient and responsible support services for the Mission | 4.1.1 Average annual percentage of women international civilian staff (2022/23: 30.0 per cent; 2023/24: 34.0 per cent; 2024/25: 35.0 per cent; 2025/26: ≥ 40.0 per cent; 2026/27: ≥ 35.0 per cent) |
|  | 4.1.2 Average number of days for roster recruitments, from posting of job opening to candidate selection, for international candidates (2022/23: 100; 2023/24: 117; 2024/25: 85; 2025/26: ≥ 90; 2026/27: ≤ 120) |
|  | 4.1.3 Average number of days for post-specific recruitments, from posting of job opening to candidate selection, for international candidates (2022/23: 203; 2023/24: 392; 2024/25: 141; 2025/26: ≤ 120 calendar days for P-3 to D-1 and FS-3 to FS-7 levels; 2026/27: ≤ 120 calendar days) |
|  | 4.1.4 Overall score on the property management index based on 20 underlying key performance indicators (2022/23: 1,985; 2023/24: 1,950; 2024/25: 1,948; 2025/26: ≥ 1,975; 2026/27: ≥ 1,975) |
|  | 4.1.5 Percentage of contingent personnel in standard-compliant United Nations accommodations at 30 June, in accordance with memorandums of understanding (2022/23: 97.0 per cent; 2023/24: 100.0 per cent; 2024/25: 99.0 per cent; 2025/26: 100.0 per cent; 2026/27: 97.5 per cent) |
|  | 4.1.6 Compliance of vendors with United Nations rations standards for delivery, quality and stock management (2022/23: 98.4 per cent; 2023/24: 92.0 per cent; 2024/25: 94.7 per cent; 2025/26: 97.0 per cent; 2026/27: 97.0 per cent) |
| External factors |  |
| Changes in the political, security, economic and humanitarian contexts or unforeseen weather conditions that impede and delay the delivery of planned logistical mission support projects; and other instances of force majeure and changes in the mandate during the budget period |  |

Evaluation activities

64.	The following evaluations were completed by the Office of Internal Oversight Services (OIOS) during the 2024/25 period:

(a)	Evaluation of protection of civilians, security and human rights in the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic (IED-25-018);

(b)	Triennial review report on the implementation of OIOS recommendations in the report on the evaluation of political affairs in peacekeeping missions (IED-25-013);

(c)	Evaluation of children and armed conflict in peacekeeping operations (IED-25-005).

65.	The Mission has duly noted the findings of the above-referenced evaluations. While these evaluations provide valuable thematic insights, the Mission considers that a focused assessment of the implementation of the mission plan would yield greater strategic value, given the robust results framework guiding Mission priorities. Recognizing that ongoing liquidity constraints have at times limited full implementation of recommendations from thematic evaluations, the Mission underscores the importance of assessments that take into account both operational realities and the financial context. Such evaluations would enhance evidence-based decision-making, inform resource allocation and support adaptive strategies to maximize the effectiveness and impact of Mission activities.

66.	In addition, MINUSCA relies on semi-annual assessments conducted by the Comprehensive Planning and Performance Assessment System team against a set of indicators drawn from the mission plan’s outputs and outcomes. These indicators, now integrated at the outcome level into the present report, enable progress measurement and trend identification and provide leadership with data-driven analysis for informed decision-making. The integration of these indicators will also facilitate the use of infographics to present findings more clearly and accessibly. These assessments are well positioned to feed lessons learned into the Mission’s planning process.

II.	Financial resources

A.	Overall

(Thousands of United States dollars; budget year is from 1 July to 30 June)

|  |  |  | Variance |  |  | 2026/27 cost estimates | Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2024/25 apportionment | 2024/25 expenditure | Unencumbered balance | Percentage | 2025/26 apportionment |  | Amount | Percentage |
| Category | (1) | (2) | (3)=(1)-(2) | (4)=(3)÷(1) | (5) | (6) | (7)=(6)-(5) | (8)=(7÷5) |
| Military and police personnel |  |  |  |  |  |  |  |  |
| Military observers | 8 230.9 | 9 003.7 | (772.8) | (9.4) | 8 891.7 | 1 022.2 | (7 869.5) | (88.5) |
| Military contingents | 520 321.4 | 506 685.8 | 13 635.6 | 2.6 | 510 354.2 | 409 057.4 | (101 296.8) | (19.8) |
| United Nations police | 31 109.1 | 32 671.5 | (1 562.4) | (5.0) | 33 952.9 | 26 262.7 | (7 690.2) | (22.6) |
| Formed police units | 83 216.0 | 80 055.9 | 3 160.1 | 3.8 | 82 037.5 | 63 687.0 | (18 350.5) | (22.4) |
| Subtotal | 642 877.4 | 628 416.9 | 14 460.5 | 2.2 | 635 236.3 | 500 029.3 | (135 207.0) | (21.3) |
| Civilian personnel |  |  |  |  |  |  |  |  |
| International staff | 172 019.0 | 185 054.8 | (13 035.8) | (7.6) | 189 789.4 | 186 053.8 | (3 735.6) | (2.0) |
| National Professional Officer | 11 127.9 | 12 589.7 | (1 461.8) | (13.1) | 12 049.6 | 12 571.7 | 522.1 | 4.3 |
| National General Service staff | 19 166.5 | 20 067.2 | (900.7) | (4.7) | 19 017.7 | 19 289.6 | 271.9 | 1.4 |
| United Nations Volunteers | 20 227.6 | 19 308.6 | 919.0 | 4.5 | 20 825.1 | 17 700.6 | (3 124.5) | (15.0) |
| General temporary assistance | 7 526.8 | 7 130.3 | 396.5 | 5.3 | 8 544.9 | 899.8 | (7 645.1) | (89.5) |
| Government-provided personnel | 5 857.6 | 5 994.7 | (137.1) | (2.3) | 6 279.3 | 2 383.9 | (3 895.4) | (62.0) |
| Subtotal | 235 925.4 | 250 145.3 | (14 219.9) | (6.0) | 256 506.0 | 238 899.4 | (17 606.6) | (6.9) |
| Operational costs |  |  |  |  |  |  |  |  |
| Civilian electoral observers | – | – | – | – | – | – | – | – |
| Consultants and consulting services | 665.5 | 304.9 | 360.6 | 54.2 | 526.0 | 436.1 | (89.9) | (17.1) |
| Official travel | 3 623.5 | 3 265.2 | 358.3 | 9.9 | 3 597.3 | 5 196.0 | 1 598.7 | 44.4 |
| Facilities and infrastructure | 77 549.6 | 76 249.7 | 1 299.9 | 1.7 | 78 465.1 | 83 314.5 | 4 849.4 | 6.2 |
| Ground transportation | 19 616.5 | 19 111.5 | 505.0 | 2.6 | 18 831.5 | 18 505.4 | (326.1) | (1.7) |
| Air operations | 93 746.6 | 73 919.4 | 19 827.2 | 21.1 | 85 811.5 | 76 904.7 | (8 906.8) | (10.4) |
| Marine operations | 501.0 | 1 066.2 | (565.2) | (112.8) | 501.0 | 501.0 | – | – |
| Communications and information technology | 39 700.8 | 34 034.2 | 5 666.6 | 14.3 | 39 700.8 | 38 058.9 | (1 641.9) | (4.1) |
| Medical | 2 048.9 | 1 419.6 | 629.3 | 30.7 | 2 555.2 | 2 521.5 | (33.7) | (1.3) |
| Special equipment | – | – | – | – | – | – | – | – |
| Other supplies, services and equipment | 51 364.5 | 54 755.8 | (3 391.3) | (6.6) | 48 401.3 | 53 268.6 | 4 867.3 | 10.1 |
| Quick-impact projects | 4 000.0 | 3 580.4 | 419.6 | 10.5 | 4 000.0 | 4 000.0 | – | – |
| Subtotal | 292 816.9 | 267 706.9 | 25 110.0 | 8.6 | 282 389.7 | 282 706.7 | 317.0 | 0.1 |
| Gross requirements | 1 171 619.7 | 1 146 269.1 | 25 350.6 | 2.2 | 1 174 132.0 | 1 021 635.4 | (152 496.6) | (13.0) |
| Staff assessment income | 18 237.5 | 20 184.6 | (1 947.1) | (10.7) | 21 144.2 | 20 405.4 | (738.8) | (3.5) |
| Net requirements | 1 153 382.2 | 1 126 084.5 | 27 297.7 | 2.4 | 1 152 987.8 | 1 001 230.0 | (151 757.8) | (13.2) |
| Voluntary contributions in kind (budgeted) | – | – | – | – | – | – | – | – |
| Total requirements | 1 171 619.7 | 1 146 269.1 | 25 350.6 | 2.2 | 1 174 132.0 | 1 021 635.4 | (152 496.6) | (13.0) |

B.	Non-budgeted contributions

67.	The value of non-budgeted contributions for the periods from 1 July 2024 to 30 June 2025 and from 1 July 2026 to 30 June 2027 is as follows:

(Thousands of United States dollars)

| Category | Actual value (2024/25) | Estimated value (2026/27) |
| --- | --- | --- |
| Status-of-mission agreementa | 69 772.1 | 75 885.5 |
| Voluntary contributions in kind (non-budgeted) | 578.0 | 578.0 |
| Total | 70 350.1 | 76 463.5 |

a	Represents buildings, land and services provided by the Government of the Central African Republic.

C.	Efficiency gains

68.	The cost estimates for the period from 1 July 2026 to 30 June 2027 take into account the following efficiency initiatives:

(Thousands of United States dollars)

|  |  | Estimated efficiency gains (2024/25) | Realized efficiency gains (2024/25) | Variance (2024/25) | Investment since inception to generate the efficiency gains of 2026/27 | Cumulated efficiency gains since inception and before 2026/27 | Estimated efficiency gains (2026/27) | Cumulated investments and efficiency gains as of 2026/27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Budget class | Description of the initiative | (1) | (2) | (3)=(2)-(1) | (4) | (5) | (6) | (7)=(4)+(5)+(6) |
| Military and police personnel |  |  |  |  |  |  |  |  |
| Military observers | Reduction in planned deployment of personnel, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities | – | – | – | – | – | 7 050.4 | 7 050.4 |
| Military contingents |  | – | – | – | – | – | 98 149.4 | 98 149.4 |
| United Nations police |  | – | – | – | – | – | 7 756.9 | 7 756.9 |
| Formed police units |  | – | – | – | – | – | 14 836.8 | 14 836.8 |
| Civilian personnel |  |  |  |  |  |  |  |  |
| International staff | Efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to the staffing structure, while maintaining the delivery of core mandated activities | – | – | – | – | – | 19 473.9 | 19 473.9 |
| United Nations Volunteers |  | – | – | – | – | – | 1 178.2 | 1 178.2 |
| Government-provided personnel | Reduction in planned deployment of personnel, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities | – | – | – | – | – | 3 936.3 | 3 936.3 |
| Operational costs |  |  |  |  |  |  |  |  |
| Consultants and consulting services | Decrease in the engagement of individual consultants for expert support, in favour of greater use of in-house capacities and expertise | – | – | – | – | – | 89.9 | 89.9 |
| Facilities and infrastructure | (a) Installation of additional diesel-hybrid and solar power systems at various MINUSCA premises to reduce the Mission’s carbon footprint and increase its reliance on renewable energy, which is expected to result in lower fuel consumption and reduced generator operation and maintenance costs | 1 164.4 | 1 164.4 | – | – | 1 164.4 | – | 1 164.4 |
|  | (b) Further reduction of approximately 1,726 tons of CO2 emissions | 168.5 | 168.5 | – | – | 168.5 | – | 168.5 |
|  | (c) Cost avoidance through the non-acquisition of prefabricated facilities, accommodation and refrigeration equipment, generators and electrical equipment, construction materials and field defence supplies | 1 245.9 | 1 245.9 | – | – | 1 245.9 | – | 1 245.9 |
|  | (d) Introduction of a diesel-hybrid solar power system with integrated battery storage in Kaga Bandoro, featuring a total installed capacity of 400 kWp | – | – | – | – | – | 297.0 | 297.0 |
|  | (e) The drilling of 10 boreholes to provide bulk water supply, reducing reliance on bottled water at various Mission locations | – | – | – | – | – | 421.0 | 421.0 |
| Ground transportation | (a) Adoption of a 10,000 km maintenance schedule, in place of the current 5,000 km schedule, limited to light passenger vehicles in Bangui, with a view to reducing maintenance frequency and spare parts consumption | – | – | – | – | – | 150.0 | 150.0 |
|  | (b) Reduction in the use of spare parts as a result of the extension of the maintenance schedule | – | – | – | – | – | 179.5 | 179.5 |
|  | (c) Acquisition of 22 single-cabin utility pick-up trucks in place of sport utility vehicles to improve operational mobility in Bangui | – | – | – | – | – | 281.6 | 281.6 |
|  | (d) Limitation of vehicle painting exclusively to accident-related repairs, excluding any routine or aesthetic refinishing | – | – | – | – | – | 5.8 | 5.8 |
| Air operations | Enhancement of air asset utilization for improved response to medical emergencies, enabling more efficient operations through the effective use of existing assets | – | – | – | – | – | 732.5 | 732.5 |
| Communications and information technology | Replacement of the high-cost Cisco Webex Room Panorama 85 with a lower-cost, functionally equivalent Smart TV + Cisco Room Kit EQ PTZ set-up for high-quality video and audio conferencing | – | – | – | – | – | 459.6 | 459.6 |
| Total |  | 2 578.8 | 2 578.8 | – | – | 2 578.8 | 154 998.8 | 157 577.6 |
| Approved budget for 2025/26 |  |  |  |  |  |  | 1 174 132.0 |  |
| 2026/27 estimated efficiencies as a percentage of the approved budget for 2025/26 |  |  |  |  |  |  | 13.2 |  |

D.	Unencumbered balance

69.	The unencumbered balance for the periods from 2022/23 to 2024/25, as reported in the relevant performance reports, is as follows:

Trend of the unencumbered balance

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 2 128.7 | 15 773.9 | 14 460.5 |
| Civilian personnel | 5 835.5 | (11 233.8) | (14 219.9) |
| Operational costs | (7 478.4) | (1 962.9) | 25 110.0 |
| Total | 485.8 | 2 577.2 | 25 350.6 |

E.	Cancellation of prior-period obligations

70.	Prior-period obligations for the periods from 2022/23 to 2024/25 were cancelled as follows:

Trend of the cancellation of prior-period obligations

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 12 610.2 | 8 461.6 | 3 923.2 |
| Civilian personnel | 513.5 | 143.7 | (958.5) |
| Operational costs | 7 376.6 | 5 332.1 | 6 470.8 |
| Total | 20 500.3 | 13 937.4 | 9 435.5 |

Note: The amounts represent the total obligations that were cancelled at the end of the 12-month period following the end of the budget period in respect of goods supplied and services rendered in the budget period, and at the end of an additional period of four years in respect of obligations to troop- and police-contributing countries.

F.	Other revenue and adjustments, and borrowing

1.	Other revenue and adjustments

(Thousands of United States dollars)

| Category | Amount |
| --- | --- |
| Investment revenue | 11 502.2 |
| Other/miscellaneous revenuea | 811.5 |
| Voluntary contributions in cash | – |
| Prior-period adjustments | – |
| Cancellation of prior-period obligations | 9 435.5 |
| Total | 21 749.2 |

a	Breakdown of other/miscellaneous revenue: refund of prior-period expenses ($243,500); and other revenue ($568,000).

71.	Credits comprising the unencumbered balances, other revenue and the cancellation of prior-period obligations reduce the assessed contributions owed by Member States in the following financial year. The credit for the 2024/25 period for overall peacekeeping operations amounts to $335.5 million, including the support entities and the United Nations Multidimensional Integrated Stabilization Mission in Mali. In the current financial situation, offsetting this large amount of credit against a future assessment for the 2026/27 period will reduce the collection and undermine the ability of peacekeeping operations to fully implement their mandates. Accordingly, the Secretary-General proposes that the General Assembly approve that the credits in respect of the financial period 2024/25 be placed in a reserve that would be used in the event that collections are insufficient to enable the implementation of those mandates; and allow Member States to apply their share towards current or future dues once the Assembly determines that the liquidity situation has sufficiently improved. This proposal is explained in more detail in the peacekeeping overview report.

2.	Borrowing

72.	MINUSCA did not receive loans from other peacekeeping missions in the reporting period.

G.	Vacancy factors

73.	The cost estimates for the period from 1 July 2026 to 30 June 2027 take into account the vacancy factors outlined in the table below. The table also summarizes, by category, the actual rates in the periods from 2022/23 to 2024/25, as well as the approved and current rates for the 2025/26 period.

(Percentage)

|  | Actual |  |  | 2025/26 approved | Actual as at 31 December 2025 | Actual average, January to December 2025 | 2026/27 proposed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Category | 2022/23 | 2023/24 | 2024/25 |  |  |  |  |
| Military and police personnel |  |  |  |  |  |  |  |
| Military observers | 4.5 | 2.6 | 1.9 | 0.0 | 27.7 | 7.1 | 90.3 |
| Military contingents | 7.0 | 2.4 | 2.4 | 2.1 | 11.8 | 3.9 | 23.7 |
| United Nations police | 7.5 | 3.2 | 1.5 | 0.8 | 31.8 | 7.5 | 24.4 |
| Formed police units | 6.0 | 0.3 | 0.1 | 0.0 | 22.7 | 3.5 | 24.5 |
| Civilian personnel |  |  |  |  |  |  |  |
| International staff | 16.0 | 12.2 | 8.7 | 8.9 | 13.6 | 10.1 | 4.0 |
| National staff |  |  |  |  |  |  |  |
| National Professional Officer | 8.8 | 7.0 | 5.2 | 6.1 | 7.8 | 6.0 | 6.0 |
| National General Service staff | 4.6 | 6.9 | 7.2 | 7.1 | 10.6 | 8.2 | 8.2 |
| United Nations Volunteers |  |  |  |  |  |  |  |
| International | 3.3 | 5.2 | 5.2 | 5.2 | 21.4 | 10.5 | 3.0 |
| National | 8.0 | 13.2 | 12.7 | 13.0 | 16.4 | 14.5 | 14.5 |
| Temporary positionsa |  |  |  |  |  |  |  |
| International staff | 38.7 | 16.7 | 23.3 | 6.7 | 6.7 | 23.3 | 0.0 |
| National General Service staff | – | 18.2 | 9.1 | 9.1 | 90.9 | 45.5 | 90.0 |
| Government-provided personnel | 4.6 | 2.8 | 1.9 | 0.9 | 12.0 | 2.8 | 63.0 |

a	Funded under general temporary assistance.

74.	The vacancy factors take into account the high number of abolishments included in the proposed budget for 2026/27. Accordingly, the proposed vacancy rates for civilian personnel categories with abolishments were estimated using the total number of vacant posts and positions as at 31 December 2025, net of the number of posts and positions proposed for abolishment. For categories without proposed abolishments, the standard policy guidance was applied, using either the 12-month average vacancy rate from January to December 2025 or the actual vacancy rate as at 31 December 2025. For military and police personnel, the vacancy factors reflect their planned deployment during the 2026/27 period. This approach ensures that vacancy rates are based on, to the extent possible, the actual data while maintaining consistency across the proposed budgets. A vacancy rate of 50 per cent has been applied in calculating the costs of the proposed establishment and reassignment of posts.

H.	Analysis of requirements for air operations

75.	The flight-hour utilization rates for the periods from 2022/23 to 2024/25, the approved number of flight hours for the 2024/25 and 2025/26 periods, the proposed number for the 2026/27 period and the number of flight hours calculated on the basis of the new policy guidance are as follows:

|  | Flight-hour utilization (percentage) |  |  |  | Flight hours |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual |  |  | Average (2022/23 to 2024/25) |  | Approved |  |  | Policy |  | Proposed |  |
|  | 2022/23 | 2023/24 | 2024/25 |  |  | 2024/25 | 2025/26 |  | 2026/27 |  | 2026/27 | Variance |
| Aircraft type | (1) | (2) | (3) | (4) |  | (5) | (6) |  | (7) | (8) |  | (9)=(8)-(6) |
| Fixed-wing | 83.9 | 91.4 | 86.9 | 87.5 | 6 938 |  | 6 077 | 6 069 |  | 6 119 |  | 42 |
| Helicopters | 86.7 | 77.0 | 76.5 | 79.4 | 7 698 |  | 5 980 | 6 113 |  | 5 948 |  | (32) |
| Total |  |  |  |  | 14 636 |  | 12 057 | 12 182 |  | 12 067 |  | 10 |

76.	The Mission will deploy a total of 20 aircraft (7 fixed-wing aircraft and 13 rotary-wing aircraft) across various mission locations to support the transportation of passengers and cargo; intelligence, surveillance and reconnaissance operations; troop rotations; insertions and extractions; cargo resupply; and medical evacuation (medical and casualty evacuations).

77.	In the 2025/26 period, the Mission included a total of 1,678 flight hours for electoral support. As described in the planning assumptions for the 2026/27 period, after the successful conduct of the combined presidential, legislative, regional and municipal elections on 28 December 2025, MINUSCA began to adjust its footprint and posture in line with its mandate under Security Council resolution 2800 (2025). In the post-election context, MINUSCA proposes to repurpose the former 1,678 electoral flight hours to strengthen support for the Armed Forces of the Central African Republic and the internal security forces, given that the Mission is initiating a phase of consolidation, reconfiguration and transition.

I.	Programmatic activities

78.	The estimated resource requirements for programmatic activities for the period from 1 July 2026 to 30 June 2027, and the approved resources and performance during the 2024/25 period, are as follows:

(Thousands of United States dollars)

| Category | 2024/25 apportionment | 2024/25 expenditure | 2026/27 cost estimates | Related expected accomplishment |
| --- | --- | --- | --- | --- |
| Mine detection and mine clearing services | 8 387.0 | 7 721.8 | 8 270.0 | 1.1, 2.1 |
| Rule of law and security sector reform | 6 862.9 | 6 469.7 | 7 550.3 | 1.1, 1.4, 2.1, 3.1 |
| Promotion and protection of human rights | 1 607.7 | 1 528.1 | 1 799.2 | 1.1, 1.4, 2.1, 3.1 |
| Community stabilization projects | 750.0 | 689.7 | 736.0 | 1.1, 1.2, 2.2, 3.1 |
| Peace consolidation | 602.5 | 1 751.6 | 600.0 | 1.1, 1.2 |
| Confidence-building and trust in security institutions | 1 300.0 | 1 440.1 | 1 658.0 | 3.1 |
| Community violence reduction | 8 400.0 | 8 399.5 | 8 500.0 | 1.2 |
| Disarmament, demobilization, reintegration and repatriation | 500.0 | 144.3 | 500.0 | 1.1 |
| Women and peace and security | 200.0 | 239.3 | 175.0 | 1.2, 3.1 |
| Small arms and light weapons management | 100.0 | 100.0 | – | 1.2 |
| Total | 28 710.1 | 28 484.1 | 29 788.5 |  |

79.	Detailed information on programmatic activities undertaken during the 2024/25 period and those planned for the 2026/27 period is provided in the supplementary information. The associated resource requirements for the performance and budget periods correspond to projects implemented by the Mission in support of mandate implementation, as reflected in the Mission’s results-based budgeting framework.

J.	Quick-impact projects

80.	The estimated resource requirements for quick-impact projects for the period from 1 July 2026 to 30 June 2027, compared with previous periods, are as follows:

(Thousands of United States dollars)

| Period | Amount | Number of projects |
| --- | --- | --- |
| 1 July 2024 to 30 June 2025 (actual) | 3 580.4 | 90 |
| 1 July 2025 to 30 June 2026 (approved) | 4 000.0 | 110 |
| 1 July 2026 to 30 June 2027 (proposed) | 4 000.0 | 110 |

81.	The proposed resource requirements for the 2026/27 period will amount to $4,000,000.

82.	Through quick-impact projects, the Mission will continue to create an enabling environment that strengthens peace, security and State authority across the Central African Republic. Quick-impact projects will enhance the Mission’s presence, build trust with local communities and support political, peace and reconciliation processes by delivering basic social services, promoting socioeconomic empowerment initiatives for women, young people and vulnerable populations and facilitating the reintegration of ex-combatants. The Mission will also support the sustainable restoration of State authority by rehabilitating public administrative infrastructure, providing equipment, strengthening local governance, promoting human rights, enhancing the justice system and supporting security deployments. Furthermore, quick-impact projects will improve security conditions and civilian protection by increasing the mobility and presence of national and MINUSCA security forces, reinforcing early warning and communication systems, restoring freedom of movement, mitigating local conflicts and facilitating humanitarian access. All projects will be implemented in coordination with national authorities, United Nations agencies, humanitarian organizations and local communities, ensuring grass-roots participation, local ownership and sustainable impact across the seven proposed regions.

III.	Analysis of variances

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Military observers | ($772.8) | (9.4%) | ($7 869.5) |  | (88.5%) |

83.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) a higher actual rate of mission subsistence allowance, based on revised rates effective 1 January 2025, compared with the rate in the approved budget; and (b) a lower actual average vacancy rate of 1.9 per cent compared with 2.6 per cent in the approved budget.

84.	For the 2026/27 period, the reduced requirements are attributable primarily to the application of a higher vacancy rate of 90.3 per cent compared with 0 per cent in the approved budget, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Military contingents | $13 635.6 | 2.6% | ($101 296.8) |  | (19.8%) |

85.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) lower contingent-owned equipment costs resulting from the repatriation of one heavy transport company and the non-deployment of certain major equipment, particularly explosive ordnance disposal equipment; (b) lower rations costs due to (i) a lower actual average ceiling individual daily rate compared with the budgeted levels; and (ii) lower actual within-mission transportation costs through the use of MINUSCA air assets instead of contractor-provided assets; (c) the delayed rotation of one heavy transport company due to challenges in identifying a replacement unit; and (d) the partial rotation of one infantry battalion due to non-clearance of incoming troops.

86.	The reduced requirements were offset in part by: (a) a lower actual average adjustment against the standard reimbursement for the deployment of non-functional or absent contingent-owned major equipment compared with the adjustment in the approved budget; (b) a lower actual average vacancy rate of 2.4 per cent compared with 2.9 per cent in the approved budget; (c) higher freight costs resulting from the repatriation of one heavy transport company; and (d) a higher actual rate of mission subsistence allowance, based on revised rates effective 1 January 2025, compared with the rate in the approved budget.

87.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) the application of a higher vacancy rate of 23.7 per cent compared with the 2.1 per cent rate applied in the approved budget, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies, based on a review of operational requirements and workload distribution and implemented mainly through adjustments to planned deployment, while maintaining the delivery of core mandated activities; and (b) the reduction in authorized military strength, as decided by the Security Council in its resolution 2800 (2025).

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| United Nations police | ($1 562.4) | (5.0%) | ($7 690.2) |  | (22.6%) |

88.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) a higher actual rate of mission subsistence allowance, based on revised rates effective 1 January 2025, compared with the rate in the approved budget; and (b) a lower actual average vacancy rate of 1.5 per cent compared with 3.8 per cent in the approved budget.

89.	For the 2026/27 period, the reduced requirements are attributable primarily to the application of a higher vacancy rate of 24.4 per cent compared with 0.8 per cent in the approved budget, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Formed police units | $3 160.1 | 3.8% | ($18 350.5) |  | (22.4%) |

90.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) lower rations costs owing to (i) a lower actual average ceiling individual daily rate and average strength compared with the budgeted levels; and (ii) lower within-mission transportation costs through the use of MINUSCA air assets instead of contractor-provided assets; (b) the increased non-functionality of major equipment; and (c) the postponement of the rotation of one unit’s contingent-owned equipment.

91.	For the 2026/27 period, the reduced requirements are attributable primarily to the application of a higher vacancy rate of 24.5 per cent compared with 0 per cent in the approved budget, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| International staff | ($13 035.8) | (7.6%) | ($3 735.6) |  | (2.0%) |

92.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) a lower actual average vacancy rate of 8.7 per cent compared with 12.5 per cent in the approved budget; and (b) higher actual common staff costs as a percentage of actual salary costs compared with the budgeted percentage.

93.	For the 2026/27 period, the reduced requirements are attributable primarily to the proposed abolishment of 74 international posts, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to the staffing structure, while maintaining the delivery of core mandated activities.

94.	The reduced requirements are offset in part by the application of: (a) a lower vacancy rate of 4.0 per cent compared with 8.9 per cent in the approved budget; and (b) higher revised salary rates.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| National Professional Officer | ($1 461.8) | (13.1%) | $522.1 |  | 4.3% |

95.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) the revised salary scale for national staff, effective 1 September 2023 and promulgated in March 2024, reflecting the outcome of a comprehensive salary survey, for which no provision had been included in the approved budget; and (b) a lower actual average vacancy rate of 5.2 per cent compared with 7.8 per cent in the approved budget.

96.	For the 2026/27 period, the increased requirements are attributable primarily to the application of an exchange rate of 566.066 CFA francs to the United States dollar, compared with 621.642 CFA francs in the approved budget. The increased requirements are offset in part by lower common staff cost rates, based on historical trends, compared with the rates in the approved budget.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| National General Service staff | ($900.7) | (4.7%) | $271.9 |  | 1.4% |

97.	For the 2024/25 period, the increased requirements were attributable primarily to the revised salary scale for national staff, effective 1 September 2023 and promulgated in March 2024, for which no provision had been included in the approved budget. The increased requirements were offset in part by a higher actual average vacancy rate of 7.2 per cent compared with 5.9 per cent in the approved budget.

98.	For the 2026/27 period, the increased requirements are attributable primarily to the application of an exchange rate of 566.066 CFA francs to the United States dollar compared with 621.642 CFA francs in the approved budget.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| United Nations Volunteers | $919.0 | 4.5% | ($3 124.5) |  | (15.0%) |

99.	For the 2024/25 period, the reduced requirements were attributable primarily to a higher actual average vacancy rate of 5.2 per cent for international United Nations Volunteers compared with 2.8 per cent in the approved budget, as well as fewer international United Nations Volunteers eligible for settling-in grants, pre-departure and repatriation entitlements and rest and recuperation compared with the estimates in the approved budget.

100.	For the 2026/27 period, the reduced requirements are attributable primarily to the proposed abolishment of 47 international United Nations Volunteers, including: (a) 37 election-related positions as a result of the scheduled completion of the Mission’s electoral mandate by 30 June 2026; and (b) 10 other positions reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to the staffing structure, while maintaining the delivery of core mandated activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| General temporary assistance | $396.5 | 5.3% | ($7 645.1) |  | (89.5%) |

101.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) a higher actual average vacancy rate of 23.3 per cent for temporary international staff compared with 13.3 per cent in the approved budget; and (b) lower actual common staff costs for temporary international positions, as a percentage of actual salary costs, compared with the budgeted percentage.

102.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) the proposed abolishment of 30 election-related positions (29 international and one national) as a result of the scheduled completion of the Mission’s electoral mandate by 30 June 2026; and (b) the application of a higher vacancy rate of 90.0 per cent for national temporary positions compared with 9.1 per cent in the approved budget.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Government-provided personnel | ($137.1) | (2.3%) | ($3 895.4) |  | (62.0%) |

103.	For the 2024/25 period, the increased requirements were attributable primarily to a higher actual rate of mission subsistence allowance, based on revised rates effective 1 January 2025, compared with the rates in the approved budget.

104.	For the 2026/27 period, the reduced requirements are attributable primarily to the application of a higher vacancy rate of 63.0 per cent compared with 0.9 per cent in the approved budget, reflecting efficiency measures aimed at enhancing effectiveness through organizational optimization, functional streamlining and allocative efficiencies. These measures, based on a review of operational requirements and workload distribution, are implemented mainly through adjustments to planned deployments, while maintaining the delivery of core mandated activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Consultants and consulting services | $360.6 | 54.2% | ($89.9) |  | (17.1%) |

105.	For the 2024/25 period, the reduced requirements were attributable primarily to a decrease in the engagement of consultants compared with the estimates in the approved budget, due to the cancellation or postponement of several planned activities in which individual consultants had been scheduled to participate, as a result of: (a) liquidity constraints; (b) the security situation in the country; and (c) shifting government priorities.

106.	For the 2026/27 period, the reduced requirements are attributable primarily to the anticipated decrease in the engagement of individual consultants for expert support in favour of greater use of in-house capacities and expertise.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Official travel | $358.3 | 9.9% | $1 598.7 |  | 44.4% |

107.	For the 2024/25 period, the reduced requirements were attributable primarily to a reduction in non-training travel outside the mission area, as well as a reduction in trainer travel and on-site training sessions, compared with the estimates in the approved budget, owing to liquidity constraints.

108.	For the 2026/27 period, the increased requirements are attributable primarily to additional travel planned to support the transport and delivery of significant quantities of equipment and supplies from field locations scheduled for closure as part of the consolidation and reconfiguration of MINUSCA in the post-election context. These adjustments, undertaken in line with paragraph 48 of Security Council resolution 2800 (2025) and in view of persistent liquidity constraints, are intended to refine the Mission’s footprint, seek efficiencies and strengthen the prioritization of critical mandate activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Facilities and infrastructure | $1 299.9 | 1.7% | $4 849.4 |  | 6.2% |

109.	For the 2024/25 period, the reduced requirements were attributable primarily to lower actual costs for: (a) generators and electrical equipment, due to the cancellation of two planned renewable energy projects and the availability of stock from prior periods, as well as internal sourcing through the United Nations Logistics Base; and (b) prefabricated facilities, accommodation and refrigeration equipment, due to liquidity constraints and the non-acquisition of several prefabricated units, security containers, bridges and tents, including for support for the Armed Forces of the Central African Republic.

110.	The reduced requirements were offset in part by higher actual costs for: (a) security reimbursements for individual uniformed personnel, due to lower actual average vacancy rates for military and police components; (b) construction materials and field defence supplies, due to the acquisition of additional cement, raw materials and other hardware to support mission-wide projects; and (c) construction, alteration, renovation and major maintenance, due to the implementation of priority projects not provided for in the approved budget, including the installation of membrane-covered structures and aviation hangars in field locations and the establishment of boreholes to support the Armed Forces of the Central African Republic.

111.	For the 2026/27 period, the increased requirements are attributable primarily to additional construction, alteration, renovation and major maintenance works, the planned acquisition of prefabricated facilities, accommodation and refrigeration equipment, and the application of an exchange rate of 566.066 CFA francs to the United States dollar, compared with 621.642 CFA francs in the approved budget. These measures support the Mission’s consolidation and reconfiguration in the post-election context and, undertaken in line with paragraph 48 of Security Council resolution 2800 (2025) and in view of persistent liquidity constraints, are intended to refine the Mission’s footprint, enhance efficiencies and strengthen the prioritization of critical mandate activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Ground transportation | $505.0 | 2.6% | ($326.1) |  | (1.7%) |

112.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) a lower actual volume of 6.4 million litres of fuel for vehicles compared with 7.1 million litres in the approved budget, due to a lower actual number of roadworthy vehicles and the implementation of control measures for fuel distribution; (b) the non-mobilization of additional fuel distribution points, due to liquidity constraints; and (c) a lower actual average price of $1.680 per litre of fuel compared with $1.686 per litre in the approved budget.

113.	The reduced requirements were offset in part by the acquisition of four additional aviation fire trucks to address critical air safety risks at four field locations, as well as one passenger bus to replace an unserviceable unit, for which no provision had been included in the approved budget.

114.	For the 2026/27 period, the reduced requirements are attributable primarily to (a) the rationalization of the Mission’s existing fleet and the postponement of planned vehicle replacements and write-offs; and (b) the adoption of manufacturer-recommended maintenance intervals, in lieu of the United Nations standard for severe operating conditions, for light passenger vehicles in Bangui.

115.	The reduced requirements are offset in part by: (a) a higher anticipated average cost of $1.877 per litre compared with $1.741 in the approved budget; and (b) higher operational, maintenance and mobilization fees to support the planned mobilization of fuel in Sector East.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Air operations | $19 827.2 | 21.1% | ($8 906.8) |  | (10.4%) |

116.	For the 2024/25 period, the reduced requirements were attributable primarily to lower actual costs for: (a) the rental and operation of fixed-wing aircraft and helicopters, due to fewer flight hours operated by both types of aircraft compared with the hours in the approved budget, as a result of the partial availability and delayed deployment of a number of helicopters, lower utilization of the air ambulance, the unavailability of one fixed-wing aircraft for slightly over a month, a lower number of support flights for the deployment of the Armed Forces of the Central African Republic and the postponement of provisional electoral data list deployment to the 2025/26 period; and (b) petrol, oil and lubricants, due to the lower actual volume of 9.9 million litres of aviation fuel, acquired at the lower actual average price of $1.329 per litre, compared with the budgeted volume of 11.7 million litres at an average price of $1.483 per litre, and the non-mobilization of an additional fuel storage facility due to liquidity constraints.

117.	The reduced requirements were offset in part by higher costs for services, resulting from demobilization and de-positioning costs associated with the termination of the commercial contract for the unmanned aerial systems, for which no provision had been included in the approved budget.

118.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) the anticipated lower costs for two fixed-wing aircraft (DHC-8-400 and DHC-8-311), resulting from changes in contractual arrangements, which affect both fixed costs and cost per flight hour, compared with the estimates in the approved budget; (b) the anticipated lower costs for one MI-17 helicopter, resulting from changes in contractual arrangements, which affect the cost per flight hour, compared with the estimates in the approved budget; (c) the lower anticipated consumption of 9.7 million litres of aviation fuel at an average cost of $1.330 per litre compared with 10.9 million litres in the approved budget, as a result of the scheduled completion of the Mission’s electoral mandate by 30 June 2026; and (d) the anticipated lower expenditure for landing fees and ground handling charges, based on historical expenditure patterns.

|  | 2024/25 variance |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Marine operations | ($565.2) | (112.8%) |  |  |  |

119.	For the 2024/25 period, the increased requirements were attributable primarily to the acquisition of additional sea containers to ensure the timely and secure transportation of infrastructure materials and prefabricated structures to designated field locations.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Communications and information technology | $5 666.6 | 14.3% | ($1 641.9) |  | (4.1%) |

120.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) lower-than-anticipated costs for public information and publication services, due to the scaling down of production and outreach activities as a result of liquidity constraints; (b) the non-acquisition of communications and information technology equipment, due to the transfer of equipment from MINUSMA and other available resources; (c) lower actual costs for spare parts, due to effective preventive maintenance, the re-use of existing components and the non-acquisition of satellite imagery; and (d) lower actual costs for telecommunications and network services, resulting from the partial implementation of bandwidth upgrades, lower subscription cost and transponder rates, and reduced satellite radio streaming due to liquidity constraints.

121.	For the 2026/27 period, the reduced requirements are attributable primarily to lower anticipated expenditures across various areas, including: (a) promotional and outreach activities, following the scheduled completion of the Mission’s electoral mandate by 30 June 2026; (b) the lower rates for centrally managed information and communications technology services and the cancellation of the long-term evolution (LTE) expansion to Bambari and Ndélé; and (c) maintenance and technical support, reflecting the planned termination of specialized server room contracts and the transition of videoconferencing and Terrestrial Trunked Radio (TETRA) services to the United Nations Logistics Base at a reduced cost.

122.	The reduced requirements are offset in part by increased requirements, related primarily to the strengthening of the Mission’s information technology and communications infrastructure, including enhancements to mission-wide power protection, connectivity and communications systems, as well as the planned deployment of new technologies to improve operational resilience and support critical mission activities.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Medical | $629.3 | 30.7% | ($33.7) |  | (1.3%) |

123.	For the 2024/25 period, the reduced requirements were attributable primarily to the availability of sufficient inventory stocks, which resulted in the acquisition of fewer vaccines, pharmaceuticals and patient care products; the non-acquisition of first-aid kits, in line with a Headquarters directive restricting pharmaceutical procurement to established contracts; and the deferral of acquisition of selected medical and hygiene supplies owing to liquidity constraints.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Other supplies, services and equipment | ($3 391.3) | (6.6%) | $4 867.3 |  | 10.1% |

124.	For the 2024/25 period, the increased requirements were attributable primarily to: (a) higher actual costs for freight and related services, due to the unplanned transportation of materials, equipment and prefabricated structures to improve warehouse conditions in field locations, as well as additional in-land cargo transport to field locations; and (b) administrative and management fees payable under the agreement with the United Nations Office for Project Services for the management of individual contractual personnel, for which no provision was included in the approved budget.

125.	The increased requirements were offset in part by lower costs for: (a) mine detection and mine clearing services, due to the cancellation of various planned pre-deployment training sessions, weapons and ammunition management infrastructure activities, and training sessions, due to liquidity constraints; (b) training fees, supplies and services, owing to lower-than-anticipated trainer travel and limited on-site training sessions due to liquidity constraints; and (c) bank charges, owing to delays in establishing two branches.

126.	For the 2026/27 period, the increased requirements are attributable primarily to higher costs associated with the implementation of paragraph 48 of Security Council resolution 2800 (2025), including: (a) freight costs related to the transport of additional quantities of equipment and supplies from field locations scheduled for closure as part of the consolidation and reconfiguration of MINUSCA in the post-election context (internal movement of goods); and (b) the provision of combat ration packs for the Armed Forces of the Central African Republic for consumption during joint operations.

|  | 2024/25 variance |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Quick-impact projects | $419.6 | 10.5% |  |  |  |

127.	For the 2024/25 period, the reduced requirements were attributable primarily to the lower actual number of projects implemented compared with the number of projects in the approved in the budget, due to liquidity constraints.

IV.	Actions to be taken by the General Assembly

128.	The actions to be taken by the General Assembly in connection with the financing of the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic are:

(a)	To take note of the unencumbered balance of $25,350,600 with respect to the period from 1 July 2024 to 30 June 2025;

(b)	To take note of other revenue for the period ended 30 June 2025 amounting to $21,749,200 from investment revenue ($11,502,200), other/miscellaneous revenue ($811,500) and the cancellation of prior-period obligations ($9,435,500);

(c)	To approve the apportionment of the amount of $47,099,800 among Member States in accordance with the applicable scale of assessments for 2025 and to place such apportioned amount in a reserve that would be used in the event that collections are insufficient to enable the full, efficient and effective implementation of mandates;

(d)	To allow Member States to apply their share of the amount apportioned in subparagraph (c) above towards current or future dues once the General Assembly determines that the liquidity situation has improved sufficiently to allow such application;

(e)	To appropriate the amount of $1,021,635,400 for the maintenance of the Mission for the 12-month period from 1 July 2026 to 30 June 2027;

(f)	To assess the amount in subparagraph (e) above at a monthly rate of $85,136,284 should the Security Council decide to continue the mandate of the Mission.

V.	Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/302, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly

A.	General Assembly

Cross-cutting issues

(Resolution 76/274)

| Decision/request | Action taken to implement decision/request |
| --- | --- |
| Requests the Secretary-General to improve comprehensive oversight of the activities of peacekeeping missions and implement the recommendations of relevant oversight bodies in this regard to avoid deficiencies in management and related economic losses, with the aim of ensuring full compliance with the Financial Regulations and Rules of the United Nations (para. 17). | As at 31 December 2025, 224 of the 299 recommendations (75 per cent) issued by the Office of Internal Oversight Services and 42 of the 65 recommendations (65 per cent) issued by the Board of Auditors were implemented. Regular follow-ups are undertaken to ensure the timely closure of the remaining recommendations. |
| Requests that future budget proposals demonstrate the scalability of mission support components, including their staffing and operational costs, be proportionate in relation to the changing level of other mission components and include standard indicators (para. 27). | The mission support ratio (the total number of mission support and security personnel per 1,000 total mission personnel) in the 2025/26 period is 51.5, lower than the figure of 59.6 for the 2020/21 period. The Mission will continue to take mission support scalability into consideration in future budget reports. |
| Requests the Secretary-General to consider options for greater nationalization of functions when formulating budget submissions, commensurate with mission mandates and requirements where applicable (para. 34). | In response to the General Assembly’s request to consider options for greater nationalization of functions, MINUSCA continues to advance a structured approach to the nationalization of suitable functions, commensurate with mandate requirements and operational needs. In this regard, the Mission is implementing a 2024–2028 nationalization strategy that provides for the progressive transition of selected international functions to national positions, including through the conversion of vacant posts, natural attrition and targeted capacity-building initiatives. These measures are designed to maintain operational continuity, enhance cost efficiency and support the sustainable development of national capacities, while informing the formulation of budget submissions, as applicable. For the 2026/27 period, it is proposed that a victims’ rights function be nationalized in the Office of the Deputy Special Representative of the Secretary-General (Resident Coordinator/ Humanitarian Coordinator). |
| Recalls the provisions of section XVIII of its resolution 61/276, recognizes the important role played by quick-impact projects in establishing and building confidence in missions, further recognizes the importance of conducting assessments of the quick-impact projects regularly, on their needs and impact as required in resolution 61/276, requests the Secretary-General to include the conducted assessments in his next reports, and also requests the Secretary-General to enhance their impact (para. 82). | In line with General Assembly resolution 61/276, quick-impact projects continue to play a key role in building confidence between local communities, national authorities and the Mission, and in supporting stabilization and peacebuilding efforts in the Central African Republic. The Mission conducts regular assessments of quick-impact projects to evaluate their relevance, outcomes and impact, ensuring continued alignment with mandate priorities and community needs. The findings of these assessments have been reflected in reports of the Secretary-General, in accordance with the Assembly’s request, and demonstrate the tangible contribution of quick-impact projects to local stabilization and early peace dividends. On the basis of assessment results, MINUSCA has taken steps to enhance the impact of quick-impact projects by prioritizing projects that deliver visible and immediate benefits, including the rehabilitation and construction of essential infrastructure such as roads, administrative buildings, schools and health facilities. These interventions have improved access to basic services, strengthened community resilience and supported the re-establishment of State authority, thereby reinforcing confidence in the Mission and its mandate. |

B.	Advisory Committee on Administrative and Budgetary Questions

Financing of the United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic

(A/79/724/Add.13)

| Request/recommendation | Action taken to implement request/recommendation |
| --- | --- |
| The Advisory Committee trusts that information on expenditure related to electoral support during the 2024/25 period, taking into account the aforementioned revised timelines, will be provided to the General Assembly at the time of its consideration of the present report and in the next budget proposal (para. 17). | Election-related expenditure during the 2024/25 period amounted to $12.0 million. |
| The Advisory Committee notes the proposed restructuring of the MINUSCA mission support structure and trusts that there will be a period of stability in that regard. The Committee trusts that updated information on any efficiencies and lessons learned from the exercise will be reflected in the next programme budget submission (para. 29). | The recent restructuring of the Mission Support Division of MINUSCA has improved efficiency and operational effectiveness and is intended to provide a stable support structure going forward. The Mission is monitoring the new configuration to consolidate gains, ensure continuity and avoid further structural changes except where operationally necessary. Initial efficiencies and lessons learned are already emerging. For example, the integration of occupational health and safety under the services delivery pillar has facilitated more effective resolution of safety-related issues through improved alignment with the Medical Services Section. Similarly, the repositioning of the Claims Unit within the supply chain management pillar has streamlined access to critical data, as that pillar oversees acquisitions, property management, vendors and claims. Placing the Environmental Unit directly under the Director of Mission Support has elevated its strategic role, strengthening environmental compliance across the Mission. These revised reporting lines have supported improved planning and project implementation. In addition, the relocation of the Conference and Translation Unit to the Integrated Mission Training Cell has enhanced productivity, visibility, innovation and day-to-day operations, while also promoting multilingualism through the development of lexical resources to support learning and language proficiency. The Mission will continue to assess the impact of the restructuring, and updated information on efficiencies achieved and lessons learned will be reflected in the next programme budget submission. |
| The Advisory Committee trusts that information on the status of vacant posts, as well as on the impact of the liquidity situation on projected hirings, will be provided to the General Assembly at the time of its consideration of the present report and in the next budget submission (para. 30). | The trend in vacancy rates in MINUSCA between July and December 2025 is as follows: Period; International; National. July 2025; 9%; 8%. August 2025; 10%; 8%. September 2025; 11%; 8%. October 2025; 10%; 8%. November 2025; 12%; 9%. December 2025; 14%; 10%. During this period, the Mission experienced a steady increase in vacancy rates, in particular among international staff. The prevailing liquidity situation has constrained the Mission’s ability to proceed with projected recruitments, resulting in delays in filling critical posts and associated impacts on operational delivery. The Mission continues to closely monitor staffing levels and recruitment pipelines, and updated information on vacancy rates and the impact of liquidity constraints on projected hirings will be reflected in the next budget submission. |
| The Advisory Committee recalls paragraph 34 of General Assembly resolution 76/274 (see also A/78/744, para. 37) and is of the view that more efforts should be made to nationalize functions commensurate with mission mandates and requirements, wherever appropriate. The Committee underscores the importance of building national capacity and recommends that the Assembly request MINUSCA to enhance its efforts to implement the civilian staffing review recommendation on further nationalizations and to include proposals in that regard in the next budget proposals (para. 33). | In response to the General Assembly’s request to explore options for greater nationalization of functions, MINUSCA continues to implement a structured approach to the nationalization of suitable functions, in line with mandate requirements and operational needs. The Mission is implementing a 2024–2028 nationalization strategy that provides for the progressive transition of selected international functions to national positions, through the conversion of vacant posts, natural attrition and targeted capacity-building initiatives. These measures are intended to maintain operational continuity, enhance cost efficiency and strengthen the sustainable development of national capacities, while informing the formulation of future budget submissions. For the 2026/27 period, it is proposed that a victims’ rights function be nationalized in the Office of the Deputy Special Representative of the Secretary-General (Resident Coordinator/Humanitarian Coordinator). Due to the ongoing liquidity constraints, which have led to a temporary freeze on recruitment, the implementation of certain nationalization measures has been postponed. Nevertheless, it is proposed that 74 international positions be abolished, thereby enhancing cost efficiency. MINUSCA intends to resume implementation of the nationalization strategy in the 2027/28 fiscal year, at which time measurable targets and milestones will be established and reflected in future budget proposals. |
| The Advisory Committee trusts that further information, including a cost comparison and related lessons learned, of utilizing hard-walled buildings instead of prefabricated structures will be included in the next budget proposal. The Committee emphasizes the importance of ensuring the integration of locally sourced and manufactured materials, as well as local labour and expertise, when possible, and trusts that updates thereon will be provided in future budget proposals (para. 40). | The Mission conducted an initial cost comparison between prefabricated buildings and hard-walled structures. The analysis indicates that the annual cost of operating a six-module prefabricated building (1,008 m²) is approximately $11,377, whereas a hard-walled structure of comparable size costs about $5,600 per year, representing a cost reduction of nearly 51 per cent. From an operational perspective, prefabricated structures generate additional costs owing to international import requirements, extended timelines for fabrication and delivery to the Central African Republic, and accelerated deterioration resulting from harsh climatic conditions. By contrast, hard-walled buildings benefit from the use of locally sourced materials and labour. Their relatively straightforward construction methods and ease of skills transfer have supported rapid capacity development, created local employment opportunities and increased demand for domestic materials, thereby contributing positively to the construction sector in the Central African Republic. |
| The Advisory Committee trusts that information on the guidelines, as well as on the cost-recovery formula, will be provided in the next budget proposal (para. 41). | Guidelines to enhance the optimal utilization of the multi-purpose building are currently being developed by the Mission. The objective of these guidelines is to ensure the facility functions effectively as a multifunctional platform supporting meetings, training activities, guest accommodation and engagement with partners. Upon finalization, the guidelines will establish clear procedures and operational standards to promote efficient, transparent and equitable utilization of the facility by all stakeholders. A draft cost-recovery formula for the utilization of the multi-purpose building has been developed in close coordination with key internal stakeholders and will be in effect in the 2026/2027 period. Upon approval, the proposed formula will be submitted for configuration in the cost-recovery system of the Organization with a clear activity matrix. In the meantime, the Mission is systematically documenting all conferences and events conducted in the facility to ensure accurate and effective application of the cost-recovery framework once approval is granted. The implementation of this mechanism will strengthen financial accountability and contribute to the sustainable operation of the facility. |
| The Advisory Committee considers that the full implementation of the new contracts for the outsourcing of maintenance of facilities and camp services may not be ready with effect as of the beginning of the 2025/26 period. The Committee trusts that updated information on the status of procurement of the new contracts for facilities maintenance and camp management services will be provided to the General Assembly at the time of its consideration of the present report and presented in the next budget proposal, including on the actual start date of the outsourcing contracts and on any related financial impact on the proposed resources (para. 44). | The solicitation process for the outsourcing of facilities maintenance and camp management services was completed and approved by the Headquarters Committee on Contracts in May 2025. The award of the contracts was subsequently delayed due to a combination of liquidity constraints and risk-management considerations, particularly those related to the transition of individual contractors during the electoral period in the Central African Republic. Given the elevated political and operational risk at the time, MINUSCA determined that proceeding with contract awards and transitions would have entailed undue operational and financial exposure. Following the successful conduct of national elections on 28 December 2025 and the corresponding reduction in political risk, the Mission focused on a phased transition plan, with full activation of the outsourcing contracts expected by December 2026. Interim arrangements remain in place to ensure continuity of facilities maintenance and camp services pending completion of the transition. Updated information on the status of these contracts, including the actual start date and any related financial impacts, will be provided to the General Assembly at the time of its consideration of the present report and included in the next budget submission, in line with the Advisory Committee’s request. |
| The Advisory Committee trusts that MINUSCA will ensure that projects benefit the local population as intended and that updated information, including on planning, implementation and assessment, will be provided in the context of the next budget proposal (para. 51). | MINUSCA ensures that projects are designed and implemented in line with the needs of the local population through its established planning and results framework. This framework provides an overview of priority needs and tracks progress against indicators linked to the outputs of the mission plan, allowing for the ongoing assessment of relevance, effectiveness and impact. Planning, implementation and monitoring information will continue to be updated and reflected in future proposed budget reports, in line with the Advisory Committee’s request. While the Mission does not currently apply a standardized accountability to affected populations strategy, the needs of the local population are systematically considered through existing planning, coordination and monitoring mechanisms. |
| The Advisory Committee notes the efforts of the Mission to improve asset and inventory management and looks forward to further information on the integration of the supply chain tool as a baseline for budget preparation to be presented in the next budget report (para. 55). | The Mission uses the outputs of its supply chain planning tools, driven by a rolling demand process, as the analytical baseline for resource planning and material requirements planning. This approach aligns operational requirements with available resources and allows for adjustments in response to liquidity constraints. The outputs are updated quarterly using validated data on inventory levels, consumption trends, asset condition and service demand. They inform demand prioritization, replenishment decisions and the timing of acquisitions and disposals. |
|  | Updated information on the integration and use of the supply chain planning tools will continue to be reflected in future budget reports, in line with the Advisory Committee’s request. |

Annex

Organization charts

A.	United Nations Multidimensional Integrated Stabilization Mission in the Central African Republic

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer; PL, Principal level; UNV, United Nations Volunteer; USG, Under-Secretary-General.

a	New post.

b	Redeployed.

c	General temporary assistance.

d	Reassigned.

B.	Mission Support Division

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer; PL, Principal level; UNV, United Nations Volunteer; USG, Under-Secretary-General.

a	General temporary assistance.

Map

__________________

__________________

Note: The following abbreviations are used in the tables: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer; UNV, United Nations Volunteers; USG, Under-Secretary-General.

The actual number of posts and positions is based on the rounded average.

The results-based budgeting outputs are available for consultation on the Umoja Analytics platform as part of efforts to streamline the volume of information presented in the new combined budget and performance report.

Missions that utilized 90 per cent or more of the number of flight hours approved for the most recent performance period can propose to maintain the same number of flight hours approved for that performance period (2024/25) in the respective categories (rotary- or fixed-wing). For missions that utilized less than 90 per cent of the approved flight hours, the proposed flight hours are based on the higher of the average utilization percentage of the three most recent performance periods, as shown in the table above, and the utilization percentage of the most recent period (2024/25). The higher of those two percentages is then applied to the number of flight hours approved for the most recent performance period (2024/25) to obtain the proposed flight hours. Limited exceptions to this guidance may be considered on a case-by-case basis, should compelling justifications be provided. To provide missions with flexibility for their operating environment, total flight hours according to the policy may be distributed between the categories as required by the mission. A delayed deployment of 50 per cent is applied for new aircraft, with exceptions considered for the significant reconfiguration of an aviation fleet.

Resource variance amounts are expressed in thousands of United States dollars. Analysis is provided for variances of at least plus or minus 5 per cent or $100,000.