Eightieth session

Agenda item 156 (b)

Financing of the United Nations peacekeeping forces in the Middle East: United Nations Interim Force in Lebanon

Budget performance for the period from 1 July 2024 to 30 June 2025 and budget for the period from 1 July 2026 to 30 June 2027 for the United Nations Interim Force in Lebanon

Report of the Secretary-General

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Mandate, results achieved and planned outcome |  |  | 6 |
| - Mandate |  |  | 6 |
| - Budget implementation for 2024/25 |  |  | 6 |
| - Planning assumptions and mission support initiatives for 2026/27 |  |  | 9 |
| - Regional mission cooperation |  |  | 13 |
| - Human resources |  |  | 14 |
| - Results-based budgeting frameworks |  |  | 19 |
| - Financial resources |  |  | 23 |
| - Overall |  |  | 23 |
| - Non-budgeted contributions |  |  | 24 |
| - Efficiency gains |  |  | 24 |
| - Unencumbered balance |  |  | 25 |
| - Cancellation of prior-period obligations |  |  | 25 |
| - Other revenue and adjustments, and borrowing |  |  | 26 |
| - Analysis of requirements for air operations |  |  | 27 |
| - Programmatic activities |  |  | 28 |
| - Quick-impact projects |  |  | 28 |
| - Qana incident |  |  | 29 |
| - Analysis of variances |  |  | 29 |
| - Actions to be taken by the General Assembly |  |  | 34 |
| - Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/308, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly |  |  | 35 |
| - General Assembly |  |  | 35 |
| - Advisory Committee on Administrative and Budgetary Questions |  |  | 35 |
| Annex |  |  |  |
| Organization charts |  |  | 38 |
| Map |  |  | 40 |

Summary

The present report contains the budget performance and the budget for the United Nations Interim Force in Lebanon (UNIFIL) for the period from 1 July 2024 to 30 June 2025 and 1 July 2026 to 30 June 2027, respectively.

The 2024/25 period was marked by several key achievements by the Force in the most challenging circumstances, while remaining on the ground throughout intensified hostilities between Hizbullah and the Israel Defense Forces. UNIFIL remained in position along the Blue Line, including during Israel Defense Forces ground operations from 1 October 2024. Despite the temporary suspension of some operations, UNIFIL maintained operational readiness and implemented mandated activities, including monitoring and reporting, de-escalation and mitigation of hostilities, and facilitation of humanitarian and civilian access, where possible, while providing safe and sustainable support services for its personnel. Following the cessation of hostilities that came into effect on 27 November 2024, the Force adapted its operational posture to build on opportunities arising from its new strategic environment, to enable the full resumption of operational activities, including in support of the extension of State authority and to facilitate the return of displaced communities.

During the 2026/27 period, UNIFIL will continue to implement the provisions of Security Council resolution 1701 (2006), conditions permitting, as reaffirmed in Council resolution 2790 (2025), until it ceases operations on 31 December 2026. From 1 January 2027, UNIFIL will implement an orderly and safe drawdown and withdrawal of substantially all mission personnel and assets not required for the subsequent liquidation period, as set out in paragraphs 5 to 9 of resolution 2790 (2025).

Financial resources The Force incurred $520.0 million in expenditure for the 2024/25 budget performance period, representing a resource utilization rate of 96.9 per cent, compared with $511.5 million in expenditure and a resource utilization rate of 95.2 per cent in the 2023/24 period.

The unencumbered balance of $16.8 million reflects the net impact of: (a) reduced requirements for military and police personnel, attributable primarily to the delayed, non-deployment or partial deployment of contingent-owned equipment owing to challenges faced by the troop-contributing countries and a higher actual average vacancy rate; (b) increased requirements for civilian personnel, attributable primarily to higher common staff costs for all categories as they relate to relocation, hardship and non-family duty station allowances, and danger pay; and (c) reduced requirements for operational costs, attributable primarily to the curtailed acquisition of prefabricated facilities, which would instead be replaced with concrete structures to be constructed, lower fuel costs and lower costs for air operations owing to the temporary suspension of military air operations during the continued exchange of fire across the Blue Line.

The budget proposed for the 2026/27 period in the amount of $408.0 million represents a decrease of $144.8 million, or 26.2 per cent, compared with the apportionment of $552.8 million approved for the 2025/26 period. The budget provides for six months of operations, during the period from 1 July to 31 December 2026, followed by six months of an orderly and safe drawdown and withdrawal from 1 January to 30 June 2027.

The estimates for the 2026/27 period reflect reduced requirements for all categories of expenditure in accordance with the Force’s operational adjustments and integrated drawdown and withdrawal plan.

(Thousands of United States dollars; budget year is from 1 July to 30 June)

Category; Variance; 2026/27 cost estimates; Variance. 2024/25 apportionment; 2024/25 expenditure; Unencumbered balance; Percentage; 2025/26 apportionment; Amount; Percentage. Military and police personnel; 350 857.2; 336 134.4; 14 722.8; 4.2; 350 947.3; 259 142.9; (91 804.4); (26.2). Civilian personnel; 131 255.9; 139 393.0; (8 137.1); (6.2); 149 214.8; 114 979.8; (34 235.0); (22.9). Operational costs; 54 695.1; 44 463.8; 10 231.3; 18.7; 52 679.7; 33 901.0; (18 778.7); (35.6). Gross requirements; 536 808.2; 519 991.2; 16 817.0; 3.1; 552 841.8; 408 023.7; (144 818.1); (26.2). Staff assessment income; 18 116.9; 16 893.5; 1 223.4; 6.8; 19 490.4; 13 581.7; (5 908.7); (30.3). Net requirements; 518 691.3; 503 097.7; 15 593.6; 3.0; 533 351.4; 394 442.0; (138 909.4); (26.0). Voluntary contributions in kind (budgeted); –; –; –; –; –; –; –; –. Total requirements; 536 808.2; 519 991.2; 16 817.0; 3.1; 552 841.8; 408 023.7; (144 818.1); (26.2).

Human resourcesa The proposed budget provides for the deployment of up to 7,372 military personnel and 621 civilian posts and positions for the Force’s operational period from 1 July to 31 December 2026. On 31 December 2026, UNIFIL will cease its operations and commence the orderly and safe drawdown and withdrawal of personnel during the period from 1 January to 30 June 2027, retaining 1,037 military personnel and 464 civilian posts and positions as at 30 June 2027.

Military observers; Military contingents; United Nations police; Formed police units; Inter-national staff; National Professional Officers; National General Service; Temporary positionsb; United Nations Volunteers; Government-provided personnel; Total. Executive direction and management. Approved 2024/25; –; –; –; –; 29; 4; 9; 5; –; –; 47. Actual 2024/25; –; –; –; –; 28; 3; 9; 4; –; –; 44. Approved 2025/26; –; –; –; –; 29; 4; 9; 5; –; –; 47. Proposed 2026/27. Operational period (1 July–31 December 2026); –; –; –; –; 24; 3; 9; 4; –; –; 40. Drawdown and withdrawal period (as at 30 June 2027); –; –; –; –; 17; 2; 4; 2; –; –; 25. Components. Operations. Approved 2024/25; –; 13 000; –; –; 30; 18; 10; –; –; –; 13 058. Actual 2024/25; –; 9 762; –; –; 30; 17; 9; –; –; –; 9 818. Approved 2025/26; –; 13 000; –; –; 30; 18; 10; –; –; –; 13 058. Proposed 2026/27. Operational period (1 July–31 December 2026); –; 7 372; –; –; 24; 16; 7; –; –; –; 7 419. Military observers; Military contingents; United Nations police; Formed police units; Inter-national staff; National Professional Officers; National General Service; Temporary positionsb; United Nations Volunteers; Government-provided personnel; Total. Drawdown and withdrawal period (as at 30 June 2027); –; 1 037; –; –; 7; 6; 3; –; –; –; 1 053. Support. Approved 2024/25; –; –; –; –; 195; 24; 525; –; –; –; 744. Actual 2024/25; –; –; –; –; 183; 23; 484; –; –; –; 690. Approved 2025/26; –; –; –; –; 194; 24; 525; –; –; –; 743. Proposed 2026/27. Operational period (1 July–31 December 2026); –; –; –; –; 154; 21; 359; –; –; –; 534. Drawdown and withdrawal period (as at 30 June 2027); –; –; –; –; 131; 16; 276; –; –; –; 423. Total. Approved 2024/25; –; 13 000; –; –; 254; 46; 544; 5; –; –; 13 849. Actual 2024/25; –; 9 762; –; –; 241; 43; 502; 4; –; –; 10 552. Approved 2025/26; –; 13 000; –; –; 253; 46; 544; 5; –; –; 13 848. Proposed 2026/27. Operational period (1 July–31 December 2026); –; 7 372; –; –; 202; 40; 375; 4; –; –; 7 993. Drawdown and withdrawal period (as at 30 June 2027); –; 1 037; –; –; 155; 24; 283; 2; –; –; 1 501. Net change; –; (11 963); –; –; (98); (22); (261); (3); –; –; (12 347).

a Represents the highest level of authorized/proposed strength. b Funded under general temporary assistance.

Legislative history (Thousands of United States dollars)

2024/25 period; 2025/26 period. Report; Date; Amount; Report; Date; Amount. Proposed budget – Secretary-General; A/78/725; 22 January 2024; 538 234.5; A/79/752; 24 February 2025; 555 820.8. Recommendation – Advisory Committee on Administrative and Budgetary Questions; A/78/744/Add.3; 8 April 2024; 537 951.5; A/79/724/Add.7; 7 April 2025; 553 841.8. Appropriationsa – General Assembly; A/RES/78/305; 28 June 2024; 536 808.2; A/RES/79/308; 30 June 2025; 552 841.8. Appropriation (net); 518 691.3; 533 351.4.

a The total amount has been assessed on Member States.

The actions to be taken by the General Assembly are set out in section V of the present report.

I.	Mandate, results achieved and planned outcome

A.	Mandate

1.	The mandate of the United Nations Interim Force in Lebanon (UNIFIL) was established by the Security Council in its resolutions 425 (1978) and 426 (1978), expanded in its resolution 1701 (2006) and extended in subsequent resolutions. The mandate for the performance period was provided by the Council in its resolutions 2695 (2023) and 2749 (2024). The most recent extension of the mandate was authorized by the Council in its resolution 2790 (2025), by which it extended the mandate for a final time until 31 December 2026, when the Force is to cease its operations and to start from this date and within one year its orderly and safe drawdown and withdrawal of personnel.

2.	The Force is mandated to help the Security Council to achieve the overall objective of restoring international peace and security in southern Lebanon.

B.	Budget implementation for 2024/25

3.	During the 2024/25 period, UNIFIL experienced fundamental changes to its operational environment. After months of exchanges of fire across the Blue Line, the launch by the Israel Defense Forces of Operation Northern Arrows on 23 September 2024, with ground operations north of the Blue Line starting on 1 October 2024, represented a new phase, inhibiting mobile operations and the Force’s monitoring and reporting abilities that were required to fulfil its mandate. The subsequent announcement of a cessation of hostilities between Lebanon and Israel (see S/2024/870), effective 27 November 2024, created a period of new opportunities for the implementation of resolution 1701 (2006), with the parties committing to its full implementation. Following the announcement, the UNIFIL operational environment gradually improved, with a decrease in kinetic activity. While the Israel Defense Forces then largely withdrew from north of the Blue Line, they maintained their long-standing presence in northern Ghajar, as well as at five newly established positions and two “buffer zones” north of the Blue Line after 18 February 2025. The Lebanese Armed Forces deployed to locations across the area of operations vacated by the Israel Defense Forces, with support from UNIFIL

4.	Until 27 November 2024, with the movement of UNIFIL highly restricted, the Force’s operational priorities were monitoring violations of resolution 1701 (2006), with significantly increased reporting requirements, as well as liaison and coordination between the parties. This included facilitating humanitarian access, in accordance with an updated strategy for the protection of civilians. Once a cessation of hostilities came into effect, UNIFIL focused on facilitating the strengthened deployment of the Lebanese Armed Forces to south of the Litani River, while adapting the Force to align with new requirements prompted by the changes in the operational environment. This included removing roadblocks, clearing unexploded ordnance, and reopening and assessing secondary roads in re-establishing access throughout the area of operations and to the Blue Line. The safety and security of military and civilian personnel remained a key priority throughout the period, with additional capabilities for explosive ordnance disposal, ordnance reconnaissance and engineering support deployed.

5.	UNIFIL finalized its adaptation plan in January 2025 and subsequently implemented a more robust, operations-centred modus operandi, with dedicated operations involving multiple military assets, focused on assisting the Lebanese Armed Forces in deploying south of the Litani River, creating a safe and secure environment and preventing violations of resolution 1701 (2006). In connection with these operational changes, the Force adapted its methodology for tracking and monitoring its operational activities.

6.	UNIFIL expanded its operational footprint within its area of operations following the cessation of hostilities; however, it experienced several incidents that restricted its freedom of movement. While most of these incidents were relatively minor, with the Lebanese Armed Forces intervening to ease tensions with the local population, there were some serious incidents that resulted in injuries to peacekeepers. The Force continued to encounter roadblocks and the destruction of access roads approaching the five positions and two “buffer zones” established by the Israel Defense Forces north of the Blue Line, restricting access to five United Nations positions and inhibiting access to the full length of the Blue Line. The contamination of the area of operations with unexploded ordnance resulting from the exchanges of fire also impeded access in some areas, including parts of the Blue Line. UNIFIL, reinforced with additional explosive ordnance disposal and demining teams, conducted dedicated operations, clearing unexploded ordnance and explosive remnants of war and other debris, assessing and reopening secondary roads and re-establishing access to the Blue Line. While re-establishing its operational footprint, UNIFIL enhanced its monitoring and reporting activities.

7.	In close coordination with the Office of the United Nations Special Coordinator for Lebanon, UNIFIL utilized its unique liaison and coordination mechanisms, including the Liaison Branch, to help prevent misunderstandings and decrease tension along the Blue Line. UNIFIL also continued its engagement with the parties to promote security arrangements aimed at facilitating the full withdrawal of the Israel Defense Forces from north of the Blue Line. In support of the implementation of a cessation of hostilities, UNIFIL hosted all seven meetings of the cessation of hostilities monitoring mechanism, chaired by the United States of America with the support of France and attended by the parties.

8.	UNIFIL, in coordination with humanitarian partners, enhanced its strategy for the protection of civilians. To this end, the Force’s liaison and coordination mechanism between the parties facilitated movement and humanitarian access in areas close to the Blue Line, as well as civilian activities in the area of operations, during intense exchanges of fire and the prolonged period of active hostilities. UNIFIL also enhanced efforts to address misinformation and disinformation, in line with the Force’s strategic communications strategy, and coordinated several media visits to enhance visibility and understanding of its mandate and activities.

9.	UNIFIL and the Office of the United Nations Special Coordinator for Lebanon maintained close cooperation and coordination on public statements calling for de-escalation. UNIFIL also continued to engage with the United Nations country team and the humanitarian country team, including by participating in United Nations coordination and crisis response efforts and contributing to the implementation of the United Nations Sustainable Development Cooperation Framework for the period 2023–2025 and supporting the rapid recovery assessment, which in turn informed the extension of the Cooperation Framework to 2027. This resulted in a more coherent and sustained basis for United Nations support for the recovery and development priorities of Lebanon.

10.	Following the announcement of a cessation of hostilities, the Lebanese Armed Forces increased its presence in the UNIFIL area of operations, reaching 8,311 personnel deployed to south of the Litani River with their own equipment as at 22 June 2025, compared with between approximately 2,000 and 3,000 prior to October 2023. The percentage of UNIFIL operational activities conducted in close coordination with the Lebanese Armed Forces also increased, from 0 per cent at the beginning of the year to 23 per cent in June 2025. The Lebanese Armed Forces and UNIFIL continued to engage within the framework of the strategic dialogue process, while coordinating with the Office of the United Nations Special Coordinator for Lebanon and the Military Technical Committee for Lebanon, a newly established forum of donors in support of the strengthened deployment of the Lebanese Armed Forces in southern Lebanon.

11.	The UNIFIL Maritime Task Force provided project-based training to the Lebanese Armed Forces-Navy and continued to mentor and support them as the Navy increasingly executed the maritime interdiction command function. The training and management concept jointly developed by UNIFIL and the Navy resulted in the monthly integration of two fully crewed, equipped and trained Navy boats into Maritime Task Force operations. Despite some progress towards the partial transfer of responsibilities from the Maritime Task Force, the capabilities of the Lebanese Navy remained severely limited in terms of personnel, equipment and resources.

12.	Troop-contributing countries faced ongoing challenges regarding the deployment of contingent-owned equipment in both categories in connection with the transition away from using United Nations-owned equipment and the restructuring of some key mechanized infantry battalions. Delays were a result of attacks in the Gulf of Aden in June 2024 on a cargo ship transporting contingent-owned equipment to UNIFIL, which subsequently reached UNIFIL in 2025, as well as the decision taken by the troop-contributing country concerned to hold back its remaining equipment due to the prevailing security situation, and challenges faced by another troop-contributing country regarding the procurement of equipment.

13.	The Force implemented significant force protection measures as the safety and security of personnel remained a priority, while programme-critical civilian personnel remained on the ground to support operations. These measures included reinforcing shelters with shatter-resistant film, installing anti-blast protection, adding security access to bunkers, reducing the footprint in the most exposed positions along the Blue Line and providing alerts when personnel must remain on base. Regarding civilian personnel, between August and October 2024, there were various temporary relocation measures implemented for national staff and their dependants and international staff in accordance with the United Nations Security Management System Security Policy Manual and administrative guidelines. National staff who had not already relocated through earlier measures did so from high-risk areas north and south of the Litani River. Non-programme critical international staff were relocated from the South Litani River designated area to the North Litani River designated area and, subsequently, as the security situation evolved, from the North Litani River designated area to outside Lebanon, while programme-critical international staff were relocated from Tyre to either the North Litani River designated area or Naqoura, but remained in Lebanon. National staff who remained in the area of operations were provided with shelter at United Nations positions when needed. Restrictions for non-programme-critical international staff in the South Litani River designated area were lifted on 25 March 2025; however, movement restrictions remained in place in the area of operations.

14.	While these measures taken by UNIFIL were effective in ensuring the safety and security of UNIFIL personnel and maintaining critical operations and staff welfare, the Force absorbed significant costs that were not included in the approved budget. The Force’s financial management strategy comprised reprioritization, cost containment, internal sourcing and other austerity measures to adapt to the evolving requirements during the security crisis and the liquidity challenges. The Force implemented a hiring freeze for civilian personnel and strict limitations on official travel, training and outreach, and non-essential maintenance, and scaled back and deferred non-essential construction and acquisitions for rehabilitation, major repairs and maintenance of facilities at the Force’s headquarters and in the sectors, as well as leveraged surplus stock from other missions and the 3R (return, refurbishment and reuse) programme for critical acquisitions and strategic deployment stocks.

15.	Despite the escalation of hostilities in September 2024, which necessitated restrictions on movement and the temporary suspension of air and ground operations, followed by the longer-term liquidity situation, the Force maintained critical services, such as supply chain continuity, fuel distribution exceeding 17 million litres, medical readiness, safe conduct of rotations, contractual adjustments for catering and fuel operations, and repairs to damaged critical infrastructure. Medical demands increased sharply owing to conflict-related injuries and stress, while the UNIFIL medical network and established evacuation arrangements maintained full operational capacity and provided timely treatment and medical evacuation support for both peacekeepers and civilian personnel.

C.	Planning assumptions and mission support initiatives for 2026/27

Period of regular mandated operations from 1 July to 31 December 2026

16.	UNIFIL will, during the first six months of the 2026/27 period, prioritize activities aimed at supporting the parties in maintaining the cessation of hostilities and stability along the Blue Line, recommitting to the full implementation of resolution 1701 (2006) and taking concrete steps towards addressing outstanding provisions of that resolution, including steps towards a permanent ceasefire, and a long-term political solution between Lebanon and Israel, which are key to long-term stability. Pursuant to resolution 2790 (2025), UNIFIL will also remain ready to support, when relevant, enhanced diplomatic efforts to resolve any dispute or reservations pertaining to the international border between Lebanon and Israel. Furthermore, UNIFIL will take every measure to ensure the overall physical security of peacekeepers and respond, within its capabilities, to security concerns or threats, including by demanding full accountability for attacks on peacekeepers.

17.	Until 31 December 2026, in coordination with the Office of the United Nations Special Coordinator for Lebanon, UNIFIL will continue to proactively engage with both parties to support efforts in maintaining the cessation of hostilities between Lebanon and Israel. The Force will utilize its well-established liaison and coordination mechanisms to mitigate tensions and seek agreed solutions to contentious issues. UNIFIL will fulfil its liaison and prevention role and remain ready to convene bilateral and trilateral meetings, including through the tripartite mechanism, upon the request of the parties, as well as host meetings of the reformulated and enhanced tripartite mechanism set out in the cessation of hostilities arrangement between Israel and Lebanon of 26 November 2024 (see S/2024/870). The Force will also use its liaison and coordination channels to facilitate humanitarian access and movement, including the return of displaced persons to affected areas along the Blue Line.

18.	UNIFIL will continue to monitor, investigate and report on violations of resolution 1701 (2006), concurrently supporting the parties in fulfilling their commitments to the resolution. UNIFIL will cooperate with and support the mechanism set out in resolution 2790 (2025), including through the Force’s monitoring and verification role. UNIFIL will also continue to promote full respect for the integrity of the Blue Line, including by calling for the full withdrawal of the Israel Defense Forces from all areas north of the Blue Line.

19.	UNIFIL will maintain a proactive posture, profile and presence and a high operational tempo, conducting both daily mobile and static operational activities, including air, vehicle and foot patrols, conditions permitting. These activities will be implemented together with the Lebanese Armed Forces or conducted independently, as appropriate. UNIFIL will continue to urge the parties to ensure unhindered access throughout its area of operations and along the Blue Line in all its parts. Throughout this period, UNIFIL will maintain its strategic communications efforts, including engagement with national and local authorities and communities in support of UNIFIL activities.

20.	UNIFIL will intensify its support to the Lebanese Armed Forces to ensure their effective and sustainable deployment south of the Litani River and to enhance their capacities to implement Security Council resolution 1701 (2006). UNIFIL will also continue its support for the Lebanese Armed Forces in the establishment between the Blue Line and the Litani River of an area free of any armed personnel, assets or weapons other than those of the Government of Lebanon and of UNIFIL. UNIFIL, in coordination with the Lebanese Armed Forces, will also make use of the existing rules of engagement, specifically its operational activities aimed at discovering tunnels and weapons caches and its tactical responsiveness to mitigate denials of its freedom of movement.

21.	The Lebanese Armed Forces are to assume full operational responsibility by 31 December 2026, and the Government of Lebanon is to fully maintain maritime sovereignty thereafter, protecting the country’s maritime borders and preventing illegal activities, including the import of weapons and related materiel by sea. The UNIFIL Maritime Task Force, with a fleet of two vessels and personnel units, will continue to provide capacity-building and training activities until 31 December 2026 to strengthen the tactical and operational capabilities of the Lebanese Armed Forces-Navy.

22.	UNIFIL demining military contingent personnel will continue to undertake the clearance of mines, explosive remnants of war and improvised explosive devices from the areas where the Force is deployed.

23.	Close coordination with the United Nations Resident and Humanitarian Coordinator, the United Nations country team, the humanitarian country team and other partners will continue to support timely information-sharing and joint planning for community support, enabling the more efficient use of resources. This will also help sustain ongoing efforts to build resilience and support early recovery and reconstruction in the south.

Drawdown and withdrawal period from 1 January to 30 June 2027

24.	On 31 December 2026, UNIFIL will cease its operations and then begin and within one year complete the orderly and safe drawdown and withdrawal of its personnel as from 1 January 2027, in close consultation with the Government of Lebanon, with the aim of making the Government the sole provider of security in southern Lebanon, and in coordination with the troop-contributing countries. During the drawdown and withdrawal period, and in line with established Financial Regulations and Rules of the United Nations, UNIFIL will take all necessary steps to ensure that property and assets are safely transferred to the control of the designated entity. UNIFIL will utilize its established liaison and coordination mechanisms to address possible challenges to an orderly and safe drawdown and will maintain consistent engagement with the parties and local communities to facilitate a smooth withdrawal of the Force.

25.	UNIFIL will provide security for United Nations personnel, facilities, convoys, installations and equipment, and associated personnel. The Force will also maintain situational awareness in the vicinity of UNIFIL locations and provide escorts for United Nations uniformed and civilian personnel carrying out enabling support functions. UNIFIL will also maintain its ability to provide medical support, including casualty and medical evacuation support, for United Nations personnel. The Force will maintain effective outreach and strategic communications, including at the community level, during this period to support situational awareness and enhance force protection. In cooperation and consultation with the Government of Lebanon, and within its capacity, UNIFIL will contribute to the protection of civilians and the safe civilian-led delivery of humanitarian assistance.

26.	UNIFIL will oversee and facilitate an orderly and safe drawdown and withdrawal of the Force from 1 January to 30 June 2027 through the phased repatriation of whole contingents, guided by a consolidation plan that prioritizes efficiency and security. UNIFIL will divest the United Nations positions under the responsibility of each outgoing troop-contributing country and hand over the positions to the Lebanese authorities. Military contingent personnel and their equipment will be progressively relocated and consolidated at battalion headquarters to enable the release of smaller United Nations positions.

27.	The withdrawal plan takes into account the rotation cycles of troop-contributing countries to the extent possible, while ensuring systematic consolidation from positions along the Blue Line to battalion and sector headquarters. By 30 June 2027, remaining assets will be concentrated in Sector West at UNIFIL headquarters in Naqoura, as well as at a few possibly remaining United Nations positions.

28.	The repatriation plan for the Force’s military component takes into account restrictions on aircraft capacity, flight intervals, the staging area and the daily processing capacity of UNIFIL, and compliance with air traffic guidelines of the Lebanese civil aviation authority.

29.	Given the operational context, including the condition of roads, contamination with unexploded ordnance or explosive remnants of war and other debris, the condition of the facilities at the Beirut port, and possible continued hostile activity in the area of operations, a combination of enablers and commercial contractors, in addition to the guard units, will be required for the orderly and safe closure of United Nations positions or their handover to the Lebanese Armed Forces. Residual military contingent personnel and military staff officers will be limited to essential functions only, comprising force protection (providing escorts and support for incidents during movements, including medical evacuations, security for UNIFIL headquarters and close protection for the head of mission), military police, level 1 hospital support, convoys, telecommunications, minimal rear party duties, explosive ordnance disposal and deconstruction work.

30.	Aligned with responsible stewardship and best practice, UNIFIL will facilitate the processing and destruction of degraded ammunition for repatriating contingents, as well as ordnance clearance at UNIFIL positions. UNIFIL will support demining military contingent personnel with technical expertise and advice, training, accreditation, and quality assurance of the clearance operations, as well as certification that ammunition disposal and clearance are conducted in accordance with national and international mine action standards and that the ownership of United Nations positions can safely be transferred to the Lebanese authorities.

31.	UNIFIL, through the Secretary-General, will continue to keep the Security Council regularly informed about relevant developments in relation to this process.

Mission support initiatives

32.	During the first six months of the 2026/27 period, UNIFIL will balance providing the support required to sustain mandate delivery until 31 December 2026 with the operational, logistical, administrative and financial requirements of a safe and orderly drawdown thereafter. The Force will focus on the safety of personnel and responsible resource management while demonstrating prudent environmental responsibility.

33.	As the operating environment remains complex, characterized by regional volatility, logistical constraints and an evolving but unpredictable security landscape, UNIFIL will maintain essential enabling services and mission support functions that ensure the conduct of mandated operations, as well as operational resilience and safe working conditions for all personnel.

34.	The civilian staffing levels from 1 July to 31 December 2026 reflect the operational adjustments implemented during the 2025/26 period owing to liquidity constraints and further leverages the efficiencies achieved through the proposed abolishment of 227 positions. To ensure continuity of operations, remaining civilian personnel (621 posts and positions) will assume additional functions within their existing capacity. This approach will preserve institutional knowledge and maintain service quality without additional resource implications.

35.	Following the end of UNIFIL operations on 31 December 2026, the Force will focus on the orderly and safe downsizing and withdrawal of uniformed and civilian personnel, the repatriation of contingent-owned equipment, the processing of United Nations-owned equipment and the phased handover of mission premises to the Lebanese authorities.

36.	UNIFIL will repatriate substantially all its military personnel and contingent-owned equipment by 30 June 2027. The phased abolishment of civilian personnel posts and positions will be sequenced in connection with the drawdown of military personnel and United Nations positions and would begin on 1 January 2027. Civilian personnel will be separated in accordance with the Organization’s downsizing policy and other applicable human resources policies and practices.

37.	The retention of a limited number of civilian roles and functions during 2027 will ensure the sufficient capacity required for the drawdown, withdrawal and liquidation phases. The functions retained will include a small substantive component to orient strategic communications, which would require outreach and engagement at the national and local levels, to complete final reporting requirements and to coordinate with other United Nations entities, in support of an orderly, safe and efficient drawdown and withdrawal. Mission support functions will be retained to facilitate the significant volume and complexity of tasks related to human resources, finance, claims, property management and other administrative and logistical support required during the drawdown and withdrawal and subsequent liquidation period.

38.	While the civilian drawdown and withdrawal plan retains certain critical functions to support closure and administrative accountability, given the longevity of the Force’s mandate of over 40 years and its operational history, the security environment and the complexity and challenges of the drawdown and progress towards the liquidation period cannot be fully anticipated. The retained staffing level is based on careful prioritization of essential functions and redistribution of remaining capacities to sustain core operations throughout the phases of the Force’s closure.

39.	The Force will implement infrastructure-related activities, including (a) the safe removal of modular buildings to prepare for site decommissioning and restoration, requiring heavy equipment for demolition, excavation and transport operations; (b) regular maintenance of concrete and steel structures to ensure safety and structural integrity; (c) servicing of water wells to maintain a reliable supply of potable water for mission personnel; and (d) building maintenance to support hygiene standards and the health and well-being of mission personnel. Advanced sampling and testing of water and treated wastewater and soil will be conducted to mitigate potential environmental harm and ensure that UNIFIL positions that are closed are free from the risk of ordnance and adverse environmental impacts.

40.	The Force will maintain the following: operational security services to ensure the orderly and safe drawdown of UNIFIL; functional medical support at United Nations-owned and contingent-owned medical facilities across 10 locations and medical evacuation arrangements through the existing network of level II to IV capabilities, to ensure continuity of care and emergency readiness; and essential information technology and communications support to ensure connectivity and operational security. Mission-wide 24/7 security monitoring and response frameworks will remain in place. Mission-wide relocation and evacuation preparedness and overall support will adapt as the operational landscape evolves.

41.	The Force will implement separation processes, financial settlements and activities related to asset verification and property disposal. Activity across some enabling functions will increase as the Force finalizes staff separations, certifies entitlements, settles outstanding obligations, processes claims, verifies and reconciles all outstanding obligations related to vendors, personnel and contingents, liquidates commitments, settles travel- and separation-related claims, and prepares inputs to the final performance and financial statements. The limited personnel retained during this period will perform multiple roles, ensure the continuity of essential services, safeguard financial integrity, maintain accountability and support a transparent audit trail through to the completion of closure.

42.	Significant effort will be dedicated to property management, such as physical verification and development of the preliminary asset disposal plan to be coordinated with United Nations Headquarters and the United Nations Logistics Base at Brindisi, Italy. A review and risk analysis of existing contracts and mission liabilities will be performed, and preparatory work for the gradual conclusion of property and claims matters and documentation of the final disposition of those assets will begin.

43.	Overall, activities will focus on safeguarding institutional memory and integrity and ensuring that the withdrawal is executed efficiently, transparently and in full accordance with Financial Regulations and Rules of the United Nations and other relevant standards.

D.	Regional mission cooperation

44.	During the 2024/25 period, UNIFIL collaborated with United Nations entities and missions in the region to strengthen skills and coordination through joint training initiatives such as Safe and Secure Approaches in Field Environments courses and specialized workshops in project management, data visualization and career development. The initiatives enhanced teamwork, knowledge-sharing and regional cooperation, with training resources also extended to the United Nations Truce Supervision Organization (UNTSO) and the Office of the United Nations Special Coordinator for Lebanon.

45.	UNIFIL coordinated regional HIV/AIDS shared services provided to UNTSO, the United Nations Disengagement Observer Force, the United Nations Peacekeeping Force in Cyprus, the Office of the Special Coordinator for the Middle East Peace Process and Personal Representative of the Secretary-General to the Palestine Liberation Organization and the Palestinian Authority and the Office of the United Nations Special Coordinator for Lebanon, supporting preparedness by promoting health, reducing risk and mitigating impact on personnel, Member States and host communities. Due to the temporary relocation of personnel until March 2025, activities were conducted virtually.

46.	The Regional Conduct and Discipline Section supported 10 missions in implementing the United Nations misconduct prevention strategy through training, risk assessments and outreach. It facilitated enforcement by coordinating investigations and managing related correspondence, while also contributing to victim support efforts through the prevention of sexual exploitation and abuse network in Lebanon. Services were provided on a non-reimbursable basis, with direct costs covered by the receiving missions.

47.	Through its dual responsibility providing UNIFIL with field technology services and the Regional Field Technology Service for region 1 framework, UNIFIL coordinated the strategic management of regional cooperation related to information and communications technology (ICT). In addition, UNIFIL continued to provide ICT gateway services to the Office of the United Nations Special Coordinator for Lebanon and the Office of the Special Envoy of the Secretary-General for Syria on a cost-recovery basis, while extending Internet, telephony and VHF radio services to the UNTSO/Observer Group Lebanon.

48.	UNIFIL received support from the Kuwait Joint Support Office, where one international and two General Service staff members were embedded to process payroll for the Force’s national staff and military staff officers. The Force also maintained its arrangement with the in-house banking functions centralized for Lebanon and located at the Economic and Social Commission for Western Asia.

49.	During the 2026/27 period, the Force will continue the same regional cooperation as in the 2024/25 period to sustain mandate delivery until 31 December 2026 and to support an orderly and safe drawdown thereafter, apart from cooperation with the Kuwait Joint Support Office.

50.	After the closure of the Kuwait Joint Support Office on 30 June 2026, services for the processing of payroll for the Force’s national staff and military staff officers would be provided by the Regional Service Centre in Entebbe, Uganda. In addition, the role of UNIFIL in the Regional Field Technology Service will be subsumed by the Regional Service Centre effective 1 July 2027. In-house banking requirements will be subsumed by the Economic and Social Commission for Western Asia by the end of the period.

E.	Human resources

51.	The proposed civilian and military personnel levels for the first six months of the period reflect the operational adjustments implemented during the 2025/26 period owing to liquidity constraints. Through lateral reassignments and the consolidation of functions and units, operations were streamlined and the use of existing staff resources optimized. These measures ensured that organizational capacity was maintained, thereby redirecting resources to prioritized mandated functions and enhancing overall effectiveness.

52.	As a result of the above measures, it is proposed that 227 posts and positions be abolished as from 1 July 2026. With a view to the drawdown and withdrawal of the Force from 1 January to 30 June 2027, it is proposed that another 157 posts and positions be abolished, amounting to the abolishment of a total of 384 posts and positions during the 2026/27 period.

53.	Between 1 January and 30 June 2027, UNIFIL will implement a major drawdown from 7,372 to 1,037 military personnel, and associated equipment, and reduce the infrastructure of 43 United Nations positions, while simultaneously implementing liquidation and closure tasks. These include repatriation of contingent-owned equipment, asset disposal, handover of infrastructure, environmental remediation and contract close-out. The civilian staffing establishment will support these processes.

Note: The following abbreviations are used in the tables: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer; UNV, United Nations Volunteers; USG, Under-Secretary-General.

54.	In addition to the below post and position requirements, based on lessons learned from the closure of peacekeeping operations, additional human resources are required to perform temporary specific non-operational functions for workload that is non-recurring and time-bound. In this context, a provision for general temporary assistance is proposed to support short-term functions in mission support that are critical for drawdown and withdrawal activities and preparation for the liquidation phase, in lieu of retaining posts. This would provide the Force with maximum flexibility for “surge capacity” and limit long-term staffing liabilities. The capacity was estimated based on 22 positions (11 international (5 P-3 and 6 Field Service) and 11 national General Service) and will be adjusted on the basis of surge requirements during the period.

Table

Executive direction and management

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | 1 | 2 | 13 | 6 | 7 | 29 | 4 |  | 9 | 13 | – |  | – | – | 42 |
| Actual posts 2024/25 | 1 | 2 | 13 | 5 | 7 | 28 | 3 |  | 9 | 12 | – |  | – | – | 40 |
| Approved posts 2025/26 | 1 | 2 | 13 | 6 | 7 | 29 | 4 |  | 9 | 13 | – |  | – | – | 42 |
| Proposed posts 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) | 1 | 1 | 11 | 5 | 6 | 24 | 3 |  | 9 | 12 |  |  |  |  | 36 |
| Drawdown and withdrawal period (as at 30 June 2027) | 1 | – | 8 | 4 | 4 | 17 | 2 |  | 4 | 6 | – |  | – | – | 23 |
| Net change | – | (2) | (5) | (2) | (3) | (12) | (2) |  | (5) | (7) | – |  | – | – | (19) |
| Approved temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | 4 | 4 | – |  | – | – | 5 |
| Actual temporary positionsa 2024/25 | – | – | 1 | – | – | 1 | – |  | 3 | 3 | – |  | – | – | 4 |
| Approved temporary positionsa 2025/26 | – | – | 1 | – | – | 1 | – |  | 4 | 4 | – |  | – | – | 5 |
| Proposed temporary positionsa 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) | – | – | 1 | – | – | 1 | – |  | 3 | 3 | – |  | – | – | 4 |
| Drawdown and withdrawal period (as at 30 June 2027) | – | – | 1 | – | – | 1 | – |  | 1 | 1 | – |  | – | – | 2 |
| Net change | – | – | – | – | – | – | – |  | (3) | (3) | – |  | – | – | (3) |
| Total, including temporary positions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 | 1 | 2 | 14 | 6 | 7 | 30 | 4 |  | 13 | 17 | – |  | – | – | 47 |
| Actual 2024/25 | 1 | 2 | 14 | 5 | 7 | 29 | 3 |  | 12 | 15 | – |  | – | – | 44 |
| Approved 2025/26 | 1 | 2 | 14 | 6 | 7 | 30 | 4 |  | 13 | 17 | – |  | – | – | 47 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) | 1 | 1 | 12 | 5 | 6 | 25 | 3 |  | 12 | 15 | – |  | – | – | 40 |
| Drawdown and withdrawal period (as at 30 June 2027) | 1 | – | 9 | 4 | 4 | 18 | 2 |  | 5 | 7 | – |  | – | – | 25 |
| Net change | – | (2) | (5) | (2) | (3) | (12) | (2) |  | (8) | (10) | – |  | – | – | (22) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 032.4 |  |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  | 10 575.9 |  |

a	Funded under general temporary assistance.

55.	The proposed staffing establishment for executive direction and management will comprise 40 posts and positions (25 international, 3 National Professional Officer and 12 national General Service, including 4 temporary positions (1 international and 3 national General Service)) from 1 July to 31 December 2026. UNIFIL will draw down and withdraw personnel during the period from 1 January to 30 June 2027, retaining 25 civilian posts and positions (18 international, 2 National Professional Officer and 5 national General Service, including 2 temporary positions (1 international and 1 national General Service)) as at 30 June 2027.

56.	A lean and essential leadership and coordination structure of the executive direction and management component will continue to provide unified oversight, ensuring that political, operational and administrative activities remain fully aligned with Security Council resolution 2790 (2025), the directives of the Secretary-General and the relevant policies of the Organization.

57.	The front office of the head of mission will continue to exercise overall command of mandated activities, providing strategic direction, liaison and decision-making support to ensure a coherent and well-sequenced, orderly and safe drawdown and withdrawal of its personnel and assets, with the objective of completing the process expeditiously. The Legal Affairs Office will provide essential legal support to the Force’s operations and for its closure, protecting the Organization’s legal interests and minimizing the risk of legal liability, including regarding the termination of commercial contracts, contractual disputes and third-party claims, the downsizing of personnel, the disposal of assets, the handover of sites to the Government and other legal matters. The Regional Conduct and Discipline Section will maintain preventive and responsive mechanisms to uphold the Secretary-General’s zero-tolerance policy on sexual exploitation and abuse and other forms of misconduct.

58.	In parallel, the Office of the Principal Coordinator will oversee mission-wide planning, analytical and coordination functions, including risk management, ensuring that operational, financial and logistical activities remain synchronized between the military and civilian processes. The retained capacity will safeguard continuity of command, ongoing situational awareness and risk-informed decision-making, as well as organizational learning and institutional accountability, throughout this phase of the closure.

Component 1: operations

| Category |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I. Military contingents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 000 |
| Actual 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 762 |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 000 |
| Proposed 2026/27a |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7 372 |
| Drawdown and withdrawal period (as at 30 June 2027) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 037 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (11 963) |
|  |  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| II. Civilian staff |  | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal |  | NPO | NGS | Subtotal |  | Inter-national | National | Subtotal | Total |
| Approved posts 2024/25 |  | – | 3 | 13 | 8 | 6 | 30 | 18 |  | 10 | 28 | – |  | – | – | 58 |
| Actual posts 2024/25 |  | – | 3 | 13 | 8 | 6 | 30 | 17 |  | 9 | 26 | – |  | – | – | 56 |
| Approved posts 2025/26 |  | – | 3 | 13 | 8 | 6 | 30 | 18 |  | 10 | 28 | – |  | – | – | 58 |
| Proposed posts 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) |  | – | 2 | 10 | 6 | 6 | 24 | 16 |  | 7 | 23 | – |  | – | – | 47 |
| Drawdown and withdrawal period (as at 30 June 2027) |  | – | 1 | 2 | 2 | 2 | 7 | 6 |  | 3 | 9 | – |  | – | – | 16 |
| Net change |  | – | (2) | (11) | (6) | (4) | (23) | (12) |  | (7) | (19) | – |  | – | – | (42) |
| Total I and II |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved posts 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 058 |
| Actual posts 2024/25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 818 |
| Approved posts 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 058 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7 419 |
| Drawdown and withdrawal period (as at 30 June 2027) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 053 |
| Net change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (12 005) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 14 361.3 |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7 921.8 |

a	Represents the proposed funded strength.

59.	The proposed staffing establishment for component 1 will comprise 7,372 military personnel and 47 civilian posts (24 international and 16 national professional officers and 7 national general service) as of 1 July to 31 December 2026. UNIFIL will drawdown and withdraw personnel during the period from 1 January to 30 June 2027, retaining 1,037 military personnel and 16 civilian posts (7 international, 6 national professional officers and 3 national general service) as of 30 June 2027.

60.	A critical capacity in the Division of Political and Civil Affairs will be retained until 30 June 2027 to support the drawdown and withdrawal of the Force with engagement and outreach at the national and local levels, along with public information activities, as part of comprehensive strategic communications. Political advisory capacity will ensure that the Force’s closure period is coherent and compliant with the relevant Security Council resolutions, including through support for continuous engagement with the parties to avoid misunderstandings and miscalculations, as well as with troop-contributing countries. Political affairs functions will further continue to lead preparation of the Force’s inputs to reports to the General Assembly and the Security Council. Civil affairs functions will sustain direct liaison with local authorities and communities, including with regard to facilitating the efficient handover of United Nations positions to local authorities, finalizing the legal closure of quick-impact projects and preserving field-level communication channels essential for stability during the phase of mission closure. Strategic communications will continue to manage the Force’s public narrative and legacy messaging, countering disinformation and misinformation and ensuring transparent engagement with host authorities and the public, including as provided for under Council resolution 2790 (2025).

Component 2: support

|  | International staff |  |  |  |  |  |  | National staff |  |  |  | UNV |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | USG–ASG | D-2–D-1 | P-5–P-4 | P-3–P-2 | FS | Subtotal | NPO |  | NGS | Subtotal | Inter-national |  | National | Subtotal | Total |
| Approved posts 2024/25 | – | 3 | 30 | 23 | 139 | 195 | 24 |  | 525 | 549 | – |  | – | – | 744 |
| Actual posts 2024/25 | – | 3 | 29 | 22 | 129 | 183 | 23 |  | 484 | 507 | – |  | – | – | 690 |
| Approved posts 2025/26 | – | 3 | 30 | 23 | 138 | 194 | 24 |  | 525 | 549 | – |  | – | – | 743 |
| Proposed posts 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operational period (1 July–31 December 2026) | – | 3 | 27 | 19 | 105 | 154 | 21 |  | 359 | 380 | – |  | – | – | 534 |
| Drawdown and withdrawal period (as at 30 June 2027) | – | 1 | 25 | 17 | 88 | 131 | 16 |  | 276 | 292 | – |  | – | – | 423 |
| Net change | – | (2) | (5) | (6) | (50) | (63) | (8) |  | (249) | (257) | – |  | – | – | (320) |
| Estimated amount (civilian personnel) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (Thousands of United States dollars) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approved 2025/26 |  |  |  |  |  |  |  |  |  |  |  |  |  | 122 773.9 |  |
| Proposed 2026/27 |  |  |  |  |  |  |  |  |  |  |  |  |  | 96 482.1 |  |

61.	The staffing establishment for the support component comprises 534 posts (154 international and 21 national professional officers and 359 national general service) for the Force’s operational period from 1 July to 31 December 2026. UNIFIL will drawdown and withdraw personnel during the period from 1 January to 30 June 2027, retaining 423 civilian posts (131 international, 16 national professional and 276 national general service) as of 30 June 2027.

62.	The mission support pillar will retain the capacities required to ensure the orderly, compliant and auditable conclusion of all administrative, logistical and financial functions during the drawdown and liquidation period. The Office of the Director of Mission Support will oversee the integrated implementation of the drawdown and withdrawal plan, ensuring that all operational and financial activities are carried out in accordance with United Nations policies and internal control standards.

63.	The Finance and Budget Management Section will manage all financial closure activities, including the verification and settlement of outstanding obligations, final payroll and entitlement payments, and the preparation of the Force’s final performance and financial reports. The Human Resources Section will implement the downsizing policy and ensure the accurate and timely processing of staff separations and repatriations.

64.	The Mission Support Centre will coordinate all logistics and support operations related to the drawdown and withdrawal of uniformed personnel, including the repatriation of contingent-owned equipment, camp closures and movement control. The Centre will serve as the Force’s central hub for planning, tracking and reporting on drawdown progress, ensuring coherence across operational pillars and alignment with Headquarters guidance and the Force Commander’s directives.

65.	The service delivery management and supply chain management pillars, including the Transport Section, the Engineering and Facility Maintenance Section, the Life Support Section, the Medical Services Section, the Movement Control Section and the Procurement Section, will maintain critical services, manage the repatriation of contingent-owned equipment, oversee asset disposal and environmental restoration in accordance with the property acknowledgement and disposal plan, and ensure compliance with audit and safety standards. These retained capacities will ensure continuity of essential services, accountability of resources and a safe and efficient logistical and administrative drawdown, enabling UNIFIL to complete its withdrawal and liquidation in a disciplined and transparent manner.

F.	Results-based budgeting frameworks

Component 1: operations

Period from 1 July to 31 December 2026

| Expected accomplishments |  | Indicators of achievement |
| --- | --- | --- |
| 1.1 Stable and secure environment in southern Lebanon |  | 1.1.1 Absence of air, sea or ground incursions or firing incidents across the Blue Line (2022/23: 535 air and 1,545 ground violations; 2023/24: 4,405 air and 536 ground violations; 2024/25: 1,917 air and 4,019 ground violations; 2025/26: 3,500 air and 200 ground violations; 2026/27: 2,690 air and 697 ground violations) |
|  |  | 1.1.2 Lebanese Armed Forces deployed throughout the entire area south of the Litani River, including the part of the town of Ghajar north of the Blue Line and an adjacent area north of the Blue Line |
|  |  | 1.1.3 Area between the Blue Line and the Litani River is free of any armed personnel, assets and weapons, except for those of the Lebanese Armed Forces and UNIFIL (2022/23: 805; 2023/24: 457; 2024/25: 77; 2025/26: 500; 2026/27: 130) |
|  |  | 1.1.4 Participation by both parties in the enhanced tripartite meetings, applicable to 2026/27 in line with the Mechanism set out in the cessation of hostilities arrangement between Israel and Lebanon of 26 November 2024 (S/2024/870) and Security Council resolution 2790 (2025) and maintenance of liaison and coordination arrangements (2022/23: 6; 2023/24: yes; 2024/25: 0; 2025/26: yes; 2026/27: 6) |
|  |  | 1.1.5 Increase in the area safe from landmines and explosive remnants of war (2022/23: 25,892 m2; 2023/24: 11,290 m2; 2024/25: 1,651 m2; 2025/26: 30,000 m2; 2026/27: 15,000 m2) |
|  |  | 1.1.6 Lebanese Armed Forces are increasingly able to take over maritime interdiction operations |
| 1.2 Extension of the authority of the Government of Lebanon in southern Lebanon |  | 1.2.1 Municipalities and civic and religious institutions in the UNIFIL area of operations demonstrate continuity of basic functions and service delivery (2022/23: 145; 2023/24: 145; 2024/25: 145; 2025/26: 145; 2026/27: 145) |
|  |  | 1.2.2 Prevention, by the Lebanese Armed Forces, of the presence of any armed personnel, assets and weapons other than those of the Government of Lebanon or UNIFIL |
|  |  | 1.2.3 Lebanese Armed Forces personnel have strengthened civil-military coordination capacities through the conduct of joint activities, regular information-sharing and advocacy for external funding |
|  |  | 1.2.4 Government of Lebanon representatives are actively engaged in meetings on support for communities in the area of operations and assume a leading role in steering recovery and rehabilitation efforts, demonstrated through their involvement in recovery and coordination meetings, prioritization of community needs and projects, and maintenance of oversight of project implementation |
| External factors |  |  |
| All parties will remain committed to the implementation of Security Council resolution 1701 (2006); UNIFIL will be afforded freedom of movement by all parties |  |  |

Drawdown and withdrawal period from 1 January to 30 June 2027

| Expected accomplishments | Indicators of achievement |
| --- | --- |
| 1.3 Safe and orderly drawdown and withdrawal of UNIFIL troops and personnel, in close consultation with the Government of Lebanon | 1.3.1 Compliance with applicable standards for disposal of weapons and ammunition and camp closure |
|  | 1.3.2 UNIFIL has completed all required drawdown actions, including the safe transfer of assets to designated entities and the accountable, timely repatriation of contingents and contingent-owned equipment, with no significant incidents reported |
|  | 1.3.3 No major security incidents involving United Nations personnel, assets or convoys during withdrawal operations |

Component 2: support

Period from 1 July to 31 December 2026

| Expected accomplishments |  | Indicators of achievement |
| --- | --- | --- |
| 2.1 Rapid, effective, efficient and responsible support services for the Force |  | 2.1.1 Average annual percentage of women international civilian staff (2022/23: 37.6 per cent; 2023/24: 38.7 per cent; 2024/25: 39.7 per cent; 2025/26: ≥ 47 per cent; 2026/27: ≥ 47 per cent) |
|  |  | 2.1.2 Average number of days for roster recruitments, from posting of the job opening to candidate selection, for international candidates (2022/23: 92; 2023/24: 92; 2024/25: 111; 2025/26: ≤ 120 calendar days from posting for P-3 to D-1 and FS-3 to FS-7 levels; 2026/27: 120) |
|  |  | 2.1.3 Average number of days for post-specific recruitments, from posting of the job opening to candidate selection, for international candidates (2022/23: 201; 2023/24: 187; 2024/25: 218; 2025/26: ≤ 120 calendar days from posting for P-3 to D-1 and FS-3 to FS-7 levels; 2026/27: 120) |
|  |  | 2.1.4 Overall score on the property management index based on 20 underlying key performance indicators (2022/23: 1,893; 2023/24: 1,918; 2024/25: 1,819; 2025/26: ≥1,800; 2026/27: ≥900) |
|  |  | 2.1.5 Percentage of contingent personnel in standard-compliant United Nations accommodation at 30 June, in accordance with memorandums of understanding (2022/23: 100 per cent; 2023/24: 100 per cent; 2024/25: 100 per cent; 2025/26: 100 per cent; 2026/27: 100 per cent) |
|  |  | 2.1.6 Compliance of vendors with United Nations rations standards for delivery, quality and stock management (2022/23: 97.3 per cent; 2023/24: 95.0 per cent; 2024/25: 97.1 per cent; 2025/26: ≥ 95 per cent; 2026/27: ≥ 95 per cent) |
| External factors |  |  |
| Several factors may affect the ability to deliver proposed outputs as planned, including changes in the political, security, economic and humanitarian contexts or weather conditions not foreseen in the planning assumptions, other instances of force majeure and changes in the mandate during the reporting period |  |  |

Drawdown and withdrawal period from 1 January to 30 June 2027

| Expected accomplishments | Indicators of achievement |
| --- | --- |
| 2.2 Rapid, effective, efficient and responsible support services for the Mission during the drawdown and withdrawal period from 1 January to 30 June 2027 | 2.2.1 Receipt, management and onward distribution of United Nations-owned and contingent-owned equipment, estimated at up to 1,264 tons of cargo within the mission area |
|  | 2.2.2 Repatriation of 86 per cent of uniformed personnel and/or preparation for transfer of 85 per cent of contingent-owned equipment, and 100 per cent of assets under a letter of assist, in accordance with the integrated drawdown and withdrawal plan |
|  | 2.2.3 86 per cent of United Nations positions/bases south of the Litani River are vacated by 30 June 2027 |
|  | 2.2.4 Timely processing of separation of staff in accordance with the drawdown and withdrawal plan: 384 staff separated by 30 June 2027 |

Evaluation activities

66.	The following evaluation completed by the Office of Internal Oversight Services during the 2024/25 period guided UNIFIL planning for the 2026/27 period, where relevant, taking into consideration that the Force will cease its operations on 31 December 2026 and start from that date its orderly and safe drawdown and withdrawal: evaluation of the contribution of strategic communications to fostering public trust in peacekeeping operations.

67.	In response to the results of the evaluation referenced above, indicators of achievement, specific actions and target completion dates were attributed to each recommendation as part of an implementation plan. The plan is focused on enhancing the overall effectiveness and accountability of the Force. It serves as a structured approach to ensure timely follow-up and to translate evaluation findings into practical improvements that support transparency and operational efficiency.

68.	In 2026/27, no evaluation is anticipated while UNIFIL focuses on implementing six months of operations until 31 December 2026, followed by a safe and orderly drawdown and withdrawal from 1 January to 30 June 2027.

II.	Financial resources

A.	Overall

(Thousands of United States dollars; budget year is from 1 July to 30 June)

|  | 2024/25 apportionment | 2024/25 expenditure | Variance |  | 2025/26 apportionment | 2026/27 cost estimates | Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Unencumbered balance | Percentage |  |  | Amount | Percentage |
| Category | (1) | (2) | (3)=(1)-(2) | (4)=(3)÷(1) | (5) | (6) | (7)=(6)-(5) | (8)=(7÷5) |
| Military and police personnel |  |  |  |  |  |  |  |  |
| Military observers | – | – | – | – | – | – | – | – |
| Military contingents | 350 857.2 | 336 134.4 | 14 722.8 | 4.2 | 350 947.3 | 259 142.9 | (91 804.4) | (26.2) |
| United Nations police | – | – | – | – | – | – | – | – |
| Formed police units | – | – | – | – | – | – | – | – |
| Subtotal | 350 857.2 | 336 134.4 | 14 722.8 | 4.2 | 350 947.3 | 259 142.9 | (91 804.4) | (26.2) |
| Civilian personnel | – | – | – | – | – | – | – | – |
| International staff | 64 859.6 | 71 636.9 | (6 777.3) | (10.4) | 72 342.9 | 60 407.4 | (11 935.5) | (16.5) |
| National Professional Officer | 8 625.0 | 8 510.2 | 114.8 | 1.3 | 9 508.2 | 7 933.9 | (1 574.3) | (16.6) |
| National General Service staff | 57 241.8 | 58 293.8 | (1 052.0) | (1.8) | 66 625.4 | 43 699.8 | (22 925.6) | (34.4) |
| United Nations Volunteers | – | – | – | – | – | – | – | – |
| General temporary assistance | 529.5 | 952.1 | (422.6) | (79.8) | 738.3 | 2 938.7 | 2 200.4 | 298.0 |
| Government-provided personnel | – | – | – | – | – | – | – | – |
| Subtotal | 131 255.9 | 139 393.0 | (8 137.1) | (6.2) | 149 214.8 | 114 979.8 | (34 235.0) | (22.9) |
| Operational costs |  |  |  |  |  |  |  |  |
| Civilian electoral observers | – | – | – | – | – | – | – | – |
| Consultants and consulting services | 88.3 | 110.6 | (22.3) | (25.3) | 226.0 | 185.7 | (40.3) | (17.8) |
| Official travel | 721.3 | 880.5 | (159.2) | (22.1) | 713.7 | 493.3 | (220.4) | (30.9) |
| Facilities and infrastructure | 28 147.5 | 20 427.3 | 7 720.2 | 27.4 | 24 813.5 | 15 927.7 | (8 885.8) | (35.8) |
| Ground transportation | 6 546.4 | 7 196.0 | (649.6) | (9.9) | 5 775.5 | 4 370.2 | (1 405.3) | (24.3) |
| Air operations | 5 929.9 | 4 007.9 | 1 922.0 | 32.4 | 5 412.6 | 4 955.8 | (456.8) | (8.4) |
| Marine operations | 172.1 | 17.8 | 154.3 | 89.7 | 56.3 | 25.0 | (31.3) | (55.6) |
| Communications and information technology | 8 036.9 | 7 326.0 | 710.9 | 8.8 | 9 896.2 | 4 089.6 | (5 806.6) | (58.7) |
| Medical | 1 323.4 | 962.6 | 360.8 | 27.3 | 1 484.9 | 932.4 | (552.5) | (37.2) |
| Special equipment | – | – | – | – | – | – | – | – |
| Other supplies, services and equipment | 3 229.3 | 3 035.1 | 194.2 | 6.0 | 3 301.0 | 2 571.3 | (729.7) | (22.1) |
| Quick-impact projects | 500.0 | 500.0 | – | – | 1 000.0 | 350.0 | (650.0) | (65.0) |
| Subtotal | 54 695.1 | 44 463.8 | 10 231.3 | 18.7 | 52 679.7 | 33 901.0 | (18 778.7) | (35.6) |
| Gross requirements | 536 808.2 | 519 991.2 | 16 817.0 | 3.1 | 552 841.8 | 408 023.7 | (144 818.1) | (26.2) |
| Staff assessment income | 18 116.9 | 16 893.5 | 1 223.4 | 6.8 | 19 490.4 | 13 581.7 | (5 908.7) | (30.3) |
| Net requirements | 518 691.3 | 503 097.7 | 15 593.6 | 3.0 | 533 351.4 | 394 442.0 | (138 909.4) | (26.0) |
| Voluntary contributions in kind (budgeted) | – | – | – | – | – | – | – | – |
| Total requirements | 536 808.2 | 519 991.2 | 16 817.0 | 3.1 | 552 841.8 | 408 023.7 | (144 818.1) | (26.2) |

B.	Non-budgeted contributions

69.	The value of non-budgeted contributions for the period from 1 July 2024 to 30 June 2025 and 1 July 2026 to 30 June 2027 is as follows:

(Thousands of United States dollars)

| Category | Actual value (2024/25) | Estimated value (2026/27) |
| --- | --- | --- |
| Status-of-forces agreementa | 6 122.3 | 3 152.0 |
| Voluntary contributions in kind (non-budgeted) | – | – |
| Total | 6 122.3 | 3 152.0 |

a	Represents the estimated rental value of land and premises provided by the Government of Lebanon, including UNIFIL House in Beirut, an evacuation centre in Tyre, premises in the area of operations south of the Litani River, movement control offices at the seaport and airport, the UNIFIL headquarters in Naqoura and military positions, as well as services, value-added tax refunds and duty waivers.

C.	Efficiency gains

70.	The period from 1 July 2024 to 30 June 2025 resulted in the following efficiency initiatives:

(Thousands of United States dollars)

|  |  | Estimated efficiency gains (2024/25) | Realized efficiency gains (2024/25) | Variance 2024/25 | Investment since inception to generate the efficiency gains of 2026/27 | Cumulated efficiency gains since inception and before 2026/27 | Estimated efficiency gains (2026/27) | Cumulated investments and efficiency gains as of 2026/27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Budget class | Description of the Initiative | (1) | (2) | (3)=(2)-(1) | (4) | (5) | (6) | (7)=(4)+(5)+(6) |
| Military contingents; contingent-owned major equipment | Transition from using United Nations-owned equipment to conduct UNIFIL operations to deploying contingent-owned major equipment, which was initiated in 2023/24 | 2 148.0 | 3 231.5 | 1 083.5 | – | – | – | – |
| Facilities and infrastructure | Investment in renewable energy through replacement of conventional lighting with light-emitting diodes in line with the regular replacement cycle and an increase in solar capacity | 350.8 | 83.6 | (267.2) | – | – | – | – |
|  | Acquisition of renewable energy through turnkey contract (solar photovoltaic and hybrid systems) | – | 330.9 | 330.9 | – | – | – | – |
|  | Acquisition/installation of more efficient air conditioning units reflected in the new proposed five-year phased asset replacement plan | 154.6 | 144.5 | (10.1) | – | – | – | – |
|  | Defence barriers and binding and concertina wire sourced from MINUSMA | – | 463.9 | 463.9 | – | – | – | – |
| Ground transportation | Armoured vehicles from UNMIK (1) | – | 124.2 | 124.2 | – | – | – | – |
|  | MINUSMA (6) |  | 186.2 | 186.2 |  |  |  |  |
| Mine Action Service new delivery model |  |  |  |  |  |  |  |  |
| Other supplies, services and equipment | Mine detection and mine clearing services | 529.3 | 529.3 | 0.0 | – | – | – | – |
| General temporary assistance | 4 temporary positions (national General Service) transferred to the UNIFIL staffing table | (223.6) | (395.6) | (172.0) | – | – | – | – |
| Official travel | Travel costs associated with the programme | (13.4) | (5.4) | 8.0 | – | – | – | – |
| Subtotal |  | 292.3 | 128.3 | (164.0) |  |  |  |  |
| Total |  | 2 945.7 | 4 693.1 | 1 747.4 |  |  |  |  |

Abbreviation: MINUSMA, United Nations Multidimensional Integrated Stabilization Mission in Mali, UNMIK, United Nations Mission in Kosovo

D.	Unencumbered balance

71.	The unencumbered balance for the periods from 2022/23 to 2024/25 as reported in the respective performance reports is as follows:

Trend of the unencumbered balance

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 14 574.5 | 20 741.1 | 14 722.8 |
| Civilian personnel | (3 011.4) | (7 192.0) | (8 137.1) |
| Operational costs | (11 561.7) | 12 285.5 | 10 231.3 |
| Total | 1.4 | 25 834.6 | 16 817.0 |

E.	Cancellation of prior-period obligations

72.	Prior-period obligations for the periods from 2022/23 to 2024/25 were cancelled as follows:

Trend of the cancellation of prior-period obligations

(Thousands of United States dollars)

|  | Amount |  |  |
| --- | --- | --- | --- |
| Group | 2022/23 | 2023/24 | 2024/25 |
| Military and police personnel | 1 504.9 | 2 506.0 | 3 286.9 |
| Civilian personnel | 19.0 | 0.7 | 19.0 |
| Operational costs | 216.0 | 770.9 | 1 417.4 |
| Total | 1 739.9 | 3 277.6 | 4 723.3 |

Note: The amounts represent the total obligations that were cancelled at the end of the 12-month period following the end of the budget period in respect of goods supplied and services rendered in the budget period, and at the end of an additional period of four years in respect of obligations to troop- and police-contributing countries.

F.	Other revenue and adjustments, and borrowing

1.	Other revenue and adjustments

(Thousands of United States dollars)

| Category | Amount |
| --- | --- |
| Investment revenue | 10 727.4 |
| Other/miscellaneous revenue | 464.7 |
| Voluntary contributions in cash | – |
| Prior-period adjustments | – |
| Cancellation of prior-period obligations | 4 723.3 |
| Total | 15 915.4 |

73.	Credits comprising the unencumbered balances, other revenue and the cancellation of prior-period obligations reduce the assessed contributions owed by Member States in the following financial year. The credit for the 2024/25 period for overall peacekeeping operations amounts to $335.5 million, including the support entities and MINUSMA. In the current financial situation, offsetting this large amount of credit against a future assessment for the 2026/27 period will reduce the collection and undermine the ability of peacekeeping operations to fully implement their mandates. Accordingly, the Secretary-General proposes that the General Assembly approve that the credits in respect of the financial period 2024/25 be placed in a reserve that would be used in the event that collections are insufficient to enable the implementation of those mandates and allow Member States to apply their share towards current or future dues once the Assembly determines that the liquidity situation has sufficiently improved. This proposal is explained in more detail in the peacekeeping overview report.

2.	Borrowing

74.	Owing to cash liquidity situations in other active peacekeeping missions, the Force issued loans to missions, with the month-end loan balance as follows:

(Millions of United States dollars)

| As at | Borrowing mission | Amount |
| --- | --- | --- |
| 31 July 2024 | MINURSO (5.9), UNMIK (4.3), UNSOS (57.2), UNMISS (52.5) | 119.9 |
| 31 August 2024 | UNSOS (57.2), UNMISS (27.5) | 84.7 |
| 30 September 2024 | UNSOS (22.1) | 22.1 |
| 30 April 2025 | UNSOS (36.0), UNMISS (40.0) | 76.0 |
| 31 May 2025 | UNSOS (36.0), UNMISS (85.3) | 121.3 |
| 30 June 2025 | MINURSO (2.4), UNMIK (3.5), UNSOS (52.3), UNISFA (20.2) | 78.4 |

Abbreviations: MINURSO, United Nations Mission for the Referendum in Western Sahara; UNISFA, United Nations Interim Security Force for Abyei; UNMIK, United Nations Interim Administration Mission in Kosovo; UNMISS, United Nations Mission in South Sudan; UNSOS, United Nations Support Office in Somalia.

G.	Analysis of requirements for air operations

75.	The flight hour utilization rates for the periods from 2022/23 to 2024/25, the approved and proposed number of flight hours for the 2025/26 and 2026/27 periods, respectively, and the number of flight hours calculated based on the policy guidance are as follows:

| Aircraft type | Flight hour utilization (percentage) |  |  |  | Flight hours |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Actual |  |  | Average (2022/23 to 2024/25) |  | Approved |  |  | Policy | Proposed | Variance |
|  | 2022/23 | 2023/24 | 2024/25 |  |  | 2024/25 | 2025/26 |  | 2026/27 | 2026/27a |  |
|  | (1) | (2) | (3) | (4) |  | (5) | (6) |  | (7) | (8) | (9)=(8)-(6) |
| Fixed-wing | – | – | – | – | – |  | – | – |  | – | – |
| Helicopters | 78.2 | 30.7 | 37.9 | 48.9 | 1 200 |  | 1 200 | 587 |  | 600 | (600) |
| Total |  |  |  |  | 1 200 |  | 1 200 | 587 |  | 600 | (600) |

a	For the period from 1 July to 31 December 2026.

76.	UNIFIL will maintain its fleet of six aircraft and 600 flight hours to implement its core mandate until 31 December 2026 and provide essential support for assessing the area of operations, and ensure access to areas that are either contaminated with unexploded ordnance or explosive remnants of war and other debris or continue to be challenging to reach by ground due to various other factors. The additional 13 hours above those according to the policy will ensure implementation of its operations and adequate medical support.

77.	During the drawdown and withdrawal period, UNIFIL will maintain four aircraft in various locations and 120 flight hours in support of incident investigation, transportation of combat assets, command-and-control functions, liaison activities, casualty and medical evacuation, and technical qualifications required for landing on the Saint George Hospital helipad. The aviation unit and fleet will repatriate by 30 June 2027.

H.	Programmatic activities

78.	The period from 1 July 2024 to 30 June 2025 resulted in the following programmatic activities, compared with the approved budget for 2024/25:

(Thousands of United States dollars)

| Category | Apportionment (2024/25) | Expenditure (2024/25) | Cost estimates (2026/27) | Related expected accomplishment |
| --- | --- | --- | --- | --- |
| Youth, peace and security | 500.0 | 33.5 | – | 1.1 |  |
| Total | 500.0 | 33.5 | – |  |

79.	Detailed information on programmatic activities undertaken during the 2024/25 period is provided in the supplementary information. The resource requirements for the performance period are for projects implemented by the Force to support mandate implementation as outlined in the Force’s results-based budgeting framework.

80.	During the first six months of the 2026/27 period, the Force will focus on concluding programmatic activities approved for the 2025/26 period.

I.	Quick-impact projects

81.	The estimated resource requirements for quick-impact projects for the period from 1 July 2026 to 30 June 2027, compared with previous periods, are as follows:

(Thousands of United States dollars)

| Period | Amount | Number of projects |
| --- | --- | --- |
| 1 July 2024 to 30 June 2025 (actual) | 500.0 | 30 |
| 1 July 2025 to 30 June 2026 (approved) | 1 000.0 | 40 |
| 1 July 2026 to 30 June 2027 (proposed) | 350.0 | 14 |

82.	During the first six months of the period, UNIFIL will focus on supporting community resilience and strengthening local partnerships in support of the eventual drawdown and withdrawal, while addressing the urgent humanitarian and recovery needs of the population in the area of operations.

83.	The return of displaced populations to their villages remains severely constrained due to ongoing Israeli military activity, widespread destruction and extensive damage to civilian infrastructure. The prolonged instability has further strained local governance structures and slowed recovery efforts, deepening the vulnerability of affected populations. The projects will help address urgent priorities in areas such as the rehabilitation of public infrastructure, the restoration of basic services and livelihood support for conflict-affected populations.

84.	UNIFIL will design projects with a 90-day implementation period, allowing for swift execution, close monitoring and prompt closure. This approach will ensure that communities visibly benefit from tangible outcomes before the drawdown and withdrawal period begins.

85.	The projects will focus on three key thematic areas: extension of State authority, civic education and capacity-building; conflict management and confidence-building initiatives; and access to basic services and community infrastructure.

III.	Qana incident

86.	In paragraph 14 of its resolution 79/308, the General Assembly reiterated its request to the Secretary-General to take the measures necessary to ensure the full implementation of paragraph 8 of resolution 51/233, paragraph 5 of resolution 52/237, paragraph 11 of resolution 53/227, paragraph 14 of resolution 54/267, paragraph 14 of resolution 55/180 A, paragraph 15 of resolution 55/180 B, paragraph 13 of resolution 56/214 A, paragraph 13 of resolution 56/214 B, paragraph 14 of resolution 57/325, paragraph 13 of resolution 58/307, paragraph 13 of resolution 59/307, paragraph 17 of resolution 60/278, paragraph 21 of resolution 61/250 A, paragraph 20 of resolution 61/250 B, paragraph 20 of resolution 61/250 C, paragraph 21 of resolution 62/265, paragraph 19 of resolution 63/298, paragraph 18 of resolution 64/282, paragraph 15 of resolution 65/303, paragraph 13 of resolution 66/277, paragraph 13 of resolution 67/279, paragraph 13 of resolution 68/292, paragraph 14 of resolution 69/302, paragraph 13 of resolution 70/280, paragraph 14 of resolution 71/307, paragraph 14 of resolution 72/299, paragraph 16 of resolution 73/322, paragraph 3 of resolution 75/250 A, paragraph 39 of resolution 75/250 B, paragraph 15 of resolution 76/290, paragraph 14 of resolution 77/313 and paragraph 13 of resolution 78/305, stressed once again that Israel shall pay the amount of $1,117,005 resulting from the incident at Qana on 18 April 1996, and requested the Secretary-General to report on that matter to the Assembly at its eightieth session. Pursuant to the requests made in those resolutions, the amount has been recorded under accounts receivable in the special account for UNIFIL, and the Secretariat has transmitted 31 letters to the Permanent Mission of Israel on the subject, the most recent of which was dated 30 December 2025, to which no response has been received.

IV.	Analysis of variances

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Military contingents | $14 722.8 | 4.2% | ($91 804.4) |  | (26.2%) |

87.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) the delayed deployment of contingent-owned major equipment, the non-deployment of self-sustainment equipment of one key military contingent infantry battalion transitioning away from using United Nations-owned equipment and the partial deployment of major equipment for the restructuring of one mechanized infantry battalion, owing to challenges faced by the troop-contributing countries; and (b) the impact of the higher actual average vacancy rate of 25.4 per cent on the standard troop cost reimbursement, allowances and rations, owing to rotation schedules, compared with the rate of 24.2 per cent in the approved budget.

88.	For the 2026/27 period, the reduced requirements are attributable primarily to lower costs for standard troop cost reimbursement, allowances, rations and contingent-owned equipment and contingent marine operations owing to operational adjustments and the repatriation of military contingents as from January 2027 in accordance with the Force’s integrated drawdown and withdrawal plan compared with the approved budget for 2025/26. The reduced requirements are offset in part by higher costs for freight for the corresponding repatriation of contingent-owned equipment.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| International staff | ($6 777.3) | (10.4%) | ($11 935.5) |  | (16.5%) |

89.	For the 2024/25 period, the increased requirements were attributable primarily to (a) higher actual common staff costs owing to the introduction of (i) hardship and non-family status-related allowances in connection with changes in classification of the duty station as designated by the International Civil Service Commission (ICSC), and (ii) security evacuation allowance in connection with the implementation of personnel restrictions for non-programme critical internationally recruited personnel in North Litani River Designated Area introduced in October 2025; and (b) danger pay, for which provisions were not included in the approved budget.

90.	For the 2026/27 period, the reduced requirements are attributable primarily to (a) the abolishment of 98 international posts in accordance with the Force’s operational adjustments and integrated drawdown and withdrawal plan; and (b) the application of a lower revised post adjustment multiplier rate compared with the rate applied in the approved budget for 2025/26, offset in part by requirements for common staff costs for separation and repatriation entitlements.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| National Professional Officer | $114.8 | 1.3% | ($1 574.3) |  | (16.6%) |

91.	For the 2024/25 period, the reduced requirements were attributable primarily to the higher actual average vacancy rate of 6.5 per cent, owing to retirements and the recruitment freeze to mitigate liquidity challenges, compared with the rate of 2.2 per cent applied in the approved budget. The reduced requirements were offset in part by the introduction of danger pay in connection with the changes in classification of the duty station as designated by ICSC, for which a provision was not included in the approved budget.

92.	For the 2026/27 period, the reduced requirements are attributable primarily to the abolishment of 22 National Professional Officer posts in accordance with the Force’s operational adjustments and integrated drawdown and withdrawal plan.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| National General Service staff | ($1 052.0) | (1.8%) | ($22 925.6) |  | (34.4%) |

93.	For the 2024/25 period, the increased requirements were attributable primarily to the introduction of danger pay in connection with the changes in classification of the duty station as designated by ICSC, for which a provision was not included in the approved budget. The increased requirements were offset in part by the higher actual average vacancy rate of 7.7 per cent, owing to retirements and the recruitment freeze to mitigate liquidity challenges, compared with the rate of 5.9 per cent applied in the approved budget.

94.	For the 2026/27 period, the reduced requirements are attributable primarily to the abolishment of 261 national General Service posts in accordance with the Force’s operational adjustments and integrated drawdown and withdrawal plan, offset in part by requirements for common staff costs for separation entitlements.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| General temporary assistance | ($422.6) | (79.8%) | $2 200.4 |  | 298.0% |

95.	For the 2024/25 period, the increased requirements were attributable primarily to (a) higher costs for national staff resulting from a lower vacancy rate of 25 per cent, compared with the rate of 50 per cent applied for newly established national General Service positions in the approved budget; and (b) other personnel costs allocated to UNIFIL for general temporary assistance centralized at United Nations Headquarters.

96.	For the 2026/27 period, the increased requirements are attributable primarily to other personnel costs for support functions that are critical for drawdown and withdrawal and preparation for the liquidation phase to provide the Force with maximum flexibility for “surge capacity” for shorter durations, thereby replacing posts, estimated on the basis of 22 positions (11 international (5 P-3 and 6 Field Service) and 11 national General Service).

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Consultants and consulting services | ($22.3) | (25.3%) | ($40.3) |  | (17.8%) |

97.	For the 2024/25 period, increased requirements were attributable primarily to the engagement of consulting services to customize exterior protection for the Force’s power supplies located throughout the area of operations, which continually failed during the crisis without this protection.

98.	For the 2026/27 period, the reduced requirements are attributable to the engagement of fewer consulting services for infrastructure projects that were discontinued owing to the drawdown and withdrawal of UNIFIL as from January 2027 compared with the estimate included in the approved budget for 2025/26.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Official travel | ($159.2) | (22.1%) | ($220.4) |  | (30.9%) |

99.	For the 2024/25 period, the increased requirements were attributable primarily to the daily subsistence allowance and incidentals for staff members who were deemed programme critical and required to reside at the Naqoura camp or in Beirut following the relocation from North and South Litani River Designated Areas, and for military staff officers traveling to Beirut on a weekly basis for operational requirements, for which a provision was not included in the approved budget.

100.	The increased requirements were offset in part by fewer trips for official and training travel, which were cancelled or postponed owing to liquidity challenges, restrictions on non-essential travel and disruptions to transportation networks in connection with the prevailing security situation.

101.	For the 2026/27 period, the reduced requirements are attributable to the drawdown and withdrawal of UNIFIL as from January 2027.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Facilities and infrastructure | $7 720.2 | 27.4% | ($8 885.8) |  | (35.8%) |

102.	For the 2024/25 period, the reduced requirements were attributable primarily to: (a) the curtailed acquisition of prefabricated facilities that were reflected in the five-year phased asset replacement plan, which would instead be replaced with concrete structures to be constructed; and (b) the lower actual volume of 13.9 million litres of fuel for generators, acquired at an actual average price of $0.748 per litre, owing to the restrictions on non-essential travel and limited movement in the area of operations in connection with the prevailing security situation, and the decline in fuel costs, compared with the budgeted volume of 15 million litres at an average price of $0.868 per litre.

103.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) the prefabricated facilities conversion plan and other infrastructure projects that were discontinued; (b) the lower estimated volume of 12.3 million litres of fuel for generators, compared with 14.7 million litres included in the approved budget; and (c) the acquisition of a lower number of construction materials and field defence supplies, and various equipment and supplies, compared with the number included in the approved budget, owing to the drawdown and withdrawal of UNIFIL as from January 2027, compared with the estimates included in the approved budget for 2025/26.

104.	The reduced requirements are offset in part by increased requirements for utilities and waste disposal services to support the closure of positions, the removal of masts and all associated field technology infrastructure within UNIFIL positions, and dismantling and destruction services, in connection with the drawdown and withdrawal of UNIFIL as from January 2027.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Ground transportation | ($649.6) | (9.9%) | ($1 405.3) |  | (24.3%) |

105.	For the 2024/25 period, the increased requirements were attributable primarily to the accelerated acquisition of vehicles scheduled for the second year (2025/26) of the five-year phased asset replacement plan owing to the advanced deterioration of existing vehicles, for which a provision was not included in the approved budget.

106.	For the 2026/27 period, the reduced requirements are attributable primarily to the non-acquisition of vehicles and the acquisition of fewer spare parts for armoured vehicles, owing to the drawdown and withdrawal of UNIFIL as from January 2027.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Air operations | $1 922.0 | 32.4% | ($456.8) |  | (8.4%) |

107.	For the 2024/25 period, the reduced requirements were attributable primarily to lower costs for the rental and operation of the fleet of aircraft, owing to fewer flight hours in connection with the temporary suspension of military air operations during the continued exchange of fire across the Blue Line in connection with the prevailing security situation compared with budgeted estimates.

108.	For the 2026/27 period, the reduced requirements are attributable to lower costs for the rental and operation of fewer aircraft and flight hours owing to the drawdown and withdrawal of UNIFIL from as January 2027 compared with estimates included in the approved budget for 2025/26.

109.	The reduced requirements are offset in part by increased requirements for the deployment of a radar system for 12 months under a letter of assist that is fully operational and the deployment of a ground alert system for 12 months under a letter of assist, compared with one month included in the approved budget for 2025/26, to ensure situational awareness and the protection of UNIFIL personnel.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Marine operations | $154.3 | 89.7% | ($31.3) |  | (55.6%) |

110.	For the 2024/25 period, the reduced requirements were attributable primarily to the acquisition of a lower actual number of sea containers owing to the transportation of fewer items of equipment under facilities and infrastructure and the non-requirement for refrigerated containers, which had been acquired in the previous period based on emergent requirements, compared with the number of containers included in the approved budget.

111.	For the 2026/27 period, the reduced requirements are attributable primarily to the acquisition of a lower number of sea containers corresponding to the asset acquisitions that were discontinued owing to the drawdown and withdrawal of UNIFIL as from January 2027 compared with the number included in the approved budget for 2025/26.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Communications and information technology | $710.9 | 8.8% | ($5 806.6) |  | (58.7%) |

112.	For the 2024/25 period, the reduced requirements were attributable primarily to the non-acquisition of electronic countermeasure equipment and a conference room video and sound system, and the acquisition of fewer Cisco switches and docking stations owing to the prevailing security situation.

113.	For the 2026/27 period, the reduced requirements are attributable primarily to the acquisition of fewer items of equipment and the engagement of fewer support services for the maintenance of communications and information technology equipment owing to operational adjustments and the drawdown and withdrawal of UNIFIL as from January 2027 compared with estimates included in the approved budget for 2025/26.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Medical | $360.8 | 27.3% | ($552.5) |  | (37.2%) |

114.	For the 2024/25 period, the reduced requirements were attributable primarily to the lower utilization of hospitalization and testing services and the engagement of fewer veterinary services, as personnel were prohibited from accessing mission sites in connection with the prevailing security situation, compared with budgeted estimates.

115.	For the 2026/27 period, the reduced requirements are attributable primarily to the acquisition of fewer items of equipment and a smaller number of supplies owing to the drawdown and withdrawal of UNIFIL as from January 2027 compared with the estimates included in the approved budget for 2025/26.

|  | 2024/25 variance |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Other supplies, services and equipment | $194.2 | 6.0% | ($729.7) |  | (22.1%) |

116.	For the 2024/25 period, the reduced requirements were attributable primarily to the lower number of fee-based training courses attended in-person owing to the restrictions on non-essential travel and disrupted transportation and communications networks in connection with the prevailing security situation compared with the number of courses included in the approved budget.

117.	For the 2026/27 period, the reduced requirements are attributable primarily to: (a) no costs for implementing partners and grants associated with programmatic activities that were discontinued; and (b) lower costs for training fees, supplies and services owing to the drawdown and withdrawal of UNIFIL as from January 2027, offset in part by increased requirements for estimated potential claims in connection with the closure of 43 United Nations positions, compared with the estimates included in the approved budget for 2025/26.

|  |  |  |  | 2026/27 variance |  |
| --- | --- | --- | --- | --- | --- |
| Quick-impact projects |  |  | ($650.0) |  | (65.0%) |

118.	For the 2026/27 period, the reduced requirements are attributable to the lower number of quick-impact projects to ensure adequate time for completing and closing projects before the cessation of operations on 31 December 2026 owing to the drawdown and withdrawal of UNIFIL as from January 2027 compared with the number included in the approved budget for 2025/26.

V.	Actions to be taken by the General Assembly

119.	The actions to be taken by the General Assembly in connection with the financing of the United Nations Interim Force in Lebanon are:

(a)	To take note of the treatment of the unencumbered balance of $16,817,000 with respect to the period from 1 July 2024 to 30 June 2025;

(b)	To take note of the treatment of other revenue for the period ended 30 June 2025 amounting to $15,915,400 from investment revenue ($10,727,400), other/miscellaneous revenue ($464,700) and the cancellation of prior-period obligations ($4,723,300);

(c)	To approve the apportionment of the amount of $32,732,400 among Member States in accordance with the applicable scale of assessment for 2025 and to place such apportioned amount in a reserve that would be used in the event that collections are insufficient to enable the full, efficient and effective implementation of mandates;

(d)	To allow Member States to apply their share of the amount apportioned in subparagraph (c) above towards current or future dues once the General Assembly determines that the liquidity situation has improved sufficiently to allow such application;

(e)	To appropriate the amount of $408,023,700 for the maintenance of the Force for the 12-month period from 1 July 2026 to 30 June 2027;

(f)	To assess the amount in subparagraph (e) above at a monthly rate of $34,002,000 should the Security Council decide to continue the mandate of the Force.

VI.	Summary of follow-up action taken to implement the decisions and requests of the General Assembly in its resolutions 76/274 and 79/308, including the requests and recommendations of the Advisory Committee on Administrative and Budgetary Questions endorsed by the Assembly

A.	General Assembly

Cross-cutting issues

(Resolution 76/274)

| Decision/request | Action taken to implement decision/request |
| --- | --- |
| Requests the Secretary-General to improve comprehensive oversight of the activities of peacekeeping missions and implement the recommendations of relevant oversight bodies in this regard to avoid deficiencies in management and related economic losses, with the aim of ensuring full compliance with the Financial Regulations and Rules of the United Nations (para. 17). | As at 31 December 2025, 12 of the 13 recommendations (92 per cent) issued by the Office of Internal Oversight Services and 8 out of 12 recommendations (67 per cent) issued by the Board of Auditors had been implemented. Regular follow-ups are undertaken to ensure the timely closure of the remaining recommendations. |

B.	Advisory Committee on Administrative and Budgetary Questions

Financing of the United Nations peacekeeping forces in the Middle East: United Nations Interim Force in Lebanon

(A/79/724/Add.7 and General Assembly resolution 79/308)

| Request/recommendation | Action taken to implement request/recommendation |
| --- | --- |
| The Advisory Committee notes the challenges faced by the Maritime Task Force and that the capacity of the Force to deliver on the mandate requires maintaining six vessels in the fleet (see also A/78/744/Add.3, paras. 17 and 18). The Committee trusts that more information on the capacity of the Maritime Task Force and the concept of maritime operations will be provided to the General Assembly at the time of its consideration of the present report and that an update will be included in the next report of the Secretary-General (para. 18). | Updated information is provided in paragraphs 11 and 21 of the present report. |
| The Advisory Committee trusts that further information regarding the clearance of explosive ordnance in the area of operations will be provided in the next budget submission (see also A/78/744/Add.3, paras. 27–30) (para. 24). | Updated information is provided in paragraphs 6 and 22 of the present report. |
| The Advisory Committee trusts that UNIFIL will continue to engage the Force’s troops in the implementation of quick-impact projects and ensure that projects benefit the local population, as intended, and that updated information, including on planning, implementation and assessment, will be provided in the context of the next proposed budget report (para. 38). | The Force continues to engage troops in the design and implementation of quick-impact projects. Quick-impact projects are selected based on those with clearly demonstrated benefits for the population. |
|  | Long-term monitoring and evaluation of completed projects are regularly conducted to review the relevance, effectiveness and sustainability of their impact. This explores unintended results, identifies best practices, highlights significant accomplishments and draw lessons learned for improvement, which are then used to guide the Force’s future targeted community interventions. |
|  | In addition, the Force conducts an annual review of the impact of the projects. The most recent assessment of the Force’s quick-impact projects covered the projects implemented in 2023 and 2024. The salient findings of this assessment are as follows: |
|  | • Aligning projects with national and local priorities enhances sustainability and ensures buy-in. Engagement with line ministries of education, agriculture, health, social affairs and interior, and with municipalities, helped UNIFIL interventions complement national recovery efforts, address gaps and avoid duplication, particularly in underserved and crisis-affected areas |
|  | • Quick-impact projects must respond to rapidly changing conditions. Following the October 2023 hostilities, displaced and affected communities required flexible interventions, from supporting women to restoring basic infrastructure. Projects were adapted to the needs of populations both inside and outside the immediate area of operations. As the security situation stabilizes, quick-impact projects will transition from crisis response to recovery, requiring close coordination with local authorities, continuous field engagement and reassessment of priorities to support rebuilding communities and maintain the Force’s credibility |
|  | Gender inclusion remains critical even in crisis. UNIFIL engagement with women ensured that consultations informed education, health and livelihood projects. Over $117,000 was allocated to women-focused initiatives, reinforcing community trust and enhancing the relevance and effectiveness of interventions. |
| The Advisory Committee is not fully convinced that the scale of the construction project and the number of hard-wall buildings planned for construction in the first year and in subsequent years is feasible, as indicated in the planned timeline. The Committee is of the view that enhanced support and oversight by United Nations Headquarters is required as regards the planning, management and construction of the hard-wall structures, in particular in the light of the situation in the area of operations of the Force. The Committee trusts that an update on the construction project will be provided to the General Assembly at the time of its consideration of the present report and that regular updates, including timelines, will be provided in the context of future budget submissions (para. 43). | Construction projects were discontinued in connection with the drawdown and withdrawal of UNIFIL as from January 2027. |
| The Advisory Committee notes the efforts of the Force to improve its environmental footprint and trusts that further efficiency gains will be generated from energy initiatives, as well as other environmental initiatives, and will be reflected in future reports (para. 44). | Initiatives were discontinued in connection with the drawdown and withdrawal of UNIFIL as from January 2027. |
| The Advisory Committee expresses concern regarding the destruction of UNIFIL installations and assets and recommends that the General Assembly request the Secretary-General to provide a comprehensive assessment of the damage and detailed information on the full cost of all damage experienced by the Force, once available. The Committee trusts that the information will be provided to the Assembly in the context of the next budget submission (para. 49). | Following the October 2023 hostilities, UNIFIL sustained damage across several contingents and operational areas. One contingent reported the complete destruction of one tactical vehicle with a fair market value of $319,300. A second contingent sustained damages to an armoured personnel carrier, a troop-carrying vehicle and a utility vehicle, with total estimated costs amounting to $139,700. A third contingent reported damage to one utility truck valued at $33,500 and a water trailer valued at $2,250. In addition, damages to facilities and infrastructure were assessed at $104,700, while damages to information technology amounted to $72,700. |

Annex

Organization charts

Head of Mission/Force Commander

(4 posts)

1 ASG,

1 NPO, 2 NGS

Military Staff

UNIFIL Headquarters

Strategic Communications and Public Information Section

(10 posts)

1 P-5, 1 P-3,

1 FS, 5 NPO, 2 NGS

Deputy Head of Mission/

Director of Political and Civil Affairs

(6 posts)

1 D-1, 1 P-4, 1 P-3, 1 FS, 1 NPO, 1 NGS

Chief of Staff (Military)

Office of the

Principal Coordinator

(7 posts)

1 P-5, 2 P-4, 2 P-3,

1 FS, 1 NGS

Legal Affairs Section

(6 posts)

1 P-5, 1 P-4, 1 P-3, 1 FS, 1 NPO, 1 NGS

Security Section

(38 posts)

1 P-5, 1 P-4, 1 P-3, 17 FS, 2 NPO, 16 NGS

Regional Conduct and Discipline Section

(6 posts)

1 P-5, 2 P-4, 1 P-3, 2 FS

Operations and Resource

Management

Supply Chain

Management

Service Delivery Management

Director of Mission Support

(385 posts)

1 D-2, 9 P-5, 14 P-4, 13 P-3, 3 P-2, 71 FS, 14 NPO, 260 NGS

Mine Action Unit

(2 posts)

1 P-4a, 1 NGSa

A.	Substantive

a	General temporary assistance.

B.	Support

Abbreviations: ASG, Assistant Secretary-General; FS, Field Service; NGS, national General Service; NPO, National Professional Officer.

Map

__________________

__________________

The actual number of posts and positions is based on the rounded average.

The results-based budgeting outputs are available for consultation on the Umoja Analytics platform as part of efforts to streamline the volume of information presented in the new combined budget and performance report.

Missions that utilized 90 per cent or more of the number of flight hours approved for the most recent performance period can propose to maintain the same number of flight hours approved for that performance period (2024/25) in the respective categories (rotary or fixed-wing). For missions that utilized less than 90 per cent of the approved flight hours, the proposed flight hours are based on the higher of the average utilization percentage of the three most recent performance periods, as shown in the table above, and the utilization percentage of the most recent period (2024/25). The higher of those two percentages is then applied to the number of flight hours approved for the most recent performance period (2024/25) to obtain the proposed flight hours. Limited exceptions to this guidance may be considered on a case-by-case basis, should compelling justifications be provided. To provide missions with flexibility for their operating environment, total flight hours according to the policy may be distributed between the categories as required by the mission. A delayed deployment of 50 per cent is applied for new aircraft, with exceptions considered for the significant reconfiguration of an aviation fleet.

Resource variance amounts are expressed in thousands of United States dollars. Analysis is provided for variances of at least plus or minus 5 per cent or $100,000.