Eighty-first session

Items 138 and 139 of the preliminary list**

Proposed programme budget for 2027

Programme planning

*	The present document (A/81/6 (Sect. 20)/Part A), consisting of the programme plan and programme performance information (part II; see General Assembly resolution 77/267, para. 10), will be replaced by a document containing parts A and B (A/81/6 (Sect. 20)) once part B is issued.

**	A/81/50.

***	In keeping with paragraph 10 of General Assembly resolution 77/267, the part consisting of the programme plan and programme performance information (part II) is submitted through the Committee for Programme and Coordination for the consideration of the Assembly.

Proposed programme budget for 2027

Part V

Regional cooperation for development

Section 20

Economic development in Europe

Programme 17

Economic development in Europe

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| - Proposed programme plan for 2027 and programme performance in 2025*** |  |  | 3 |
| Overall orientation |  |  | 3 |
| Programme of work |  |  | 14 |
| Subprogramme 1. Environment |  |  | 14 |
| Subprogramme 2. Transport |  |  | 18 |
| Subprogramme 3. Statistics |  |  | 25 |
| Subprogramme 4. Economic cooperation and integration |  |  | 29 |
| Subprogramme 5. Sustainable energy |  |  | 33 |
| Subprogramme 6. Trade |  |  | 38 |
| Subprogramme 7. Forests and the forest industry |  |  | 43 |
| Subprogramme 8. Housing, land management and population |  |  | 48 |

A.	Proposed programme plan for 2027 and programme performance in 2025

Overall orientation

Mandates and background

20.1	The Economic Commission for Europe (ECE) is responsible for facilitating economic integration and cooperation among its member States and promoting sustainable development and economic prosperity in the ECE region. The mandate derives from the priorities established in relevant General Assembly and Economic and Social Council resolutions and decisions, including on the workplan on reform of ECE and the outcome of the review of the 2005 reform of ECE (resolutions 2006/38 and 2013/1, respectively), and Council resolution 36 (IV). As a regional entity with 56 member States and spanning across three continents, the Commission is uniquely positioned to support transboundary, intraregional and interregional cooperation, to help its member States to take bold, ambitious, accelerated, just and transformative action to advance the implementation of the 2030 Agenda for Sustainable Development and leave no one behind.

20.2	ECE will do so by continuing to leverage its core mandated functions of convener of policy dialogue and consensus builder, with a specific focus on existing and new normative frameworks and standards; adviser and provider of on-demand technical expertise, with the aim of strengthening national capacities; and custodian of legal instruments and regional public goods, including knowledge platforms. The support delivered by ECE to member States is also provided through the regular programme of technical cooperation, Development Account projects, and field and technical cooperation projects supported by voluntary contributions, in order to contribute to the objectives, strategy and results.

Strategy and external factors for 2027

20.3	The overall strategy and proposed programme of work of ECE is grounded in the shared vision and ambition of member States and the peoples of the ECE region for a just and prosperous future for all. It has been formulated in alignment with the commitments outlined in the Pact for the Future and remains anchored in multilateral frameworks, such as the 2030 Agenda, the Fourth International Conference on Financing for Development, the Programme of Action for Landlocked Developing Countries for the Decade 2024–2034 and the New Urban Agenda set forth by Member States to address economic and social challenges through sustained, equitable and people-centred development.

20.4	The strategy of the programme integrates sustainable development approaches and builds on synergies and the expected results of its subprogrammes. It leverages cross-sectoral synergies of the 2030 Agenda and collaboration among the subprogrammes of the ECE secretariat, its intergovernmental architecture and broad expert community for multi-stakeholder engagement and action towards accelerating progress in achieving the Sustainable Development Goals, including through the Regional Forum on Sustainable Development for the ECE Region and the United Nations Forum of Mayors. The programme will continue to provide support to its member States in addressing the economic and environmental challenges of achieving the Goals, with a focus on the demographic, digital and green transitions that have significant catalytic and multiplier effects.

20.5	The execution of the strategy will be realized through: (a) the facilitation of intergovernmental processes to promote consensus and cooperation, enable peer-to-peer exchanges of innovative policy solutions and good practices, and strengthen the existing and establish new norms and standards, as well as legal instruments and frameworks; (b) thought leadership and ensuring that member States have access to timely and quality evidence, including by supporting them in measuring their progress towards the achievement of the Sustainable Development Goals, and foresight-based policy and technical advice and recommendations for informed decision-making; and (c) the strengthening of capacities of national institutions to implement norms and standards and commitments outlined in multilateral agreements and ECE legal instruments to which the member States are Parties.

20.6	In 2027, the Commission’s work will continue to focus on a range of issues in the ECE region pertaining to, among others, transboundary, subregional, intraregional and interregional cooperation on economic integration and trade; transport and mobility; environmental protection and the management of natural resources; forests and forest industry; affordable and clean energy; competitiveness and public-private partnerships for sustainable development; emerging social and demographic challenges; and land management.

20.7	ECE plans further strengthening of the secretariat’s operational model by enhancing internal coordination, streamlining internal workflows and processes and reinforcing data-driven and cross-sectoral approaches, in line with action 45 (a) of the Pact for the Future for more agile, timely and impactful support to its member States, and the UN80 Initiative.

20.8	With regard to cooperation with other entities at the global, regional, national and local levels, ECE will build on its close cooperation with international and regional organizations and other regional actors to exchange knowledge, develop joint initiatives and enhance collective impact. Partnerships with the private sector and civil society organizations, think tanks and the academic sector will be strengthened to facilitate ECE policy dialogue and normative work and to engage them in the implementation of the 2030 Agenda by member States.

20.9	With regard to inter-agency coordination and liaison, ECE will continue to lead inter-agency coordination in the region, co-chairing the Regional Collaborative Platform for Europe and Central Asia to strengthen joint action on cross-cutting policy issues at the regional level. Through its strategic partnerships and collaboration with United Nations entities and international financial institutions, including through initiatives such as the United Nations Special Programme for the Economies of Central Asia, ECE will continue to deliver integrated policy advice and regional perspectives globally. At the country level, ECE will collaborate with resident coordinators and United Nations country teams to support the implementation of joint programmes, aligned with national priorities and the United Nations Sustainable Development Cooperation Frameworks. The programme will also foster interregional, South-South and triangular cooperation.

20.10	With regard to the external factors, the overall plan for 2027 is based on the following planning assumptions:

(a)	ECE member States continue to actively engage and support sustainable development initiatives and related intergovernmental processes and to prioritize regional and subregional cooperation and integration for shared development outcomes;

(b)	All relevant stakeholders maintain the political will and commitment to multilateral cooperation and the implementation of ECE legal instruments, norms and standards;

(c)	Sufficient resources are available for the implementation of planned activities.

20.11	Guided by its corporate policy and action plan on gender equality and the empowerment of women, ECE integrates a gender perspective into its results, deliverables and operational model that enables their delivery, as appropriate, as indicated, for example, in the programme performance for 2025 under subprogramme 6. In doing so, ECE aims to support member States in achieving commitments outlined under Sustainable Development Goal 5 and targets of other Goals relating to gender equality and women’s empowerment.

20.12	In line with the United Nations Disability Inclusion Strategy, ECE will continue to ensure that disability inclusion is mainstreamed into its operational activities, deliverables and results, as appropriate.

Adjustments arising from the UN80 Initiative

20.13	The proposed programme plan for 2027 reflects changes arising from the UN80 Initiative. In particular, the tables of deliverables reflect updated deliverables for 2026, in line with the approved programme budget for 2026.

20.14	ECE will be guided by any future decisions taken in the context of the UN80 Initiative, in accordance with the applicable rules and procedures, including decisions, resolutions and established practice of the competent intergovernmental organs. This includes, among others, any decisions concerning proposals for strengthening collaboration with the United Nations Conference on Trade and Development, the Department of Economic and Social Affairs and the other regional commissions through joint mechanisms. ECE will jointly explore options for strengthening macroeconomic analysis capacities, with a view to contributing more harmonized analysis and policy support to Member States. ECE will also be guided by the competent intergovernmental organs on the ongoing right-sizing and right-servicing exercise within ECE.

Legislative mandates

20.15	The list below, which was reviewed in the preparation of the proposed programme budget, provides all mandates entrusted to the programme.

General Assembly resolutions

| 66/288 | The future we want |
| --- | --- |
| 67/10 | Cooperation between the United Nations and the Eurasian Economic Community |
| 69/213 | Role of transport and transit corridors in ensuring international cooperation for sustainable development |
| 69/277 | Political declaration on strengthening cooperation between the United Nations and regional and subregional organizations |
| 69/283 | Sendai Framework for Disaster Risk Reduction 2015–2030 |
| 69/313 | Addis Ababa Action Agenda of the Third International Conference on Financing for Development |
| 70/1 | Transforming our world: the 2030 Agenda for Sustainable Development |
| 71/256 | New Urban Agenda |
| 72/279 | Repositioning of the United Nations development system in the context of the quadrennial comprehensive policy review of operational activities for development of the United Nations system |
| 73/195 | Global Compact for Safe, Orderly and Regular Migration |
| 75/12 | Cooperation between the United Nations and the Black Sea Economic Cooperation Organization |
| 75/290 A and B | Review of the implementation of General Assembly resolution 72/305 on the strengthening of the Economic and Social Council |
|  | Review of the implementation of General Assembly resolutions 67/290 on the format and organizational aspects of the high-level political forum on sustainable development and 70/299 on the follow-up and review of the 2030 Agenda for Sustainable Development at the global level |
| 77/289 | Political declaration of the high-level meeting on the midterm review of the Sendai Framework for Disaster Risk Reduction 2015–2030 |
| 78/9 | Commemoration of the twenty-fifth anniversary of the United Nations Special Programme for the Economies of Central Asia |
| 78/162 | Development cooperation with middle-income countries |
| 78/182 | Follow-up to the Fourth World Conference on Women and full implementation of the Beijing Declaration and Platform for Action and the outcome of the twenty-third special session of the General Assembly |
| 79/1 | The Pact for the Future |
| 79/11 | Cooperation between the United Nations and the Organization for Democracy and Economic Development – GUAM |
| 79/135 | Cooperation between the United Nations and the Central European Initiative |
| 79/194 | Information and communication technologies for sustainable development |
| 79/214 | Implementation of the outcomes of the United Nations Conferences on Human Settlements and on Housing and Sustainable Urban Development and strengthening of the United Nations Human Settlements Programme (UN-Habitat) |
| 79/223 | Women in development |
| 79/226 | Quadrennial comprehensive policy review of operational activities for development of the United Nations system |
| 79/233 | Programme of Action for Landlocked Developing Countries for the Decade 2024–2034 |
| 79/323 | Sevilla Commitment |
| 79/326 | Cooperation between the United Nations and the Commonwealth of Independent States |
| 79/330 | Cooperation between the United Nations and the Economic Cooperation Organization |
| 80/5 | Doha Political Declaration of the “World Social Summit” under the title “the Second World Summit for Social Development” |
| 80/129 | Follow-up to and implementation of the outcomes of the International Conferences on Financing for Development |
| 80/131 | The pivotal role of reliable and stable energy connectivity in driving sustainable development |
| 80/135 | Promoting sustainable consumption and production patterns for the implementation of the 2030 Agenda for Sustainable Development, building on Agenda 21 |
| 80/137 | Disaster risk reduction |
| 80/142 | Ensuring access to affordable, reliable, sustainable and modern energy for all |
| 80/147 | Science, technology and innovation for sustainable development |
| 80/151 | Follow-up to the Third United Nations Conference on Landlocked Developing Countries |
| 80/156 | South-South cooperation |
| 80/157 | Agriculture development, food security and nutrition |

Economic and Social Council resolutions

| 36 (IV) | Economic Commission for Europe |
| --- | --- |
| 1998/46 | Further measures for the restructuring and revitalization of the United Nations in the economic, social and related fields |
| 2006/38 | Workplan on reform of the Economic Commission for Europe and revised terms of reference of the Commission |
| 2013/1 | Outcome of the review of the 2005 reform of the Economic Commission for Europe |
| 2023/4 | Science, technology and innovation for development |
| 2025/4 | Mainstreaming a gender perspective into all policies and programmes in the United Nations system |

Economic Commission for Europe decisions

| B (66) | Endorsement of the Geneva Charter on Sustainable Housing |
| --- | --- |
| D (70) | Extension of the mandate of the Regional Forum on Sustainable Development |
| A (71) | Climate action and resilient infrastructure for a sustainable future |
| B (71) | Sequential review procedure of the programme of work |
| F (71) | Economic and social effects of Russia’s aggression against Ukraine |

Subprogramme 1

Environment

General Assembly resolutions

| 2994 (XXVII) | United Nations Conference on the Human Environment |
| --- | --- |
| 67/291 | Sanitation for All |
| 70/204 | International Strategy for Disaster Reduction |
| 76/300 | The human right to a clean, healthy and sustainable environment |
| 77/334 | Follow up to the United Nations Conference on the Midterm Comprehensive Review of the Implementation of the Objectives of the International Decade for Action, “Water for Sustainable Development”, 2018–2028 |
| 78/327 | Modalities of the 2026 United Nations Water Conference to Accelerate the Implementation of SDG 6: Ensure availability and sustainable management of water and sanitation for all |
| 80/141 | Education for sustainable development in the framework of the 2030 Agenda for Sustainable Development |
| 80/216 | The human rights to safe drinking water and sanitation |

Economic and Social Council resolutions

| 2023/21 | Implementation of the rapid response mechanism for the protection of environmental defenders under the Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters (Aarhus Convention) |
| --- | --- |

| 2025/27 | Multilingualism in meetings under the Convention on the Protection and Use of Transboundary Watercourses and International Lakes |
| --- | --- |

Economic Commission for Europe decisions

| ECE/BATUMI. CONF/2016/2/ Add.2 | Batumi Ministerial Statement on Education for Sustainable Development adopted by the High-level Meeting of Education and Environment Ministries of the region of ECE |
| --- | --- |
| ECE/CEP/2020/2 | Report of the Committee on Environmental Policy on its twenty-sixth session |
| ECE/AC.21/2021/ 2-EUCHP2018924/ 4.3.2 | Report of the High-level Meeting on Transport, Health and Environment and of the special session of the Steering Committee of the Transport, Health and Environment Pan-European Programme |
| ECE/NICOSIA. CONF/2022/2/ Add.1 | Declaration by ministers of the region of ECE |
| ECE/NICOSIA. CONF/2022/2/ Add.2 | Nicosia Ministerial Statement on Education for Sustainable Development adopted by the High-level Meeting of Education and Environment Ministries of the region of ECE |
| ECE/CEP/2023/2 | Report of the Committee on Environmental Policy on its twenty-eighth session |
| ECE/CEP/2025/2 | Report of the Committee on Environmental Policy on its thirtieth session |

Relevant decisions of the governing bodies of the multilateral environmental agreements of the Economic Commission for Europe

| ECE/MP.EIA/34-ECE/MP.EIA/ SEA/15 and Add.1, Add.2 and Add.3 | Report of the Meeting of the Parties to the Convention on Environmental Impact Assessment in a Transboundary Context on its ninth session, and the Meeting of the Parties to the Convention on Environmental Impact Assessment in a Transboundary Context serving as the Meeting of the Parties to the Protocol on Strategic Environmental Assessment on its fifth session |
| --- | --- |
| ECE/MP.WAT/75 and Add.1 and Add.2 | Report of the Meeting of the Parties to the Convention on the Protection and Use of Transboundary Watercourses and International Lakes on its tenth session |
| ECE/CP.TEIA/47 and Add.1 | Report of the Conference of the Parties to the Convention on the Transboundary Effects of Industrial Accidents on its thirteenth meeting |
| ECE/MP.WH/27 and Add.1 and Add.2 | Report of the Meeting of the Parties to the Protocol on Water and Health to the Convention on the Protection and Use of Transboundary Watercourses and International Lakes on its seventh session |
| ECE/MP.PRTR/ 2025/2 and Add.1 | Report of the Meeting of the Parties to the Protocol on Pollutant Release and Transfer Registers to the Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters on its fifth session |
| ECE/MP.PP/ 2025/16-ECE/ MP.PRTR/2025/ 13 and Add.1 | Report of the Joint High-level Segment of the eighth session of the Meeting of the Parties to the Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters and of the fifth session of the Meeting of the Parties to the Protocol on Pollutant Release and Transfer Registers, and the Geneva Declaration on advancing public rights to tackle the triple planetary crisis in the face of geopolitical tensions , adopted by the two Meetings of the Parties |
| ECE/EB.AIR/ 158 and Add.1 | Report of the Executive Body for the Convention on Long-range Transboundary Air Pollution on its forty-fifth session |

Subprogramme 2

Transport

General Assembly resolutions

| 70/197 | Towards comprehensive cooperation among all modes of transport for promoting sustainable multimodal transit corridors |
| --- | --- |
| 77/286 | World Sustainable Transport Day |
| 78/148 | Strengthening the links between all modes of transport to achieve the Sustainable Development Goals |
| 78/290 | Improving global road safety |
| 80/132 | United Nations Decade of Sustainable Transport 2026–2035 |

Economic and Social Council resolutions

| 1999/65 | Reconfiguration of the Committee of Experts on the Transport of Dangerous Goods into a Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals |
| --- | --- |
| 2013/7 | Europe-Africa fixed link through the Strait of Gibraltar |
| 2022/2 | Revised terms of reference of the Inland Transport Committee of the Economic Commission for Europe |
| 2023/5 | Work of the Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals |
| 2025/21 | Work of the Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals |

Economic Commission for Europe decisions

| ECE/AC.21/2014/2 | Report of the High-level Meeting on Transport, Health and Environment on its fourth session |
| --- | --- |
| ECE/TRANS/288 and Add.2; ECE/TRANS/344 | Reports of the Inland Transport Committee on its eighty-first session; the adoption of the ITC Strategy 2030 and the adoption of ITC Strategy on Reducing Greenhouse Gas Emissions from Inland Transport |

| K (70) | Matters related to sustainable transport and mobility |
| --- | --- |

Decisions of the treaty bodies of United Nations transport agreements

| E/ECE/TRANS/ 505/Rev.3 | 1958 Agreement Concerning the Adoption of Harmonized Technical United Nations Regulations for Wheeled Vehicles, Equipment and Parts which can be Fitted and/or be Used on Wheeled Vehicles and the Conditions for Reciprocal Recognition of Approvals Granted on the Basis of these United Nations Regulations |
| --- | --- |
| ECE/RCTE/ CONF/4 | 1997 Agreement concerning the adoption of uniform conditions for periodical technical inspections of wheeled vehicles and the reciprocal recognition of such inspections |
| ECE/TRANS/132 | 1998 Agreement concerning the establishment of global technical regulations for wheeled vehicles, equipment and parts which can be fitted and/or used on wheeled vehicles |
| ECE/TRANS/ ADN/CONF/10/ Add.1 | European Agreement concerning the International Carriage of Dangerous Goods by Inland Waterways |
| ECE/TRANS/ WP.30/AC.2/125 | Report of the Administrative Committee for the TIR Convention 1975 on its sixty-first session |
| ECE/TRANS/ WP.30/AC.2/147 and Corr.1 | Report of the Administrative Committee for the TIR Convention 1975 on its seventy-second session |
| ECE/TRANS/ WP.30/AC.2/157 | Report of the Administrative Committee for the TIR Convention 1975 on its seventy-seventh session (February 2022): AC.2, in line with annex 11, article 5, adopted the eTIR concepts and the eTIR functional specifications, including the amendments adopted by TIB at its first session. This provides a complete legal and technical basis for those countries that are willing to implement the eTIR procedure |
| ECE/TRANS/ WP.30/AC.2/TIB/2 | Report of the Technical Implementation Body (TIB) of the Administrative Committee for the TIR Convention, 1975, on its first session: TIB for eTIR implementation, adopted version 4.3 of the eTIR technical specifications and confirmed their alignment with version 4.3 of the eTIR concepts and the eTIR functional specifications |

Subprogramme 3

Statistics

General Assembly resolutions

| 68/261 | Fundamental Principles of Official Statistics |
| --- | --- |
| 69/282 | World Statistics Day |
| 71/313 | Work of the Statistical Commission pertaining to the 2030 Agenda for Sustainable Development |

Economic and Social Council resolutions and decisions

| 2006/6 | Strengthening statistical capacity |
| --- | --- |
| 2020/5 | Strengthening coordination of the statistical programmes in the United Nations system |
| 2022/3 | Ensuring that the work in the field of statistics and data is adaptive to the changing statistical and data ecosystem |
| 2023/325 | Report of the Statistical Commission on its fifty-fourth session (Statistical Commission decision 54/119: Data stewardship) |
| 2024/312 | Report of the Statistical Commission on its fifty-fifth session (Statistical Commission decisions: 55/106: Governance statistics; 55/112: Gender statistics; 55/120: Open data; 55/121: International Comparison Programme) |
| 2025/12 | System of National Accounts 2025 |
| 2025/13 | 2030 World Population and Housing Census Programme |
| 2025/26 | Strengthening integration of statistics and geography |
| 2025/315 | Report of the Statistical Commission on its fifty-sixth session (Statistical Commission decisions: 56/101: National accounts; 56/102: Population and housing censuses; 56/107: Data and indicators for the 2030 Agenda for Sustainable Development; 56/108: Social and demographic statistics, 56/110. Work and employment statistics; 56/111 Economic statistics; 56/118: Household surveys; 56/122: World Statistics Day; 56/124 Environment and climate change statistics) |

Economic Commission for Europe decisions

| ECE/EX/2023/ L.1 | Decisions relating to the Conference of European Statisticians (terms of reference for steering group on statistics for Sustainable Development Goals) |
| --- | --- |
| ECE/EX/2024/ L.1 | Decisions relating to the Conference of European Statisticians (terms of reference for the high-level group for the modernization of official statistics) |
| ECE/EX/2024/ L.15 | Decisions relating to the Conference of European Statisticians (terms of reference for steering group on statistics on population and migration for the period 2024–2027 and for steering group on statistics on children for the period 2024–‍2027) |

| ECE/EX/2025/ L.16 | Decisions relating to the Conference of European Statisticians (terms of reference for steering group on measuring poverty and inequality, for steering group on consumer price indices and for task force on indicators for monitoring action on ageing) |
| --- | --- |
| ECE/CES/105 ECE/CES/107 ECE/CES/109 | Reports of the Conference of European Statisticians plenary sessions |

Subprogramme 4

Economic cooperation and integration

General Assembly resolutions

| 79/228 | Towards global partnerships: a principle-based approach to enhanced cooperation between the United Nations and all relevant partners |
| --- | --- |
| 80/118 | Information and communication technologies for sustainable development |
| 80/127 | Promoting investments for sustainable development |

Economic and Social Council resolutions and decisions

| 2024/13 | Assessment of the progress made in the implementation of and follow-up to the outcomes of the World Summit on the Information Society |
| --- | --- |
| 2025/19 | Science, technology and innovation for development |

Economic Commission for Europe decisions

| ECE/EX/2015/L.8 | Draft decision on renaming the Committee on Economic Cooperation and Integration and on its revised terms of reference (revising terms of reference of the Committee on Innovation, Competitiveness and Public-Private Partnerships) |
| --- | --- |

Subprogramme 5

Sustainable energy

General Assembly resolutions

| 69/225 | Promotion of new and renewable sources of energy |
| --- | --- |

Economic and Social Council resolutions and decisions

| 2011/222 | Best Practice Guidance for Effective Methane Drainage and Use in Coal Mines |
| --- | --- |
| 2021/249 | Best Practice Guidance for Effective Methane Recovery and Use from Abandoned Coal Mines |
| 2021/250 | Updated United Nations Framework Classification for Resources |
| 2023/18 | Best Practice Guidance for Effective Management of Coal Mine Methane at National Level: Monitoring, Reporting, Verification and Mitigation |

| 2023/19 | United Nations Resource Management System Principles and Requirements |
| --- | --- |
| 2023/20 | Request to strengthen the role of the secretariat of the Economic Commission for Europe in supporting member States in building resilient energy systems and modernizing resource management systems |

Economic Commission for Europe decisions

| E (70) | Building resilient energy systems |
| --- | --- |
| F (70) | Decision to study finance for energy-related climate change activities in the region of the Economic Commission for Europe, particularly related to critical raw materials |
| G (70) | Best Practice Guidance for Effective Management of Coal Mine Methane at National Level: Monitoring, Reporting, Verification and Mitigation |
| H (70) | United Nations Resource Management System Principles and Requirements |
| I (70) | Request to strengthen the role of the secretariat of the Economic Commission of Europe in supporting member States in building resilient energy systems and modernizing resource management systems |
| ECE/ENERGY/ 156 | Report of the Committee on Sustainable Energy on its thirty-fourth session |

Subprogramme 6

Trade

General Assembly resolutions

| 79/201 | Entrepreneurship for sustainable development |
| --- | --- |
| 80/121 | International trade and development |
| 80/133 | Agricultural technology for sustainable development |

Economic and Social Council resolutions and decisions

| 1991/76 | Promotion of interregional cooperation in the area of international trade facilitation |
| --- | --- |
| 1997/225 | Economic Commission for Europe Recommendation 25, entitled “Use of the UN/EDIFACT Standard” |
| 2020/18 | Revised terms of reference of the Steering Committee on Trade Capacity and Standards of the Economic Commission for Europe |

Economic Commission for Europe decisions

| ECE/TRADE/210 | Report of the forty-fifth session of the Committee on the Development of Trade |
| --- | --- |
| ECE/EX/4 (2000) | Recommendations concerning the United Nations Centre for Trade Facilitation and Electronic Business |
| ECE/CTCS/WP.7/ 2015/22 | Geneva Understanding on Agricultural Quality Standards |
| ECE/EX/2017/L.7 | Decision approving the consolidated United Nations Centre for Trade Facilitation and Electronic Business mandate and terms of reference |
| ECE/EX/2023/ L.12 | Decisions relating to the Steering Committee on Trade Capacity and Standards and its subsidiary bodies (revised terms of reference of the Working Party on Regulatory Cooperation and Standardization Policies (WP.6)) |
| ECE/CTCS/ 2024/2 | Report of the Steering Committee on Trade Capacity and Standards on its ninth session (mandate extension of WP.6 subsidiary bodies) |
| ECE/EX/2024/L.9 | Decisions relating to the Steering Committee on Trade Capacity and Standards and its subsidiary bodies (revised terms of reference of the Working Party on Agricultural Quality Standards (WP.7)) |
| ECE/EX/2025/L.8 | Decisions relating to the United Nations Centre for Trade Facilitation and Electronic Business (mandate extension of the Team of Specialists on Environmental, Social and Governance Traceability of Sustainable Value Chains in the Circular Economy) |

| ECE/EX/2025/L.13 | Decision relating to the Steering Committee on Trade Capacity and Standards (terms of reference of the Group of Experts on Risk Management and Market Surveillance) |
| --- | --- |

Subprogramme 7

Forests and the forest industry

General Assembly resolutions

| 67/200 | International Day of Forests |
| --- | --- |
| 71/286 | United Nations forest instrument |
| 73/284 | United Nations Decade on Ecosystem Restoration (2021–2030) |
| 78/169 | Natural plant fibres and sustainable development |
| 78/320 | Fostering sustainable forest management, including afforestation and reforestation, in degraded lands, including drylands, as an effective solution to environmental challenges |

| 79/283 | United Nations Decade for Afforestation and Reforestation in line with Sustainable Forest Management (2027–2036) |
| --- | --- |
| 80/140 | Implementation of the Convention on Biological Diversity and its contribution to sustainable development |

Economic and Social Council resolutions

| 2015/33 | International arrangement on forests beyond 2015 |
| --- | --- |
| 2017/4 | United Nations strategic plan for forests 2017–2030 and quadrennial programme of work of the United Nations Forum on Forests for the period 2017–2020 |
| 2020/14 | Outcome of the fifteenth session of the United Nations Forum on Forests |
| 2024/15 | Outcome of the nineteenth session of the United Nations Forum on Forests (programme of work of the United Nations Forum on Forests for the period 2025–2028) |

Economic Commission for Europe decisions

| ECE/TIM/2017/2 | Report of the joint session of the Committee on Forests and the Forest Industry and the European Forestry Commission (terms of reference of the ECE Committee on Forests and the Forest Industry) |
| --- | --- |
| ECE/TIM/2021/2 | Report of the seventy-ninth session of the Economic Commission for Europe Committee on Forests and the Forest Industry and the forty-first session of the Food and Agriculture Organization European Forestry Commission (terms of reference of the Working Party on Forest Statistics, Economics and Management ) |

| ECE/EX/2026/L.2 | Decisions relating to the Committee on Forests and the Forest Industry (mandate of the Team of Specialists on Monitoring Sustainable Forest Management until 2027, of the Team of Specialists on Sustainable Forest Products until 2027 and of the Team of Specialists on Forest Products- and Wood Energy Statistics until 2027) |
| --- | --- |

Subprogramme 8

Housing, land management and population

General Assembly resolutions

| 75/131 | United Nations Decade of Healthy Ageing (2021–2030) |
| --- | --- |
| 80/175 | Inclusive policies and programmes to address homelessness, including in the aftermath of the coronavirus disease (COVID-19) |

| 80/179 | Follow-up to the Second World Assembly on Ageing |
| --- | --- |

Economic and Social Council resolutions and decisions

| 2020/19 | Change of name and revised terms of reference of the Working Group on Ageing of the Economic Commission for Europe |
| --- | --- |
| 2025/8 | Modalities for the fifth review and appraisal of the Madrid International Plan of Action on Ageing, 2002 |

| 2025/25 | Strengthening the United Nations Forum of Mayors |
| --- | --- |

Economic Commission for Europe decisions

| ECE/AC.23/ 2002/2/Rev.6 | Regional Implementation Strategy for the Madrid International Plan of Action on Ageing, 2002 |
| --- | --- |
| ECE/HBP/190 | Report of the Committee on Housing and Land Management on its seventy-eighth session (Geneva Ministerial Declaration on Sustainable Housing and Urban Development) |
| ECE/HBP/208; ECE/HBP/213 | Report of the Committee on Urban Development, Housing and Land Management (eighty-second and eighty-third sessions) |
| ECE/AC.30/2022/2 | Report of the Ministerial Conference on Ageing “A Sustainable World for All Ages: Joining Forces for Solidarity and Equality Opportunities Throughout Life” |
| ECE/WG.1/2023/2 | Report on the sixteenth meeting of the Standing Working Group on Ageing, which adopted the Programme of Work of the Standing Working Group on Ageing, 2023–2027 |
| ECE/EXCOM/ CONCLU/131 | Extension of mandate of the Working Party on Land Administration until 2030 and approval of its terms of reference for the period 2025–2030 (ECE/HBP/2023/5) |
| ECE/EXCOM/ CONCLU/136 | Extension of the mandate of the Real Estate Market Advisory Group for Sustainable, Climate-Neutral and Energy-Efficient Buildings and Cities and its terms of reference for the period 2025–2026 (ECE/HBP/2024/8) |
| ECE/HBP/2025/2 | Report of the Committee on Urban Development, Housing and Land Management on its eighty-sixth session (ministerial commitments on housing affordability and sustainability) |

Deliverables

20.16	Table 20.1 lists the cross-cutting deliverables of the programme.

Table 20.1

Cross-cutting deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 40 | 40 | 23 | 35 |
| 1. The Economic Commission for Europe | 13 | 11 | – | 11 |
| 2. Regional Forum on Sustainable Development for the region of the Economic Commission for Europe | 2 | 2 | 2 | 2 |
| 3. The ECE Executive Committee | 25 | 27 | 21 [25] | 22 |
| Substantive services for meetings (number of three-hour meetings) | 26 | 21 | 18 | 23 |
| 4. The Economic Commission for Europe | 4 | 4 | - | 4 |
| 5. Regional Forum on Sustainable Development for the region of the Economic Commission for Europe | 3 | 4 | 4 | 4 |
| 6. The ECE Executive Committee | 10 | 6 | 5 [6] | 6 |
| 7. The Working Group on Gender and Sustainable Development Goals of the United Nations Special Programme for the Economies of Central Asia | 2 | – | 2 | 2 |
| 8. The Fifth Committee | 1 | 1 | 1 | 1 |
| 9. The Advisory Committee on Administrative and Budgetary Questions | 1 | 1 | 1 | 1 |
| 10. The Committee for Programme and Coordination | 1 | 1 | 1 | 1 |
| 11. The Regional Collaborative Platform | 4 | 4 | 4 [6] | 4 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Publications (number of publications) | 2 | 2 | 1 | 1 |
| 12. On gender equality and sustainable development | 1 | 1 | – | – |
| 13. ECE annual highlights report | 1 | 1 | 1 | 1 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advice to and consultations with member States and United Nations country teams to facilitate implementation of the United Nations Sustainable Development Cooperation Framework process in up to 3 programme countries. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: promotional materials; information materials for United Nations Road Safety Fund advocacy campaign and awareness-raising material; and films on ECE activities. |  |  |  |  |
| External and media relations: ECE weekly newsletter; approximately 200 press releases per year; and 2 press conferences on ECE activities. |  |  |  |  |
| Digital platforms and multimedia content: ECE website; ECE Executive Committee, the gender equality and the technical cooperation activities websites; and news on ECE activities on four social media platforms. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

Evaluation activities

20.17	The evaluation planned for 2025 was not completed owing to the lack of required staff capacity and resources. Nevertheless, ECE focused on the implementation of the recommendations from previous evaluations, including the one conducted by the Office of Internal Oversight Services in 2023, which also guided the programme plan for 2027.

20.18	In response to the results of the evaluations referenced above, ECE will focus on strengthening programme planning through a review of subprogramme-specific strategies and results frameworks, encompassing initiatives supported by the regular budget, the regular programme for technical cooperation, the Development Account and voluntary contributions. It will also continue to adjust its modes of programme delivery and operational model, including by leveraging modern technologies and cross-cutting initiatives.

20.19	A programme-level evaluation of the ECE normative function is planned for 2027.

Programme of work

Subprogramme 1

Environment

Objective

20.20	The objective, to which the subprogramme contributes, is to improve environmental governance and performance for safeguarding the environment and health.

Strategy

20.21	To contribute to the objective, the subprogramme will:

(a)	Undertake environmental performance reviews and environmental assessments and assist member States in the implementation of recommendations and monitoring of the resulting impact on national policies;

(b)	Standardize indicators for evidence-based decision-making and environmental assessments and support member States in generating, disseminating and providing open access to environmental information;

(c)	Provide technical advice to member States and strengthen national capacities, including through the facilitation of peer-to-peer exchanges of good practices, on matters pertaining to (i) environmental policymaking, (ii) environmental performance, (iii) environmental monitoring and assessments, (iv) the mainstreaming of environmental concerns into economic and social development policies, (v) education for sustainable development, (vi) air quality, (vii) water, (viii) industrial safety, (ix) public participation and (x) impact assessment;

(d)	Provide platforms for policy dialogue, consensus-building and advocacy to assist member States in addressing priority and emerging environmental issues and in developing region-wide approaches, including for sustainable and resilient infrastructure, while ensuring effective and inclusive access to information, public participation in decision-making and access to justice.

20.22	In addition, the subprogramme, in its role of secretariat to eight multilateral environmental agreements, will support existing Parties in their implementation, advocate for and facilitate the accession of additional member States and promote synergies among these agreements. Moreover, the subprogramme, in its role of co-custodian for Sustainable Development Goal indicator 6.5.2, will support member States in identifying gaps and opportunities in and advancing cooperation on the protection and use of transboundary water resources.

20.23	Furthermore, in its commitment to drive cross-sectoral, cross-cutting and joint initiatives, the subprogramme will continue to implement the ECE Strategy for Education for Sustainable Development and the Transport, Health and Environment Pan-European Programme.

20.24	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 3, 4, 6, 9, 11–13 and 15–17 and is expected to result in:

(a)	Improved environmental governance and performance, more effective development and implementation of environmental legislation and policies, enhanced integration of environmental concerns into national sectoral policies, and a better response to current and emerging environmental challenges;

(b)	Strengthened implementation of multilateral environmental commitments and their increased geographical coverage.

Programme performance in 2025

Member States apply foresight approaches to develop recommendations for environmental policies to address gaps and emerging issues

20.25	Urbanization, demographic change, digitalization and trends in globalization interact with and may, if not addressed holistically, potentially amplify the adverse effects of climate change and environmental degradation on environmental and socioeconomic systems. The subprogramme, in collaboration with a higher education institution, facilitated science-policy dialogue and developed guidance for environmental policymakers in the region on applying foresight approaches to support the early identification of emerging trends and gaps in sectoral policies that have an impact on the achievement of climate-related commitments and goals. Subsequently, the subprogramme supported member States and enhanced their capacity to identify priority areas for action and formulate coherent environmental policies aimed at gaps and emerging issues.

20.26	Progress towards the objective is presented in the performance measure below (see table 20.2).

Table 20.2

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| – | – | Member States applied foresight approaches to develop recommendations for environmental policies to address gaps and emerging issues |

Planned results for 2027

Result 1: modernized database on pollutants to enable responsive fact-based decisions

Programme performance in 2025 and target for 2027

20.27	The subprogramme’s work contributed to the adoption of a decision on modernizing pollutant release and transfer registers by the Meeting of the Parties to the Protocol on Pollutant Release and Transfer Registers, which met the planned target.

20.28	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.3).

Table 20.3

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| Draft decision on modernizing pollutant release and transfer registers agreed by the Protocol’s Bureau | Draft decision on modernizing pollutant release and transfer registers approved by the Working Group of the Parties to the Protocol on Pollutant Release and Transfer Registers | Meeting of the Parties to the Protocol adopted a decision on modernizing pollutant release and transfer registers | Wide dissemination and continuous implementation of the decision on modernizing pollutant release and transfer registers by Parties and interested member States | At least five member States implement measures to modernize pollutant release and transfer registers in line with the adopted decision |

Result 2: strengthened pan-European environmental knowledge base for informed policymaking

Programme performance in 2025 and target for 2027

20.29	The subprogramme’s work contributed to the approval of indicators for the next assessment by the Committee on Environmental Policy, which met the planned target.

20.30	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.4).

Table 20.4

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| – | The Committee on Environmental Policy welcomed the progress made in elaborating the concept of the eighth pan-European environmental assessment | The Committee on Environmental Policy approved indicators for the next assessment | The Committee on Environmental Policy considers the final draft of the eighth pan-European environmental assessment | Draft ministerial declaration, to be considered for adoption at the tenth Environment for Europe Ministerial Conference, addresses the findings of the eighth pan-European environmental assessment |

Result 3: improved reporting of air emissions data

Proposed programme plan for 2027

20.31	Reporting air emissions data is a prerequisite for assessing progress made by the Parties in meeting their commitments under the Convention on Long-range Transboundary Air Pollution. Furthermore, the reported data support modelling efforts that allow for an assessment of the effectiveness of previously adopted measures and the strengthening of existing and development of new, ambitious policies, strategies and legal instruments pertaining to emissions reduction. The subprogramme has supported Parties in generating and improving the reporting of air emissions data, including by identifying gaps in inventories.

Lessons learned and planned change

20.32	The lesson for the subprogramme was that there were opportunities to further improve data quality and completeness to support the modelling and robustness of the evidence for environmental policymaking. In applying the lesson, the subprogramme will enhance its assessments of the data submitted through informative inventory reports and evaluate the effectiveness and robustness of methodologies applied by Parties to collect and process data, with the aim of identifying gaps and challenges, as well as good practices and innovative solutions. Concurrently, it will provide technical advice to and strengthen capacities of the Parties to produce national reports on air emissions.

20.33	Expected progress towards the objective is presented in the performance measure below (see table 20.5).

Table 20.5

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| – | – | 70 per cent of Parties to the Convention on Long-range Transboundary Air Pollution submitted reports on air emissions that are of good quality or above | At least two Parties to the Convention improve the quality of their reporting on air emissions under the Convention | At least two additional Parties to the Convention improve the quality of their reporting on air emissions under the Convention |

Deliverables

20.34	Table 20.6 lists all deliverables of the subprogramme.

Table 20.6

Subprogramme 1: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 260 | 198 | 147 | 130 |
| 1. The Committee on Environmental Policy and subsidiary bodies | 20 | 16 | 16 [20] | 16 |
| 2. The Meeting of the Parties to the Convention on the Protection and Use of Transboundary Watercourses and International Lakes and subsidiary bodies and the Meeting of the Parties to the Protocol on Water and Health and subsidiary bodies | 26 | 24 | 20 [22] | 26 |
| 3. The Conference of the Parties to the Convention on the Transboundary Effects of Industrial Accidents and subsidiary bodies | 2 | 2 | 14 [15] | 2 |
| 4. The Executive Body for the Convention on Long-range Transboundary Air Pollution and subsidiary bodies | 24 | 22 | 20 [21] | 17 |
| 5. The Meeting of the Parties to the Convention on Environmental Impact Assessment in a Transboundary Context and subsidiary bodies and the Meeting of the Parties to the Convention serving as the Meeting of the Parties to the Protocol on Strategic Environmental Assessment to the Convention on Environmental Impact Assessment in a Transboundary Context and subsidiary bodies | 16 | 14 | 14 [16] | 16 |
| 6. The Meeting of the Parties to the Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters and subsidiary bodies and the Meeting of the Parties to the Protocol on Pollutant Release and Transfer Register to the Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters and subsidiary bodies | 161 | 115 | 56 [60] | 45 |
| 7. The High-level Meeting on Transport, Health and Environment and subsidiary bodies | 3 | 3 | 2 [3] | 3 |
| 8. The Steering Committee on Education for Sustainable Development | 8 | 2 | 5 [6] | 5 |
| Substantive services for meetings (number of three-hour meetings) | 243 | 190 | 192 | 180 |
| 9. The Committee on Environmental Policy and subsidiary bodies | 28 | 28 | 26 [30] | 23 |
| 10. The Parties to the Convention on the Protection and Use of Transboundary Watercourses and International Lakes and subsidiary bodies and the Parties to the Protocol on Water and Health and subsidiary bodies | 47 | 47 | 36 [38] | 38 |
| 11. The Conference of the Parties to the Convention on the Transboundary Effects of Industrial Accidents and subsidiary bodies | 19 | 15 | 16 [18] | 14 |
| 12. The Executive Body for the Convention on Long-range Transboundary Air Pollution and subsidiary bodies | 23 | 18 | 18 [21] | 17 |
| 13. The Parties to the Convention on Environmental Impact Assessment in a Transboundary Context and subsidiary bodies and the Parties to the Convention serving as the Meeting of the Parties to the Protocol on Strategic Environmental Assessment to the Convention on Environmental Impact Assessment in a Transboundary Context and subsidiary bodies | 34 | 26 | 30 [34] | 30 |
| 14. The Parties to the Convention on Access to Information, Public Participation in Decision-Making and Access to Justice in Environmental Matters and subsidiary bodies and the Parties to the Protocol on Pollutant Release and Transfer Register and subsidiary bodies | 84 | 48 | 60 [64] | 51 |
| 15. The High-level Meeting on Transport, Health and Environment and subsidiary bodies | 2 | 2 | 2 | 2 |
| 16. The Steering Committee on Education for Sustainable Development | 6 | 6 | 4 [6] | 5 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Seminars, workshops and training events (number of days) | 32 | 32 | 29 | 16 |
| 17. Workshops on environmental issues for government officials and other stakeholders in the ECE region to improve environmental governance and performance | 32 | 32 | 29 [39] | 16 |
| Publications (number of publications) | 9 | 4 | 9 | 10 |
| 18. On environmental issues and multilateral environmental agreements administered by the subprogrammeb | 9 | 4 | 9 [12] | 10 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services for some 100 government officials and other stakeholders of States participating in the United Nations Special Programme for the Economies of Central Asia on water, energy and other environmental issues. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: environmental performance review highlights. |  |  |  |  |
| External and media relations: press releases on environmental issues. |  |  |  |  |
| Digital platforms and multimedia content: website of the subprogramme. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Including progress reports and performance reviews on environmental issues listed separately under A/80/6 (Sect. 20).

Subprogramme 2

Transport

Objective

20.35	The objective, to which the subprogramme contributes, is to advance an intraregionally and interregionally sustainable inland transport (road, rail, inland waterway and intermodality) system by making it safer, cleaner, more efficient, more inclusive and more affordable, both for freight transport and people’s mobility.

Strategy

20.36	To contribute to the objective, the subprogramme will:

(a)	Service the Inland Transport Committee, its 21 working parties, 13 administrative committees and the Economic and Social Council Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals and its 2 subcommittees, as well as more than 50 expert networks. It will support the Inland Transport Committee’s coordination of its subsidiary bodies and its broader interregional role, as endorsed in the revised Inland Transport Committee terms of reference adopted by the Council (E/RES/2022/2) and promote implementation of the Inland Transport Committee strategy until 2030 and the Inland Transport Committee Strategy on Reducing Greenhouse-gas Emissions from Inland Transport;

(b)	Service, administer and further develop the international regulatory framework comprising 61 United Nations legal instruments on inland transport that enable the safe, efficient and sustainable movement of people and goods across borders, ensuring that they remain open to accession by all United Nations Member States, when and as appropriate, and that they stimulate economic growth, facilitate trade and support innovation and competitiveness. In this capacity, the subprogramme will:

(i)	Update and promote the application of vehicle regulations covering safety, environmental performance, energy efficiency, automated and electric mobility, and intelligent transport systems, thereby supporting innovation and cleaner fleets;

(ii)	Ensure the continuous updating and global alignment of the regulatory framework governing the safe transport of hazardous substances by road, rail and inland waterways, reducing risks to people, communities and the environment;

(iii)	Advance implementation of United Nations road traffic conventions and vehicle regulation agreements that help to save lives and enhance the safety of all road users;

(iv)	Continue the administration and operations of the Convention on International Transport of Goods under Cover of TIR Carnets (TIR Convention), including the implementation and operations of its electronic procedure (eTIR); the International Convention on the Harmonization of Frontier Controls of Goods; the Convention on the Contract for the International Carriage of Goods by Road and its electronic implementation (eCMR); and the Customs Convention on the Temporary Importation of Commercial Road Vehicles and preparation of its electronic carnets (eCPDs) and related conventions, to enhance supply chain efficiency, lower transaction costs and foster resilient trade connectivity;

(v)	With regard to infrastructure agreements, administer conventions on road, rail, inland waterways, combined transport and related infrastructure to promote modal integration, energy efficiency and resilience;

(c)	Provide an intergovernmental platform for policy dialogue and consensus-building through the annual sessions of the Inland Transport Committee and its subsidiary bodies. The Committee platform reviews emerging challenges, strengthens regional and interregional cooperation and promotes harmonized action through the adoption of strategies, action plans, high-level statements and resolutions that enable the full implementation of the Committee’s mandate;

(d)	Analyse trends and provide technical assistance and capacity-building to enable member States to accede to and implement legal instruments, at the request of member States and contracting Parties within and beyond the ECE region;

(e)	Facilitate horizontal and cross-sectoral initiatives, including implementation of the United Nations Decade of Sustainable Transport (see General Assembly resolution 78/148) and the Transport, Health and Environment Pan-European Programme, and promote synergies among and cooperation with key transport stakeholders, including the Special Envoy of the Secretary-General for Road Safety and the United Nations Road Safety Fund.

20.37	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 3, 5–9 and 11–13 and is expected to result in:

(a)	Enhanced efficiency, interoperability and resilience of inland transport and border-crossing operations through the implementation and digitalization of United Nations legal instruments, leading to more seamless and sustainable flows of goods and people within and across regions;

(b)	Improved road traffic safety and the overall safety of inland transport through strengthened regulatory frameworks and the effective implementation of vehicle and driver standards and regulations;

(c)	Reduced greenhouse gas emissions and environmental impacts from inland transport, accelerated progress towards net-zero emissions by 2050 and the strengthened adaptation and resilience of transport systems, guided by Inland Transport Committee strategies.

Programme performance in 2025

Open-source software enables implementation of annex 11 of the Convention on International Transport of Goods under Cover of TIR Carnets

20.38	A lack of cost-effective and adaptable digital infrastructure has impeded the implementation of annex 11 of the TIR Convention, which governs the transition to fully electronic procedures in accordance with the Convention. To date, direct interconnection to the eTIR international system, the main data exchange hub of the electronic TIR procedure, requires investment of national resources and up to a year to complete. To enable access to the eTIR procedure, the subprogramme designed an open-source, technology-neutral, secure and scalable tool, the eTIR National Application, which can be installed and deployed within two weeks on existing national systems and allows countries with limited information technology capacity to implement paperless cross-border procedures, without the need to invest into costly and lengthy national system redesign. Subsequently, the subprogramme engaged with member States to build their capacity to roll out the tool.

20.39	Progress towards the objective is presented in the performance measure below (see table 20.7).

Table 20.7

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| – | – | Republic of Moldova and Ukraine completed installation and conducted testing of the eTIR National Application |

Planned results for 2027

Result 1: increased accessions to core road safety conventions as an initial step to contribute to fewer worldwide road accident fatalities and injuries

Programme performance in 2025 and target for 2027

20.40	The subprogramme’s work contributed to four additional accessions, of Bahrain to the Convention on Road Traffic (1949), Israel to the European Agreement concerning the Work of Crews of Vehicles engaged in International Road Transport, Kyrgyzstan to the Agreement concerning the International Carriage of Dangerous Goods by Road and Uzbekistan to the Agreement concerning the Adoption of Harmonized Technical United Nations Regulations for Wheeled Vehicles, Equipment and Parts which can be Fitted and/or be Used on Wheeled Vehicles and the Conditions for Reciprocal Recognition of Approvals Granted on the Basis of these United Nations Regulations (1958), for a total of 495 accessions, which exceeded the planned target of 492. In addition, the subprogramme’s work contributed to 8 events, for a total of 18, during which member States shared challenges and good practices on road safety convention implementation, which exceeded the planned target of 14.

20.41	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.I).

Figure 20.I

Performance measure: number of contracting Parties to core United Nations road safety conventions and number of events during which member States share challenges and good practices on road safety convention implementation (cumulative)

Result 2: enhanced regulatory framework for sustainable inland transport systems

Programme performance in 2025 and target for 2027

20.42	The subprogramme’s work contributed to five additional accessions, for a total of 1,847 accessions, which exceeded the planned target of 1,844.

20.43	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.II).

Figure 20.II

Performance measure: number of contracting Parties to United Nations legal instruments on transport administered by the Economic Commission for Europe (cumulative)

–

–

Result 3: accelerated digitalization of legal instruments in inland transport

Proposed programme plan for 2027

20.44	The digitalization of legal instruments pertaining to inland transport helps to advance their implementation by contracting Parties by enhancing the efficiency, safety and security of international transport, which is a critical component of trade facilitation. The subprogramme has promoted accession to United Nations transport conventions, while supporting efforts to modernize procedures governed by these instruments.

Lessons learned and planned change

20.45	The lesson for the subprogramme was that the modernization of national and international legal frameworks and sustained investment in capacity-building, in addition to technical infrastructure, helped to accelerate implementation of electronic procedures under legal instruments. In applying the lesson, the subprogramme will prioritize support for contracting Parties in aligning and modernizing national legal frameworks, strengthening institutional coordination and building the capacities of relevant authorities to operationalize electronic procedures in a consistent and sustainable manner. The subprogramme will also develop new and promote the use of existing open-source, technology-neutral and scalable digital tools, including but not limited to the eTIR National Application, the e-CMR conceptual and functional specifications and the digitized signs and signals under the Convention on Road Signs and Signals, with the aim of enabling equitable access of all contracting Parties, including ECE programme countries, to modern transport governance systems.

20.46	Expected progress towards the objective is presented in the performance measure below (see figure 20.III).

Figure 20.III

Performance measure: number of contracting Parties to ECE legal instruments that have made the transition to electronic solutions for implementation (cumulative)

Deliverables

20.47	Table 20.8 lists all deliverables of the subprogramme.

Table 20.8

Subprogramme 2: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 1 155 | 948 | 1 012 | 1 012 |
| 1. Documentation for the Inland Transport Committee |  |  |  |  |
| (a) Inland Transport Committee and Bureau | 31 | 34 | 28 [31] | 28 |
| (b) World Forum for Harmonization of Vehicle Regulations | 550 | 485 | 472 [550] | 499 |
| (c) Working Party on the Transport of Perishable Foodstuffs | 33 | 30 | 30 [33] | 29 |
| (d) Working Party on the Transport of Dangerous Goods | 160 | 133 | 135 [160] | 135 |
| (e) Working Party on Transport Trends and Economics and subsidiary groups of experts | 28 | 22 | 26 [28] | 16 |
| (f) Working Party on Transport Statistics | 14 | 12 | 14 | 11 |
| (g) Working Party on Road Transport and subsidiary groups of experts | 26 | 20 | 18 | 17 |
| (h) Global Forum for Road Traffic Safety and subsidiary groups of experts | 20 | 9 | 17 [20] | 17 |
| (i) Working Party on Rail Transport and subsidiary groups of experts | 30 | 23 | 24 | 21 |
| (j) Working Party on Intermodal Transport and Logistics | 12 | 18 | 24 [25] | 20 |
| (k) Working Party on Inland Water Transport | 45 | 25 | 42 [45] | 38 |
| 2. Global Forum on Customs Questions Affecting Transport including Border Crossing Facilitation and subsidiary groups of expertsb | 50 | 48 | 48 [50] | 48 |
| 3. Documentation for the Economic and Social Council |  |  |  |  |
| (a) Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals | 1 | 1 | 3 [5] | 1 |
| (b) Subcommittee of Experts on the Transport of Dangerous Goods | 120 | 76 | 100 [120] | 102 |
| (c) Subcommittee of Experts on the Globally Harmonized System of Classification and Labelling of Chemicals | 32 | 10 | 28 [32] | 27 |
| 4. Documentation for the High-Level Meeting on Transport, Health and Environment | 3 | 2 | 3 | 3 |
| Substantive services for meetings (number of three-hour meetings) | 410 | 338 | 360 | 357 |
| 5. Meetings of the Inland Transport Committee |  |  |  |  |
| (a) Inland Transport Committee and Bureau | 16 | 16 | 14 [16] | 14 |
| (b) World Forum for Harmonization of Vehicle Regulations | 121 | 92 | 100 [121] | 109 |
| (c) Working Party on the Transport of Perishable Foodstuffs | 8 | 7 | 7 [8] | 7 |
| (d) Working Party on the Transport of Dangerous Goods | 58 | 51 | 50 [58] | 50 |
| (e) Working Party on Transport Trends and Economics and subsidiary groups of experts | 18 | 14 | 16 [18] | 14 |
| (f) Working Party on Transport Statistics | 6 | 6 | 6 | 6 |
| (g) Working Party on Road Transport and subsidiary groups of experts | 24 | 14 | 12 | 10 |
| (h) Global Forum for Road Traffic Safety and subsidiary groups of experts | 28 | 19 | 24 [28] | 24 |
| (i) Working Party on Rail Transport and subsidiary groups of experts | 30 | 19 | 24 | 22 |
| (j) Working Party on Intermodal Transport and Logistics | 6 | 16 | 16 [18] | 14 |
| (k) Working Party on Inland Water Transport | 18 | 17 | 16 [18] | 14 |
| (l) Global Forum on Customs Questions Affecting Transport including Border Crossing Facilitation and subsidiary groups of expertsb | 40 | 36 | 38 [40] | 36 |
| 6. Meetings of the Economic and Social Council |  |  |  |  |
| (a) Committee of Experts on the Transport of Dangerous Goods and on the Globally Harmonized System of Classification and Labelling of Chemicals | – | – | 1 | – |
| (b) Subcommittee of Experts on the Transport of Dangerous Goods | 25 | 24 | 26 [29] | 25 |
| (c) Subcommittee of Experts on the Globally Harmonized System of Classification and Labelling of Chemicals | 10 | 5 | 8 [10] | 10 |
| 7. Meetings of the High-Level Meeting on Transport, Health and Environment | 2 | 2 | 2 | 2 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 2 | 2 | 2 | 4 |
| 8. On the Trans-European North-South Motorway | 1 | 1 | 1 | 1 |
| 9. On the Trans-European Railway | 1 | 1 | 1 | 1 |
| 10. On resilient transport systems | – | – | – | 1 |
| 11. On the implementation Inland Transport Committee normative and digital frameworks | – | – | – | 1 |
| Seminars, workshops and training events (number of days) | 11 | 11 | 10 | 11 |
| 12. Workshops for government officials and other stakeholders in the ECE region and in contracting Parties to legal instruments under the purview of the Inland Transport Committee on intelligent transport systems; transport statistics and trends; road, rail, inland water, intermodal and intersectoral transport issues; and vehicle agreements and regulations | 5 | 5 | 5 | 5 |
| 13. Seminars for national coordinators, experts, customs officials and transport industry on the efforts to digitalize the inland transport conventions | 6 | 6 | 5 [6] | 6 |
| Publications (number of publications) | 11 | 10 | 7 | 12 |
| 14. On the transport of dangerous goods | 3 | 2 | 1 [2] | 4 |
| 15. On the transport of perishable foodstuffs | 1 | – | 1 | 1 |
| 16. On reducing greenhouse gas emissions from the inland transport sector and safe transport and cross-cutting issues | 4 | 5 | 2 [4] | 4 |
| 17. On vehicle regulations | 1 | 1 | 1 | 1 |
| 18. On statistics | 1 | 1 | 1 | 1 |
| 19. On border crossing facilitation | 1 | 1 | 1 | 1 |
| Technical materials (number of materials) | 2 | 2 | 2 | 2 |
| 20. Recommendations for performance evaluation of automated driving systems | 1 | 1 | 1 | 1 |
| 21. Transport statistics – country profiles | 1 | 1 | 1 | 1 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services for contracting Parties of United Nations transport conventions administered by ECE on legal instruments relating to inland transport, facilitation of transport, border crossing, road safety, vehicle construction, and transport of dangerous goods and other special cargo. |  |  |  |  |
| Databases and substantive digital materials: the International TIR Data Bank for users from more than 70 contracting Parties of the TIR Convention; TIR and eTIR portals; the eTIR mobile application for customs officers and transport operators; the eTIR international system; the eTIR National Application; the International Transport Infrastructure Observatory; the Sustainable Inland Transport Connectivity Indicators online user platform; database of main standards and parameters of the E waterway network; inventory of existing European Agreement on Main International Railway Lines and European Agreement on Important International Combined Transport Lines and Related Installations standards and parameters; databases on transport statistics, road traffic accidents, transport of dangerous goods, transport of perishable foodstuffs, urban transport and transport and environment; Rail Security Observatory; digitized signs and signals (E-CoRSS) under the Convention on Road Signs and Signals; and smart and sustainable connectivity e-learning platform. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: information materials, including brochures on legal instruments and activities of the subprogramme for global and regional access. |  |  |  |  |
| External and media relations: press releases for the subprogramme. |  |  |  |  |
| Digital platforms and multimedia content: LearnITC and other digital platforms and multimedia content on sustainable transport and mobility; and website of the subprogramme; eTIR website. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Adjusted from Working Party on Customs Questions Affecting Transport and subsidiary groups of experts, in line with 	E/ECE/1514.

Subprogramme 3

Statistics

Objective

20.48	The objective, to which the subprogramme contributes, is to advance official statistics at the national and international levels for evidence-based policymaking and assessing progress towards achieving the Sustainable Development Goals and to ensure the coordination of statistical activities in the ECE region under the Conference of European Statisticians.

Strategy

20.49	To contribute to the objective, the subprogramme will:

(a)	Develop methodological guidelines, recommendations and models to modernize and enhance the quality of official statistics;

(b)	Promote the in-depth discussion and exchange of experience and good practice in official statistics at the Conference of European Statisticians and at expert meetings on social, economic and environment statistics and statistical modernisation;

(c)	Promote the uptake by member States of international statistical standards, guidelines and models and enhance capacities of national statistical offices, including on cross-cutting topics such as statistics for measuring progress against the Sustainable Development Goals, statistical legislation, and the collection, integration and dissemination of data;

(d)	Support the integration of geospatial information into statistics, in partnership with geospatial experts and relevant United Nations entities in the region;

(e)	Maintain and enhance the ECE statistical database, of which it is a custodian.

20.50	The above-mentioned work will help member States make progress towards achieving Sustainable Development Goals 1, 5, 6, 8, 10 and 12–17 and is expected to result in:

(a)	Production by member States of statistics necessary to develop evidence-based policies to advance the achievement of and measure the progress against the Sustainable Development Goals;

(b)	The use by member States of innovative and efficient approaches to conducting censuses that result in the improved cost-efficiency, coverage, accuracy, comparability and timeliness of dissemination of the census results.

Programme performance in 2025

Member States adopt enhanced global statistical standards

20.51	A harmonized approach to statistical production helps to ensure comparability, efficiency and quality across national statistical systems. The subprogramme developed the Generic Statistical Business Process Model, which provides a standard framework and harmonized terminology to help statistical organizations to modernize their statistical production processes, as well as to share methods and components. To address the evolving needs and users’ feedback, the subprogramme facilitated a consultative process under the auspices of the High-level Group for the Modernization of Official Statistics, to update the existing model, including by ensuring alignment with modernization priorities – for example, increasing the use of new data sources and modern technologies – and promoting the interregional engagement of key stakeholders. The subprogramme also supports the roll-out of the model by member States.

20.52	Progress towards the objective is presented in the performance measure below (see table 20.9).

Table 20.9

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| 80 per cent of national statistical offices reported using the Generic Statistical Business Process Model | – | Conference of European Statisticians adopted the revised Generic Statistical Business Process Model |

Planned results for 2027

Result 1: Economic Commission for Europe statistical database for improved research and decision-making

Programme performance in 2025 and target for 2027

20.53	The subprogramme’s work contributed to 2,141,963 downloads from the ECE statistical database, which exceeded the planned target of 1,029,333.

20.54	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.IV).

Figure 20.IV

Performance measure: number of downloads from the Economic Commission for Europe statistical database (annual)

–

–

–

Result 2: improved reporting for monitoring the Sustainable Development Goals

Programme performance in 2025 and target for 2027

20.55	The subprogramme’s work contributed to 73 per cent of Sustainable Development Goal indicators having sufficient data for assessing progress on the level in the ECE region, which exceeded the planned target of 71 per cent.

20.56	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.V).

## Figure 20.V

## Performance measure: percentage of Sustainable Development Goal indicators that have sufficient data for assessing progress on the level in the Economic Commission for Europe region (annual)

–

–

## Result 3: enhanced availability and accessibility of climate change-related statistics

## Proposed programme plan for 2027

20.57	As the impact of climate change on economies and societies evolves, policymakers require timely, reliable and comparable climate-related statistics to inform effective decision-making. The subprogramme has supported national statistical offices in the production of evidence for policymaking by developing methodological guidance, building capacities and facilitating the exchange of good practices. The report Data for Climate Action: How National Statistical Offices Can Contribute, published in 2024, was an examination of how official statistics could contribute to the reporting under the Paris Agreement by providing data for climate change mitigation, adaptation and just transition, informing the public and measuring climate-related costs, transfers and financial flows.

#### Lessons learned and planned change

20.58	The lesson for the subprogramme was that, while a wealth of relevant data were often already available, they were often scattered across statistical domains and not easily accessible or linked to climate change. In applying the lesson, the subprogramme will promote dialogue and closer engagement between producers and users of such statistics to improve understanding of data gaps, needs and availability. It will also support member States by enabling the exchange of best practices and innovative solutions in the production, dissemination and utilization of climate change-related statistics, including establishing dedicated national climate change-related statistics platforms, aimed at improving the availability and accessibility of these data for informed decision-making and the general public.

20.59	Expected progress towards the objective is presented in the performance measure below (see figure 20.VI).

## Figure 20.VI

## Performance measure: number of member States with a dedicated platform for climate change-related statistics (cumulative)

# Deliverables

20.60	Table 20.10 lists all deliverables of the subprogramme.

## Table 20.10

## Subprogramme 3: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 69 | 59 | 58 | 56 |
| 1. Documentation for the Conference of European Statisticians and its subsidiary and expert bodiesb | 69 | 59 | 58 [69] | 56 |
| Substantive services for meetings (number of three-hour meetings) | 85 | 63 | 72 | 68 |
| 2. Meetings of the Conference of European Statisticians, its Bureau and subsidiary and expert bodiesc | 85 | 63 | 72 [84] | 68 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | – | 1 | – | 2 |
| 3. On modernizing statistical production | – | 1 | – | 1 |
| 4. On supporting the integration of geospatial and statistical data across the ECE region | – | – | – | 1 |
| Seminars, workshops and training events (number of days) | 7 | 5 | 7 | 6 |
| 5. On social and economic statistics, and innovating statistical productiond | 7 | 5 | 7 | 6 |
| Publications (number of publications) | 7 | 5 | 5 | 4 |
| 6. On topics covering multiple statistical areas, including social, environmental and economic statistics | 7 | 5 | 5 [7] | 4 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services for more than 100 government officials and other stakeholders of up to 4 programme countries in the ECE region on economic, social, demographic and environment statistics, statistics for the Sustainable Development Goals, geospatial statistics and institutional issues and modernization of official statistics. |  |  |  |  |
| Databases and substantive digital materials: the ECE statistical database with 5 data domains. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Digital platforms and multimedia content: interactive digital workspaces; and website of the subprogramme and social media posts. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 1. Documentation for the Conference of European Statisticians; and 2. Documentation for groups of experts on statistical issues.

c	Presented in A/80/6 (Sect. 20) as 3. Meetings of the Conference of European Statisticians and its Bureau; and 4. Meetings of groups of experts on statistical issues.

d	Presented in A/80/6 (Sect. 20) as 6. Workshops on social and economic statistics; and 7. Workshops on innovating statistical production.

# Subprogramme 4

# Economic cooperation and integration

# Objective

20.61	The objective, to which the subprogramme contributes, is to strengthen policies on innovation, competitiveness and public-private partnerships for sustainable development in the ECE region.

# Strategy

20.62	To contribute to the objective, the subprogramme will:

(a)	Support the development of normative tools that complement existing economic policy, such as good practices, policy recommendations, and guidelines and standards on innovation and competitiveness policies and on sustainable public-private partnerships and infrastructure finance;

(b)	Strengthen national capacities and institutions through demand-driven capacity-building activities and policy advisory services, for example, by undertaking analyses of innovation systems, policies and institutions, offering related capacity-building activities, creating regulatory frameworks and project pipelines, and supporting the use of a methodology to evaluate and score public-private partnerships and infrastructure projects in support of sustainable development;

(c)	Support policy dialogue and peer learning, including by convening workshops, seminars, networks and forums that will provide relevant stakeholders with opportunities to discuss cutting-edge themes related to innovation and competitiveness policies and to sustainable public-private partnerships and infrastructure finance;

(d)	Carry out analytical work on innovation and competitiveness policies and on the mobilization of financing for public-private partnerships and infrastructure in the region.

20.63	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 8, 9, 12 and 17 and is expected to result in:

(a)	Publicly available, freely accessible and continuously updated standards and normative instruments in the field of innovation, competitiveness, sustainable public-private partnerships and infrastructure finance;

(b)	More effective harnessing of the transformative power of innovation for competitiveness and for sustainable development in member States;

(c)	Increased mobilization of financing to bridge the infrastructure financing gap faced by member States.

# Programme performance in 2025

## ECE Transformative Innovation Charter adopted by member States

20.64	Innovation plays an important role in advancing implementation of the 2030 Agenda. In the context of rapid technological change and multifaceted, interlinked Sustainable Development Goal-related challenges, there is increasingly recognition of a more holistic and adaptive policy framework capable of steering innovation towards societal goals. The subprogramme, working through the ECE Transformative Innovation Network, engaged governments, experts and practitioners over several years in the analysis of innovation policy trends and good practices. That collaborative effort culminated in the development of the Transformative Innovation Charter. Since its adoption, the subprogramme has been working with member States to help to operationalize it and expand its use in national policymaking.

20.65	Progress towards the objective is presented in the performance measure below (see table 20.11).

## Table 20.11

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| Key elements of a new transformative innovation policy agenda developed by the ECE Transformative Innovation Network | – | Member States adopted the new Transformative Innovation Charter, which sets out principles, guidelines and practical approaches for supporting transformative innovation effectively |

# Planned results for 2027

## Result 1: more public-private partnership infrastructure projects assessed as compliant with the Sustainable Development Goals

## Programme performance in 2025 and target for 2027

20.66	The subprogramme’s work contributed to assessments of 284 public-private partnership infrastructure projects, which did not meet the planned target of 300. The target was not met owing to the subprogramme’s limited capacity and resources to support all the planned reviews.

20.67	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.VII).

## Figure 20.VII

## Performance measure: number of public-private partnership infrastructure projects assessed as Sustainable Development Goal-compliant using the Public-private Partnership and Infrastructure Evaluation and Rating System methodology (cumulative)

## Result 2: improved innovation policies and initiatives for sustainable development

## Programme performance in 2025 and target for 2027

20.68	The subprogramme’s work contributed to 55 innovation stakeholders improving their innovation policy capacities, which exceeded the planned target of 50.

20.69	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.12).

## Table 20.12

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| Seven ECE programme countries implemented policy reforms supporting innovation for sustainable development | The report entitled Sustainable Development in the ECE Region: Facing a Headwind in 2024 found insufficient progress by member States on most Sustainable Development Goals and targets, including on innovation (Goal 9) | 55 innovation stakeholders improved their innovation policy capacities | At least 50 additional policymakers and other innovation stakeholders improve their innovation policy capacities | At least 40 additional policymakers and other innovation stakeholders improve their innovation policy capacities |

## Result 3: public-private partnerships aligned with ECE standards and guidelines on public-private partnerships in support of the Sustainable Development Goals

## Proposed programme plan for 2027

20.70	While private sector finance can help to scale up financing for sustainable and resilient infrastructure, there can be challenges in identifying and preparing bankable public-private partnerships and infrastructure projects that also contribute to achieving the Sustainable Development Goals. The subprogramme has been developing standards and guidelines on public-private partnerships, policy recommendations and best practices that enable member States to identify and prepare infrastructure projects aligned with the Goals and contribute to increased access and equity, environmental sustainability and resilience, economic effectiveness, replicability and stakeholder engagement in and ownership of the projects.

#### Lessons learned and planned change

20.71	The lesson for the subprogramme was that the identification and preparation phases of public-private partnership projects could benefit from the further integration of sustainability criteria, to ensure that projects are designed to advance long-term economic, social and environmental objectives, while being attractive to potential investors. In applying the lesson, the subprogramme will enhance the normative toolbox through the inclusion of additional standards and guidelines and will identify and avail targeted policy recommendations and best practices, with the aim of enhancing member States’ ability to identify and develop public-private partnership projects that are sustainable and bankable, thereby facilitating the mobilization of private finance for infrastructure development.

20.72	Expected progress towards the objective is presented in the performance measure below (see figure 20.VIII).

## Figure 20.VIII

## Performance measure: number of infrastructure projects improved as a result of using ECE standards and guidelines on public-private partnerships in support of the Sustainable Development Goals (cumulative)

Deliverables

20.73	Table 20.13 lists all deliverables of the subprogramme.

## Table 20.13

## Subprogramme 4: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 18 | 9 | 14 | 16 |
| 1. Documentation for the Committee on Innovation, Competitiveness and Public-Private Partnerships and its subsidiary bodies | 18 | 9 | 14 [18] | 16 |
| Substantive services for meetings (number of three-hour meetings) | 19 | 14 | 16 | 16 |
| 2. The Committee on Innovation, Competitiveness and Public-Private Partnerships and its subsidiary bodies | 18 | 13 | 15 [18] | 15 |
| 3. The Working Group on Innovation and Technology for Sustainable Development of the United Nations Special Programme for the Economies of Central Asia | 1 | 1 | 1 | 1 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | – | – | – | 2 |
| 4. On innovation and competitiveness policies | – | – | – | 1 |
| 5. On public-private partnerships | – | – | – | 1 |
| Seminars, workshops and training events (number of days) | 16 | 15 | 14 | 14 |
| 6. On innovation and competitiveness policies for sustainable development and public-private partnershipsb | 16 | 15 | 14 [16] | 14 |
| Publications (number of publications) | 3 | – | 2 | 2 |
| 7. On innovation for sustainable development and public-private partnershipsc | 3 | – | 2 [3] | 2 |
| Fact-finding, monitoring and investigation missions (number of missions) | 3 | – | 3 | – |
| 8. Fact-finding missions for innovation for sustainable development reviews and public-private partnership needs assessments | 3 | – | 3 | – |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services under the Working Party on Public-Private Partnership and the Team of Specialists on Innovation and Competitiveness Policies reaching 30 government ministries and agencies and stakeholder entities. |  |  |  |  |
| Databases and substantive digital materials: database of public-private partnership case studies. |  |  |  |  |
| D. Communication deliverables: |  |  |  |  |
| External and media relations: launch events for publications for regional, subregional and national access. |  |  |  |  |
| Digital platforms and multimedia content: website of the subprogramme. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 6. Capacity-building and policy advisory workshops, seminars, webinars and training on innovation and competitiveness policies for sustainable development; and 7. Capacity-building and policy advisory workshops, seminars, webinars and training on and public-private partnerships.

c	Presented in A/80/6 (Sect. 20) as 8. Innovation for Sustainable Development Reviews; and 9. Comparative reviews on innovation policy and/or public-private partnerships.

# Subprogramme 5

# Sustainable energy

# Objective

20.74	The objective, to which the subprogramme contributes, is to ensure secure access to affordable, reliable, sustainable and modern energy for all and to reduce greenhouse gas emissions and the carbon footprint of the energy sector in the region.

# Strategy

20.75	To contribute to the objective, the subprogramme will:

(a)	Conduct analysis and develop guidance, normative instruments and tools that help member States to meet their commitments, including the 2030 Agenda and the Paris Agreement, working with them to build their capacities to identify barriers to resilient, low-emission and low-carbon energy systems, to assess options that facilitate energy for sustainable development, to reduce the environmental footprint of energy, to accelerate the deep transformation of the energy sector, to facilitate the sustainable management of resources and to devise just energy transition pathways;

(b)	Strengthen national capacities and institutions through demand-driven technical assistance, capacity-building and policy advisory services – working in partnership with other relevant ECE subprogrammes – on sustainable resource management through (i) the application of the United Nations Framework Classification for Resources and the United Nations Resource Management System, in particular for critical raw materials, (ii) the interplay of low-carbon technologies, (iii) the measurement of, reporting on and mitigation of methane emissions from coal mines and gas operations, (iv) the safe operation and closure of coal mines, (v) energy efficiency across buildings and industry, transport and other sectors, leveraging digital technologies and systems integration, (vi) and the building of resilient energy systems through just energy transition strategies that align environmental, social and economic goals within a democratic governance framework;

(c)	Promote and facilitate policy dialogue, training, peer learning, public-private collaboration and the access of member States to other international cooperation mechanisms – working in collaboration with other relevant regional commissions, in particular for subprogramme work recognized by the Economic and Social Council for its global relevance – with the aim of advancing policy implementation and the use of normative instruments on sustainable energy.

20.76	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 7, 9, 12 and 13 and is expected to result in:

(a)	Adoption and implementation of national policies and normative frameworks that integrate sustainable resource management, circular economy approaches and just energy transition approaches, promote low-emission and low-carbon technologies, sustainable infrastructure and more efficient and digitalized energy systems, and support the implementation of the 2030 Agenda and the Paris Agreement;

(b)	Application of instruments and tools to reduce the environmental footprint of the energy sector, the enhanced management of natural resources, and strengthened energy resilience and security;

(c)	Increased investment in the modernization of energy systems, supported by more efficient and digitalized networks.

# Programme performance in 2025

## Strengthened cross-border cooperation on energy connectivity

20.77	Integrated and interconnected energy systems can enhance reliability, reduce costs and enable the deployment of renewable energy solutions at larger scales. In Central Asia, where national energy profiles and sources are often complementary, expanding cross-border electricity trade has been beneficial for advancing the energy transition, promoting economic diversification and creating jobs. Between 2023 and 2025, the subprogramme convened a series of policy dialogues and technical capacity-building workshops for policymakers, transition system operators and strategic energy planners from more than 20 member States on cross-border infrastructure development and renewable energy integration. The dialogues facilitated the exchange of best practices, the alignment of approaches and the identification of synergies across existing initiatives. To date, eight member States (Georgia, Kazakhstan, Kyrgyzstan, Republic of Moldova, Tajikistan, Turkmenistan, Ukraine and Uzbekistan) have completed in-depth analyses on cross-border cooperation on energy connectivity and infrastructure. Subsequently, three member States in Central Asia (Kazakhstan, Tajikistan and Uzbekistan) integrated cross-border cooperation measures into their national energy strategies, further strengthening the political commitment to expanding electricity trade across the region. Owing to the facilitated peer-to-peer engagements, the initiative has also gained traction beyond Central Asia, resulting in two member States (Georgia and Republic of Moldova) adopting new policies on cross-border energy connectivity.

20.78	Progress towards the objective is presented in the performance measure below (see figure 20.IX).

## Figure 20.IX

## Performance measure: number of member States having completed in-depth analyses of cross-border cooperation on energy connectivity and having incorporated regional cross-border cooperation measures into their national energy strategies (cumulative)

# Planned results for 2027

## Result 1: more sustainable and resilient natural resource management based on the United Nations Framework Classification for Resources

## Programme performance in 2025 and target for 2027

20.79	The subprogramme’s work contributed to 5 additional countries (Canada, Mongolia, Nicaragua, Switzerland and Zambia) adopting the United Nations Framework Classification for Resources guidelines and 10 Member States (Armenia, Austria, Canada, Kazakhstan, Mexico, Norway, Russian Federation, Slovenia, Türkiye and United Kingdom of Great Britain and Northern Ireland) providing input to the United Nations Framework Classification for Resources knowledge hub, which met the planned target.

20.80	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.14).

## Table 20.14

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| United Nations Framework Classification for Resources included in European Union’s Critical Raw Materials Act | Two additional International Centres of Excellence on Sustainable Resource Management established | Five additional countries (Canada, Mongolia, Nicaragua, Switzerland and Zambia) adopted the United Nations Framework Classification for Resources guidelines | Three additional International Centres of Excellence on Sustainable Resource Management established | Six additional Member States provide input to the United Nations Framework Classification for Resources knowledge hub |
| One bridging document between the United Nations Framework Classification for Resources and Russia’s petroleum classification updated and endorsed | Five countries adopted the United Nations Framework Classification for Resources guidelines | Ten Member States (Armenia, Austria, Canada, Kazakhstan, Mexico, Norway, Russian Federation, Slovenia, Türkiye and United Kingdom of Great Britain and Northern Ireland) provided input to the United Nations Framework Classification for Resources knowledge hub | Five additional Member States provide input to the United Nations Framework Classification for Resources knowledge hub |  |

## Result 2: increased adoption of electric mobility for a sustainable energy transition

## Programme performance in 2025 and target for 2027

20.81	The subprogramme’s work contributed to three additional member States (Albania, Belarus and Tajikistan) having adopted e-mobility policies, for a cumulative total of four countries, which met the planned target.

20.82	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.X).

## Figure 20.X

## Performance measure: number of member States adopting e-mobility policies that apply Economic Commission for Europe recommendations on best practices for integration of e-mobility into energy systems (cumulative)

## Result 3: reducing greenhouse gas emissions in high-emission intensity industries

## Proposed programme plan for 2027

20.83	Many energy- and associated greenhouse gas emissions-intensive industries may face barriers such as the lack of technology, infrastructure, regulations and investment required to reduce emissions. The subprogramme has supported member States in their efforts to transform industries in which emission reductions are most challenging.

#### Lessons learned and planned change

20.84	The lesson for the subprogramme was that a systems-oriented, holistic approach offered important advantages for addressing complex and interconnected policy challenges. In applying the lesson, the subprogramme will further strengthen its role as a platform for integrated analysis and policy dialogue, including through the development of analytical models and tools that reflect holistic pathways for reducing greenhouse gas emissions. The subprogramme will also enhance cross-sectoral coordination and support member States in developing coherent policy frameworks that align industrial energy efficiency strategies with broader climate and sustainability objectives, while taking into account economic competitiveness and other economic implications.

20.85	Expected progress towards the objective is presented in the performance measure below (see figure 20.XI).

## Figure 20.XI

## Performance measure: number of member States that adopted policies and measures supporting systemic efficiency and reducing greenhouse gas emissions of the sectors where emission reductions are most challenging (cumulative)

# Deliverables

20.86	Table 20.15 lists all deliverables of the subprogramme.

## Table 20.15

## Subprogramme 5: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 40 | 38 | 36 | 32 |
| 1. Documentation for the Committee on Sustainable Energy and related subsidiary bodies | 40 | 38 | 36 [40] | 32 |
| Substantive services for meetings (number of three-hour meetings) | 38 | 34 | 34 | 30 |
| 2. Meetings of the Committee on Sustainable Energy, its Bureau and related subsidiary bodies | 38 | 34 | 34 [38] | 30 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 3 | 3 | 4 | 4 |
| 3. On sustainable resource management and governance, including access to critical raw materials | 1 | 1 | 2 | 2 |
| 4. On accelerating transformations of the energy sector | 1 | 1 | – | 1 |
| 5. On resilient energy systems | 1 | 1 | 1 | 1 |
| 6. On scaling systemic energy efficiencies and digitalization of energy system networks | – | – | 1 | – |
| Seminars, workshops and training events (number of days) | 11 | 9 | 12 | 11 |
| 7. On the application of the United Nations Framework Classification for Resources and the United Nations Resource Management System; energy efficiency; renewable energy and low-carbon gas development and policy reforms for climate change mitigation; the “just transition” approach to sustainable resources and methane management; and other related topicsb | 8 | 6 | 9 | 8 |
| 8. International Forum on Energy for Sustainable Development | 3 | 3 | 3 | 3 |
| Publications (number of publications) | 3 | 1 | 2 | 2 |
| 9. On renewable energy, resilient energy systems, sustainable resources management, methane management and other related topicsc | 3 | 1 | 2 [4] | 2 |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: booklets on sustainable energy and related topics. |  |  |  |  |
| External and media relations: press releases, keynote speeches, interviews and articles on the activities of the energy subprogramme. |  |  |  |  |
| Digital platforms and multimedia content: websites of the subprogramme and social media posts. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 8. On the application of the United Nations Framework Classification for Resources and the United Nations Resource Management System; 9. On energy efficiency measures and accelerators; 10. On renewable energy and low-carbon gases (biogas, hydrogen) development and policy reforms for climate change mitigation; 12. On methane management; and 13. On the “just transition” approach.

c	Presented in A/80/6 (Sect. 20) as 14. On the United Nations Framework Classification for Resources and the United Nations Resource Management System; 15. On digitalization and on best practices in methane management; 16. On resilient energy systems; 17. On renewable energy; and 18. On hydrogen.

# Subprogramme 6

# Trade

# Objective

20.87	The objective, to which this subprogramme contributes, is to strengthen trade facilitation and electronic business, regulatory cooperation and standardization policies, agricultural quality standards and trade-related economic cooperation for an increased impact on sustainable development in the ECE region and beyond.

# Strategy

20.88	To contribute to the objective, the subprogramme will:

(a)	Support the development of normative tools that complement existing international economic law and policy, such as good practices, policy recommendations, common regulatory arrangements, standards (including information exchange standards and commercial quality standards) and guidelines;

(b)	Strengthen national capacities and institutions through demand-driven technical assistance and policy advisory services pertaining to regulatory and procedural barriers to trade, trade facilitation and digital connectivity, and support the practical implementation of normative instruments;

(c)	Support international policy dialogue and peer learning to foster consensus to facilitate trade, including by advancing digital connectivity in trade corridors, enhancing sustainability, transparency and resilience and reducing waste along value chains in critical sectors, and mainstreaming a gender perspective into quality infrastructure;

(d)	Undertake analytical work and evidence-based studies on issues related to digital and sustainable trade in the region.

20.89	In addition, the subprogramme, in its role as the custodian of trade-related standards, in particular those pertaining to information exchange under the United Nations Centre for Trade Facilitation and Electronic Business, code lists of the United Nations Code for Trade and Transport Locations, and marketing and commercial quality control of agricultural produce (Working Party on Agricultural Quality Standards), will facilitate their continuous review and maintain their repositories and repositories of related guidelines.

20.90	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 2, 5, 8, 9, 12 and 17 and is expected to result in:

(a)	More sustainable, inclusive and resilient cross-border trade, based on simplified, transparent, digitalized and harmonized global standards and procedures;

(b)	Improved consumption and production patterns along value chains based on increased transparency and traceability, and a reduction in waste.

# Programme performance in 2025

## Adopted gender action plans promote inclusive quality infrastructure for trade

20.91	Gender equality in quality infrastructure helps to ensure that standards, technical regulations and conformity assessment procedures reflect the needs of all users and that all persons can participate equally in shaping trade and regulatory environments. However, implications related to gender equality can be overlooked in the design of standards and quality policies. To address this gap, the subprogramme provided targeted support to quality infrastructure institutions in developing gender action plans, which set measurable objectives and benchmarks on equal participation in technical committees, gender-responsive outputs and inclusive workplace culture. This process has supported the enhanced, systematic integration of considerations related to gender equality into quality infrastructure policies and practices, strengthened institutional accountability, and supported greater alignment with broader national equality commitments.

20.92	Progress towards the objective is presented in the performance measure below (see figure 20.XII).

## Figure 20.XII

## Performance measure: number of national quality infrastructure agencies that adopted gender action plans (cumulative)

Planned results for 2027

Result 1: enhanced digitalization of trade

Programme performance in 2025 and target for 2027

20.93	The subprogramme’s work contributed to member States achieving an average implementation rate of 61 per cent for cross-border paperless trade facilitation measures, which exceeded the planned target of 60 per cent, and an average implementation rate of 83 per cent for paperless trade facilitation measures, which did not meet the planned target of 86 per cent. The target of an average implementation rate of 86 per cent for paperless trade facilitation measures was not met owing to methodological adjustments introduced during the 2025 iteration of the United Nations Global Survey on Digital and Sustainable Trade Facilitation, completed by member States, which resulted in a downward revision of targets achieved in 2023 and 2024, thus lowering the baseline for 2025.

20.94	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.XIII).

## Figure 20.XIII

## Performance measure: average implementation rate of trade facilitation measures in the Economic Commission for Europe region

(Percentage)

Note: The data are captured every two years through the United Nations Global Survey on Digital and Sustainable Trade Facilitation), conducted most recently in 2025. Data for 2024 reflect achievements in 2023.

## Result 2: improved transparency and traceability of value chains in critical sectors

## Programme performance in 2025 and target for 2027

20.95	The subprogramme’s work contributed to 890 industry actors submitting 120 pledges, which exceeded the planned target of 870 industry actors and met the planned target of pledges.

20.96	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.XIV).

## Figure 20.XIV

## Performance measure: number of industry actors that have submitted pledges to traceability and transparency of sustainable value chains (cumulative)

Note: Pledges refers to the number of pledges submitted and industry actors refers to organizations involved in the pledges. Some of the pledges are submitted by a consortium/group of partners.

## Result 3: agricultural quality standards revised with the aim of reducing food loss and waste

## Proposed programme plan for 2027

20.97	Agricultural quality standards can help producers, traders and retail chains, and authorities to facilitate trade, improve production, maintain existing and reach new markets and protect consumers. To date, the subprogramme has facilitated the adoption of more than 120 such standards and, in recent years, promoted intergovernmental dialogue on ways to reduce food loss and waste.

#### Lessons learned and planned change

20.98	The lesson for the subprogramme was that its interventions were more impactful when food loss and waste considerations were systematically embedded in the review and development of agricultural quality standards. In applying the lesson, the subprogramme will support the normative and standard-setting efforts of the Working Party on Agricultural Quality Standards to ensure that sustainability-related issues, specifically measures for reducing food loss and waste, are duly considered in the process of revising the existing agricultural quality standards and developing new ones. As a complement, the subprogramme will develop practical guidance on food loss reduction in value chains.

20.99	Expected progress towards the objective is presented in the performance measure below (see figure 20.XV).

## Figure 20.XV

## Performance measure: number of agricultural quality standards revised with the aim of reducing food loss and waste (cumulative)

# Deliverables

20.100	Table 20.16 lists all deliverables of the subprogramme.

## Table 20.16

## Subprogramme 6: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 102 | 84 | 82 | 88 |
| 1. The Steering Committee on Trade Capacity and Standards and its subsidiary and expert bodiesb | 87 | 74 | 74 [84] | 78 |
| 2. The United Nations Centre for Trade Facilitation and Electronic Business | 15 | 10 | 8 [12] | 10 |
| Substantive services for meetings (number of three-hour meetings) | 96 | 60 | 80 | 69 |
| 3. The Steering Committee on Trade Capacity and Standards, its Bureau and subsidiary and expert bodiesc | 43 | 31 | 39 [43] | 39 |
| 4. The United Nations Centre for Trade Facilitation and Electronic Business | 53 | 29 | 40 [53] | 30 |
| 5. The Working Group on Trade of the United Nations Special Programme for the Economies of Central Asia | – | – | 1 | – |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 5 | 4 | 5 | 4 |
| 6. On quality infrastructure for trade, including gender considerations | 1 | 1 | 1 | 1 |
| 7. On agricultural quality standards and reduction of food loss in supply chains | 1 | – | 1 | 1 |
| 8. On the implementation of normative instruments for trade facilitation | 3 | 3 | 3 | 2 |
| Seminars, workshops and training events (number of days) | 18 | 12 | 15 | 4 |
| 9. On trade and trade facilitation, quality infrastructure, risk management, gender equality and trade, ECE agricultural quality standards and food loss reductiond | 18 | 12 | 15 [16] | 4 |
| Publications (number of publications) | 9 | 8 | 6 | 7 |
| 10. On regulatory and procedural barriers to trade and trade facilitation, quality infrastructure, risk management, gender equality and trade, ECE agricultural quality standards and food loss reductione | 9 | 8 | 6 [9] | 7 |
| Technical materials (number of materials) | 8 | 10 | 8 | 4 |
| 11. Guidelines on trade facilitation and cross-border trade, agricultural quality standards, quality infrastructure, risk management and traceability in value chainsf | 8 | 10 | 8 | 4 |
| Fact-finding, monitoring and investigating missions (number of missions) | 3 | – | – | – |
| 12. Fact-finding missions on trade facilitation and electronic business, agricultural quality standards, regulatory cooperation and standardization, and regulatory and procedural barriers to trade | 3 | – | – [1] | – |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: meetings of the Working Group on Trade of the United Nations Special Programme for the Economies of Central Asia; and advisory services to government officials and other stakeholders on trade facilitation and electronic business, agricultural quality standards, regulatory cooperation and standardization, and regulatory and procedural barriers to trade. |  |  |  |  |
| Databases and substantive digital materials: ECE databases for sustainable and digital trade facilitation; and annual updates to the United Nations Centre for Trade Facilitation and Electronic Business information exchange standards, the agricultural quality standards and related databases. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: booklets, promotional materials, fact sheets, information brochures and newsletters reaching at least 1,000 public and private sector experts. |  |  |  |  |
| External and media relations: press releases, news articles, publication launch events and articles in external newsletters intended for government officials and experts working on trade. |  |  |  |  |
| Digital platforms and multimedia content: website of the subprogramme. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 1. The Steering Committee on Trade Capacity and Standards; 2. The Working Party on Regulatory Cooperation and Standardization Policies; and 3. The Working Party on Agricultural Quality Standards.

c	Presented in A/80/6 (Sect. 20) as 5. The Steering Committee on Trade Capacity and Standards and its Bureau; 6. The Working Party on Regulatory Cooperation and Standardization Policies, its Bureau and related expert bodies; and 7. The Working Party on Agricultural Quality Standards and its specialized sections.

d	Presented in A/80/6 (Sect. 20) as 14. On trade procedures, supply chain management, conformity assessment and market surveillance, and women’s entrepreneurship; 15. Seminars on quality infrastructure, risk management, education, and gender equality and trade; 16. Seminars on ECE agricultural quality standards, trade and food loss reduction; and 17. Seminars on trade facilitation-related standards, recommendations and guidelines.

e	Presented in A/80/6 (Sect. 20) as 18. On regulatory and procedural barriers to trade; 19. On trade standard guidance in the following areas: quality infrastructure, risk management, education and sustainable development; 20. On quality infrastructure, risk management, education and gender equality and trade; 21. On mainstreaming a gender perspective into standards; 22. On agricultural trade, supply chains and food loss and waste; and 23. On trade facilitation recommendations, standards and strategies.

f	Presented in A/80/6 (Sect. 20) as 24. Guidelines on cross-border trade; and 25. Training material and guidelines on trade standards and/or regulatory cooperation.

# Subprogramme 7

# Forests and the forest industry

# Objective

20.101	This subprogramme contributes to the objective of strengthening the sustainable management of trees and forests and enhancing the contribution of forests and forest products to sustainable development, climate action and biodiversity in the region.

# Strategy

20.102	To contribute to the objective, the subprogramme will:

(a)	Facilitate regional and global policy dialogue and promote transboundary cooperation for sustainable forest management, forest landscape restoration, sustainable use of forest products and services, including links between sustainable food systems and forests, and urban and peri-urban forestry;

(b)	Collect, validate and disseminate data and information, in-depth analysis and policy recommendations related to sustainable forest management and the sustainable production, consumption and trade of wood products, including wood energy;

(c)	Facilitate the exchange of national and subnational experiences and best practices and monitor progress in achieving sustainable forest management, including trade-related matters;

(d)	Build national capacity by providing demand-driven technical assistance, specialized expertise and policy advice on forest and the forest sector, including on crisis response and solutions for more resilient economies.

20.103	The above-mentioned work will help member States to make progress towards achieving Sustainable Development Goals 7, 11–13 and 15 and the implementation of the United Nations Strategic Plan for Forests 2017-2030, and is expected to result in:

(a)	More sustainably managed resilient forest ecosystems, which deliver vital goods and services that benefit society and contribute to climate mitigation and adaptation;

(b)	Increased and more sustainable use of forest products by member States, contributing to the circular and regenerative bioeconomy and the sustainable use of natural resources;

(c)	The integration of forest resources and products into cross-sectoral planning for the increased resilience of rural and urban ecosystems and food systems.

Programme performance in 2025

Enhanced integration of sustainable urban forestry solutions into national planning

20.104	Urban forests help to cool cities and can improve physical and mental health, reduce floods, attract people to the outdoors and businesses, and create jobs, among other benefits. The subprogramme supported member States, through the Trees in Dry Cities Coalition, to advance efforts to integrate urban forests into national planning and policy through targeted plans and mainstreaming, with the aim of advancing systemic, multi-pronged action in this regard. Specifically, it led the consultative process, which resulted in member States agreeing to a voluntary action plan and the subsequent development of dedicated guidance on scaling urban forestry with national policy and using it as a delivery mechanism for the Rio Conventions, further contributing to member States’ efforts to enhance urban forest cover through multi-level approaches.

20.105	Progress towards the objective is presented in the performance measure below (see table 20.17).

## Table 20.17

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| The Trees in Dry Cities Coalition was launched at the twenty-eighth session of the Conference of the Parties to the United Nations Framework Convention on Climate Change | Coalition members agreed to voluntary action plans, which included developing relevant guidelines | Member States have access to guidelines on “Scaling urban forestry with national policy” and “Using urban forestry as a delivery mechanism for the Rio Conventions” |

# Planned results for 2027

## Result 1: evidence-based planning and action for the sustainable production and consumption of forest products

## Programme performance in 2025 and target for 2027

20.106	The subprogramme’s work contributed to 64 wood-based commodity assessments, which exceeded the planned target of 59, and 16 member States reporting the use of information in these assessments, which exceeded the planned target of 15.

20.107	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.XVI).

## Figure 20.XVI

## Performance measure: number of assessments of wood-based commodities, regarding their production, trade and consumption, and number of member States that report the use of information from these assessments (cumulative)

Result 2: increased access to data on forests and the forest industry

Programme performance in 2025 and target for 2027

20.108	The subprogramme’s work contributed to the completion of 142 replies from member States to international statistical questionnaires from ECE on forest resources, forest products and wood energy, which exceeded the planned target of 140.

20.109	Progress towards the objective and the target for 2027 are presented in the performance measure below (see figure 20.XVII).

## Figure 20.XVII

## Performance measure: number of replies from member States to international statistical questionnaires from ECE on forest resources, forest products and wood energy (annual)

(Number of replies to the most recent questionnaires in each series)

## Result 3: foresight-based planning for a resilient and sustainable forest industry

## Proposed programme plan for 2027

20.110	The forest industry is influenced by shifts in market demand, regulatory frameworks and national economic models. In this context, the subprogramme developed a standard framework to gather statistical data and analysis on forest products and wood energy markets. The framework enables an assessment of the impacts of policies and market factors on the production of, trade in and consumption of forest products in the region.

#### Lessons learned and planned change

20.111	The lesson for the subprogramme was that its support to member States could be further strengthened by anticipatory and harmonized, evidence-based analysis. This allows for an assessment and the showcase of the role of the forest sector in national strategies and plans, including those pertaining to trade in response to market and regulatory changes, which have seen increases in pace and scale. In applying the lesson, the subprogramme will support member States in applying the information made available through the standard framework for foresight analysis of the forest industry, which it will continue to maintain and enhance, as means of availing critical evidence for resilient forest sector management and anticipatory national development planning, taking into account evolving environmental and socioeconomic conditions.

20.112	Expected progress towards the objective is presented in the performance measure below (see table 20.18).

## Table 20.18

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| – | – | Member States have access to regional data, based on the standard framework for foresight analysis of the forest industry | At least one member State utilizes the standard framework for foresight analysis of the forest sector and for national policy planning | At least two additional member States utilize the standard framework for foresight-based analysis of the forest sector and for national policy planning |

# Deliverables

20.113	Table 20.19 lists all deliverables of the subprogramme.

## Table 20.19

## Subprogramme 7: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 24 | 19 | 12 | 12 |
| 1. Documentation for the Committee on Forests and the Forest Industry and its subsidiary and expert bodiesb | 24 | 19 | 12 [14] | 12 |
| Substantive services for meetings (number of three-hour meetings) | 22 | 19 | 18 | 18 |
| Meetings of: |  |  |  |  |
| 2. The Committee on Forests and the Forest Industry and its Bureauc | 10 | 7 | 8 | 8 |
| 3. The Working Party on Forest Statistics, Economics and Managementd and Teams of Specialists | 12 | 12 | 10 [12] | 10 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 1 | 1 | 1 | 1 |
| 4. Safeguarding forest management in the ECE region | 1 | 1 | 1 | 1 |
| Seminars, workshops and training events (number of days) | 12 | 12 | 10 | 10 |
| 5. Training events for policymakers, experts and relevant stakeholders from countries in the ECE region on topics related to forests and the forest industry | 12 | 12 | 10 [12] | 10 |
| Publications (number of publications) | 5 | 4 | 3 | 2 |
| 6. On sustainable forest management and forest productse | 5 | 4 | 3 [4] | 2 |
| Technical materials (number of materials) | – | 3 | – | 2 |
| 7. On sustainable forest management and forest products | – | 3 | – | 2 |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services, forest policy dialogues at the request of countries and support for forest policy issues, for up to three member States. |  |  |  |  |
| Databases and substantive digital materials: ECE region databases on forest policies and institutions, forest products, production, consumption, removals and trade, including prices, and wood energy for global access; and ECE regional databases on forest resources and forest ownership. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Outreach programmes, special events and information materials: events celebrating the International Day of Forests; brochures and information materials on various forest-related topics; and presentations at round tables and international forest-related events. |  |  |  |  |
| External and media relations: press releases for the subprogramme; and Forest Information Billboard newsletter. |  |  |  |  |
| Digital platforms and multimedia content: website of the subprogramme; social media posts; and videos and other media on forest-related topics. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 1. Documentation for the Committee on Forests and the Forest Industry; and 2. Documentation for the ECE/FAO Working Party on Forest Statistics, Economics and Management.

c	Presented in A/80/6 (Sect. 20) as 3. The Committee on Forests and the Forest Industry; and 4. The Bureau of the Committee on Forests and the Forest Industry.

d	Previously the Joint ECE/FAO Working Party on Forest Statistics, Economics and Management.

e	Includes “Forest Products Annual Market Review”, listed in A/80/6 (Sect. 20) as a separate item.

# Subprogramme 8

# Housing, land management and population

# Objective

20.114	The objective, to which the subprogramme contributes, is to strengthen member State-owned and city-level programmes and policies promoting adequate, affordable, energy-efficient and healthy housing for all, smart sustainable cities, sustainable urban development and land management, and to advance evidence-based population and social cohesion policies.

# Strategy

20.115	The subprogramme comprises two components: (a) housing and land management; and (b) population.

20.116	To contribute to the objective, the housing and land management component of the subprogramme will:

(a)	Assist national and local governments in defining, adopting and implementing sustainable urban, housing and land management policies and programmes through the development of guidance, policy recommendations and evidence and analysis on (i) affordable, accessible and energy-efficient housing for all, (ii) smart sustainable cities and digitalization in cities, (iii) innovative financial mechanisms for cities and the housing sector, (iv) sustainable land administration and management, including informal settlements, (v) the integration of climate change measures, including promotion of the climate neutrality of buildings, and (vi) urban resilience;

(b)	Promote the engagement of local and regional governments in the localization of the Sustainable Development Goals and the implementation of climate and other relevant global and regional commitments by facilitating exchanges of good practice, cooperation and dialogue among mayors, member States and relevant international organizations through the United Nations Forum of Mayors; and by supporting local authorities in the coordinated preparation of voluntary local reviews and in the application of commonly agreed indicator and monitoring frameworks;

(c)	Strengthen national and local capacities through (i) demand-driven technical assistance and capacity-building, (ii) peer learning and the exchange of best practices, (iii) advisory services and (iv) multi-stakeholder partnerships, to design and implement urban resilience plans and sustainable urban infrastructure projects, supporting also persons in vulnerable situations.

20.117	To contribute to the objective, the population component of the subprogramme will:

(a)	Collect, analyse and share data and policy information on ageing, gender equality and intergenerational relations to raise awareness on ageing, support evidence-based policymaking and monitor and appraise progress made in the implementation of the Madrid International Plan of Action on Ageing and its regional implementation strategy;

(b)	Support the development of national capacities to address policy concerns pertaining to individual and population ageing, including through technical advice and the sharing of good practices and lessons learned on advancing the mainstreaming of ageing across policy fields and levels of government;

(c)	Support regional cooperation and policy dialogue on ageing by providing an intergovernmental and multi-stakeholder platform for experience exchange, advocacy and peer learning.

20.118	The above-mentioned work will help member States to make progress on achieving Sustainable Development Goals 1,3, 5, 7–9, 10–12, 16 and 17 and is expected to result in:

(a)	National and local sustainable urban development and housing policies and programmes aimed at improving the affordability, adequacy and accessibility of housing, energy efficiency and the climate neutrality of buildings, and urban resilience;

(b)	Strengthened multilevel governance and the engagement of local and regional governments in policymaking;

(c)	Development and implementation by land authorities of sustainable national land administration and management systems;

(d)	Strengthened systems for the collection and application of quantitative and qualitative evidence on population and social cohesion;

(e)	Age-sensitive and inclusive policies that mainstream ageing across policy fields and levels of government.

Programme performance in 2025

Member States commit themselves to advancing housing affordability and sustainability

20.119	Rising rents and housing costs, combined with limited supply and speculative pressures, have affected households, especially of younger people and marginalized groups who, more often, continue to experience difficulties in gaining access to affordable and adequate housing. At the request of member States, the subprogramme coordinated a survey and, on its basis, prepared a report and a peer-to-peer exchange aimed at identifying solutions for improving housing affordability in the region. Subsequently, the subprogramme seized the momentum and facilitated ministerial-level discussions to strengthen commitments to prioritize equity and social inclusion; promote multilevel governance; expand affordable and sustainable housing through retrofitting and the construction of climate‑resilient infrastructure and efficient building technologies; and regenerate urban areas through redevelopment and adaptive reuse.

20.120	Progress towards the objective is presented in the performance measure below (see table 20.20).

## Table 20.20

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) |
| --- | --- | --- |
| – | – | Member States adopted the ministerial commitments on housing affordability and sustainability |

# Planned results for 2027

## Result 1: more age-sensitive and inclusive policies to respond to the opportunities and challenges of individual and population ageing

## Programme performance in 2025 and target for 2027

20.121	The subprogramme’s work contributed to 21 member States having shared ageing-related policy updates for inclusion in the Ageing Policies Database, which exceeded the planned target of 15.

20.122	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.21).

## Table 20.21

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| Member States agreed on the scope and design of the Ageing Policies Database | Member States academia, civil society and the general public gain access to the Ageing Policies Database | 21 member States shared ageing-related policy updates for inclusion in the Ageing Policies Database | At least 20 member States share ageing-related policy updates for inclusion in the database | At least 30 member States participate in the fifth review and appraisal of the implementation of the Madrid International Plan of Action on Ageing |

## Result 2: acceleration of Sustainable Development Goal localization by local and regional governments

## Programme performance in 2025 and target for 2027

20.123	The subprogramme’s work contributed to three local governments (of the cities of Geneva, Helsinki and Turku) preparing voluntary local reviews applying the regional guidelines, which met the planned target.

20.124	Progress towards the objective and the target for 2027 are presented in the performance measure below (see table 20.22).

## Table 20.22

## Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027(planned) |
| --- | --- | --- | --- | --- |
| The Committee on Urban Development, Housing and Land Management invited the ECE secretariat to update the guidelines for the development of voluntary local reviews on the basis of testing in pilot cities and feedback received | Updated regional guidelines for the development of voluntary local reviews adopted by the Committee on Urban Development, Housing and Land Management | Three local governments (of the cities of Geneva, Helsinki, and Turku) prepared voluntary local reviews applying the regional guidelines | Four additional local/regional governments prepare voluntary local reviews applying the regional guidelines | Three additional local/regional governments prepare voluntary local reviews applying the regional guidelines |

## Result 3: anticipatory regional policy framework on ageing

## Proposed programme plan for 2027

20.125	The Rome Ministerial Declaration on Ageing (2022) entrusted the Standing Working Group on Ageing with leading the process of updating the regional implementation strategy for the Madrid International Plan of Action on Ageing, with a focus on societal adaptation to individual and population ageing, and the demographic transition more broadly. The subprogramme has been working with national policymakers and experts to identify policy priorities that address emerging and future challenges for ageing societies.

#### Lessons learned and planned change

20.126	The lesson for the subprogramme was that the updated regional implementation strategy would benefit from a fuller reflection on emerging economic, social and digital transitions and guide anticipatory policy responses to population ageing. In applying the lesson, the subprogramme will facilitate literature reviews, stakeholder engagement and intergovernmental consultations by the member State-led task force; collect and analyse relevant evidence, good practices and policy solutions; and advocate for the mainstreaming of ageing-related considerations into sectoral social and economic policies to help to ensure a comprehensive and cross-cutting perspective.

20.127	Expected progress towards the objective is presented in the performance measure below (see table 20.23).

Table 20.23

Performance measure

| 2023 (actual) | 2024 (actual) | 2025 (actual) | 2026 (planned) | 2027 (planned) |
| --- | --- | --- | --- | --- |
| Task force set up by Standing Working Group on Ageing to lead the update of the regional implementation strategy | Task force issued guidance on the engagement of national stakeholders | Member States identified key priority areas for action on ageing | At least 15 member States contribute solutions/proposals for the updated strategy that address priority concerns | New regional implementation strategy for the Madrid International Plan of Action on Ageing is considered for adoption by member States |

# Deliverables

20.128	Table 20.24 lists all deliverables of the subprogramme.

## Table 20.24

## Subprogramme 8: deliverables for the period 2025–2027, by category and subcategory

| Category and subcategory | 2025 planned | 2025 actual | 2026 planneda | 2027 planned |
| --- | --- | --- | --- | --- |
| A. Facilitation of the intergovernmental process and expert bodies |  |  |  |  |
| Parliamentary documentation (number of documents) | 23 | 20 | 15 | 24 |
| 1. The Committee on Urban Development, Housing and Land Management and its subsidiary and expert bodiesb | 18 | 15 | 10 [11] | 16 |
| 2. The Standing Working Group on Ageing | 5 | 5 | 5 | 4 |
| 3. Ministerial Conference on Ageing | – | – | – | 4 |
| Substantive services for meetings (number of three-hour meetings) | 33 | 30 | 24 | 33 |
| 4. The Committee on Urban Development, Housing and Land Management, its subsidiary and expert bodies and their Bureauxc | 24 | 21 | 17 [20] | 21 |
| 5. The Standing Working Group on Ageing and its Bureau | 9 | 9 | 7 [9] | 8 |
| 6. Ministerial Conference on Ageing | – | – | – | 4 |
| B. Generation and transfer of knowledge |  |  |  |  |
| Field and technical cooperation projects (number of projects) | 2 | 1 | 2 | 3 |
| 7. Country profiles on urban development, housing and land management | 1 | 1 | 1 | 1 |
| 8. Support for the United Nations Forum of Mayors | – | – | – | 1 |
| 9. Strengthening capacities of ECE member States to develop evidence-based policy measures to meet the commitments under Madrid International Plan of Action on Ageing regional implementation strategy and the 2022 Rome Ministerial Declaration on Ageing | 1 | – | 1 | 1 |
| Seminars, workshops and training events (number of days) | 8 | 8 | 6 | 8 |
| 10. Workshops, seminars and training on urban development, housing and land management (including real estate) | 8 | 8 | 6 [8] | 8 |
| Publications (number of publications) | 6 | 2 | 4 | 5 |
| 11. Country profiles and studies on urban development, housing and land management | 4 | 1 | 2 [4] | 3 |
| 12. On population | 2 | 1 | 2 | 2 |
| Technical materials (number of materials) | 3 | 3 | 3 | 3 |
| 13. Technical guidelines on urban development, housing and land management | 2 | 2 | 2 | 2 |
| 14. Tools on mainstreaming ageing | 1 | 1 | 1 | 1 |
| Fact-finding, monitoring and investigation missions (number of missions) | 2 | 1 | 2 | – |
| 15. Fact-finding missions for policymakers in preparation for and follow-up to the country profiles on urban development, housing and land management | 1 | 1 | 1 | – |
| 16. Fact-finding missions to develop national capacities in designing and implementing ageing-related policies and programmes | 1 | – | 1 | – |
| C. Substantive deliverables |  |  |  |  |
| Consultation, advice and advocacy: advisory services to member States regarding the preparation of country profiles on urban development, housing, land management; and consultations, policy dialogues and advisory services for government officials and other stakeholders to develop national capacities in designing and implementing ageing-related policies and programmes. |  |  |  |  |
| Databases and substantive digital materials: Ageing Policies Database; ageing indicators set for global access; and access to “Generations and Gender Survey” data. |  |  |  |  |
| D. Communication deliverables |  |  |  |  |
| Digital platforms and multimedia content: websites of the subprogramme; and booklets and fact sheets, articles and social media posts. |  |  |  |  |

a	Reflects updated planned deliverables for 2026. Values in square brackets represent the number of planned deliverables reflected in A/80/6 (Sect. 20).

b	Presented in A/80/6 (Sect. 20) as 1. The Committee on Urban Development, Housing and Land Management; and 2. The Working Party on Land Administration.

c	Presented in A/80/6 (Sect. 20) as 4. The Committee on Urban Development, Housing and Land Management, its Bureau and expert bodies; and 5. The Working Party on Land Administration and its Bureau.